## Identifying Factors
Maine Department of Transportation
Resident / Inspector Guidelines
WIN#: Location: Scope:
Resident: Inspector:
Responsible Project Personnel: | Resident |  | Inspector | Done
GETTING STARTED ON YOUR PROJECT
Determine whether you are on a Federal or State funded project |  | X
Obtain a copy of the Engineer's Estimate (don't assume that it is correct) |  | X
Determine whether or not there are any municipality or other 3rd party
agreements (and who is responsible for inspection/documentation) |  | X
Subcontractor Approvals printed out and on file |  | X
DBE Utilization Form on file (Print out CUFs) |  | X
Locate Testing Minimums - Page 1 of Testing File - Line up Materials Tester |  | X
Civil Rights Poster Checklist Complete prior to Contractor starting work |  | X | X
Pin up Payroll Tracking Sheet |  | X | X
Payroll Interviews (for every contractor on the project for 5 days or more,
accumulatively, 2 interviews every 90 days are required) |  |  | X
Know your Pay Items - Method of Measurement & Basis of Payment |  | X | X
Set up Books and/or Folders (names & initials of personnel making entries) |  | X | X
Make sure that both Resident & Inspector has all tools necessary to both
inspect and document, ie., inspection tools, Construction Manual, etc. |  | X | X
Resident and Inspector discuss who is responsible for which items/activities
Resident & Inspector discuss use of books and/or Fieldbook and format
Resident & Inspector make time to discuss day to day activities
Resident & Inspector use spare time to check eachother's comps
Resident & Inspector update IDRs to FieldManager daily / weekly
PRIOR TO POSTING ITEMS FOR PAYMENT
Posting quantities should be checked prior to payment. Checks need to
be initialed and dated and in should be in RED. |  | X | X
"Buy America" - submitted by Contractor (may be found on Bill of Lading) |  | X
Material Certs - check Minimums for required certs |  | X
Use "remarks" area in IDR posting to refer to notes/comments/
documentation/FQCB to justify payment |  | X | X
Pay for 403 - HMA Items in the same week as placement to apply Escalator |  | X | X
Partial postings on unit Items need to come full circle in justification
At times we see Posting remarks make reference to future posting
remarks that are sometimes never made.
CLOSING OUT YOUR PROJECT
Send "Completion of Physical Work Notification" Letter (to MDOT, Final
Payment E-mail Address and Contractor |  | X
Using IHTD "remarks", have "checker" track back to all original
documentation |  |  | X
Don't forget 403 & 502 Incentive/Disincentives (Generate Contract Mod) |  | X
Are Payrolls / Elations Complete |  | X | X
Print out IHTD by Prop. Line once all postings have been made |  | X
Complete:
Time Charge Report |  | X
ROW Encroachment Letter |  | X
Contractor Evaluation (send copy to Contractor |  | X
Call Contracts Section to schedule an appointment for Closeout |  | X

## User Checklist
Maine Department of Transportation
Employee or Independent Contractor Checklist
[Date]
JOB DESCRIPTION:
0
User Checklist | Contractor | Employee
Control factors:
Employer provides training to worker
Worker works on-site
Worker works off-site
Company supervises worker's job
Worker has regular work hours
Worker has irregular work hours
Employer sets work hours
Financial factors:
Worker is salaried
Employer sets hourly rate
Employer provides tools/equipment to worker
Worker invests in tools/equipment for use in job
Worker receives benefits from employer
Worker has ability to have profit or loss from job
Worker pays own expenses
Relationship factors:
Worker and employer have contract for services or products
Worker has ability to hire others to complete a task
Worker and employer have long-term work relationship
Work relationship relates only to contract work
Worker performs similar projects for other companies
Worker works only for company