2011 Central District Public Health Improvement Plan -- Phase I Action Summary & Timeline

| Priority District Need/Issue & Phase 1 Action | Lead **see glossary on back for abbreviations | 2011 Timeline |
| --- | --- | --- |
|  |  | 1st quarter Jan-March | 2nd quarter April-June | 3rd quarter July-Sept | 4th quarter Oct-Dec |
| Essential Public Health Service (EPHS) #7 - Linking people to needed personal health services and assure the provision of health care when otherwise unavailable |  |  |  |  |  |
| Develop EPHS #7 Workgroup work plan and work commitments | LeeAnna Lavoie, Greater Waterville PATCH |  | Implement | developed | work plan |
| Develop & implement medication management messaging campaign encouraging patient engagement in their own care | Dr. Roger Renfrew, Redington-Fairview GH |  |  |  |  |
| EPHS #4 - Mobilizing community partnerships to identify and solve health problems | Paula Thomson, Central PH District, OLPH |  |  |  |  |
| Connect DCC to newly formed District Youth Council |  |  |  |  |  |
| EPHS #3 – Inform, educate, and empower people about health issues | Bill Primmerman, Greater Somerset PHC |  | Implement | developed | work plan |
| Form new DCC workgroup to address EPHS #3 goals |  |  |  |  |  |
| Use Central District Public Health Unit Updates and DCC website to communicate important information to DCC, LHOs, & district partners | Paula Thomson, Central PH District, OLPH |  |  |  |  |
| Use Central District Public Health Unit Updates and DCC website to communicate health evidence & best practices resources to DCC, LHOs, and district partners | Paula Thomson, Central PH District, OLPH |  |  |  |  |
| Conduct 1-2 LHO certification & training programs in 2011 | Paula Thomson, Central PH District, OLPH |  |  |  |  |
| Vaccination Coordination and Support (EPHS #3, #4, & #7) | Donna Guppy , Central District Epi, MCDC, & Paula Thomson, Central PH District, OLPH |  |  |  |  |
| Establish DCC Vaccination Workgroup & communication network |  |  |  |  |  |
| Incorporate 2011 Central DPHIP into state DPHIP template & submit to SCC | Paula Thomson, Central PH District, OLPH |  |  |  |  |
| Identify new Central DPHIP Priorities in Community (HMP) & Partner Plans | HMPs & DCC |  |  |  |  |
| Other DCC Partner Plans & Central District Issues Presented to DCC | DCC |  |  |  |  |
| Provide Input for State Health Plan & HealthyMaine 2020 | DCC |  |  |  |  |
| Review 2011 Central DPHIP Implementation Progress | DCC Workgroups & DCC |  |  |  |  |
| Incorporate Priorities Identified in Community & Partner Plans | DCC |  |  |  |  |
| Update Central DPHIP for 2012 | DCC Workgroups & DCC |  |  |  |  |

Abbreviation Glossary:

Central District Epi:   Central District Infectious Disease Epidemiologist, Maine Center for Disease Control

Central PH District, OLPH:   Central Public Health District, Office of Local Public Health, Maine Center for Disease Control

DCC:   Central District Coordinating Council

DPHIP:   District Public Health Improvement Plan

EPHS:   Essential Public Health Service

Greater Somerset PHC:   Greater Somerset Public Health Council

Greater Waterville PATCH:   Greater Waterville Planned Approach to Community Health

HMP:   Healthy Maine Partnership

LHO:   Local Health Officer

Redington-Fairview GH:   Redington-Fairview General Hospital

SCC:   State Coordinating Council for Public Health