## Sheet1
Objective | Action Step | 2011-01-01 | 2011-04-01 | 2011-07-01 | 2011-10-01 | 2012-01-01 | 2012-04-01 | 2012-07-01 | 2012-10-01
Increase adult flu shot rates | Research background info
Identify worksites currently offering flu clinics | bar: 2011-01-01 to 2011-04-01
Identify who is touching worksites | bar: 2011-01-01 to 2011-04-01
Identify worksites with >50/<50 employees | bar: 2011-01-01 to 2011-04-01
Contact organizations that affect worksites | bar: 2011-07-01
Contact private orgs incl. Maxim, Concentra | bar: 2011-07-01
Research evidence of effectiveness/impact | bar: 2011-01-01 to 2011-07-01
of worksite flu shots
Implementation steps
Pull together groups of people conducting | bar: 2011-10-01
similar activities in same geographic areas | bar: 2011-10-01 to 2012-01-01
Assess individual barriers to flu shots | bar: 2011-10-01 to 2012-01-01
Look for flu shot toolkit for worksites
Education
Find out what education materials are available | bar: 2011-10-01 to 2012-04-01
Determine how best to distribute materials & | bar: 2011-10-01 to 2012-04-01
how to piggyback onto existing initiatives
Presentations to organizations that affect worksites | bar: 2012-07-01 to 2012-10-01
Distribute educational materials to worksites | bar: 2012-07-01 to 2012-10-01
Promote flu shot clinics
Healthcare workers: determine how many are | bar: 2011-07-01 to 2012-01-01
vaccinated; look for successful models to replicate
Look for pockets where no vaccine clinics | bar: 2011-07-01 to 2012-01-01
are being held; visit employers to assess barriers
Ask staff at Maxim/PHN/Human Resource nurses | bar: 2011-07-01 to 2012-01-01
who give flu shots what they've heard re: barriers
Meet with large worksites with occ health programs | bar: 2012-04-01 to 2012-10-01
to discuss how to provide/increase flu shot clinics
Build partnerships across the district | Identify organizations that provide flu clinics | bar: 2011-07-01 to 2011-10-01
Ask what others are doing and how we can help | bar: 2011-07-01 to 2011-10-01
them be more effective | bar: 2012-01-01 to 2012-04-01
Link organizations that have similar goals in the
same geographic areas; encourage collaboration
Provide presentations to other organizations and | bar: 2011-01-01 to 2011-10-01
collaboratives in western Maine re:DCC & DPHIP
Develop system to track progress | Develop spreadsheet of worksites and counts | bar: 2011-07-01 to 2012-01-01
Develop an electronic directory/ spreadsheet of | bar: 2011-01-01 to 2012-01-01
organizations providing vaccinations and organizations
affecting worksites with contact information
Evaluate process/outcome | Process evaluation
Monitor the number of worksites contacted | bar: 2012-04-01 to 2012-10-01
Monitor the number of presentations offered | bar: 2012-04-01 to 2012-10-01
Monitor the amount of educational materials | bar: 2012-04-01 to 2012-10-01
distributed
Outcome evaluation
Determine the number of workers vaccinated | bar: 2011-01-01; 2012-10-01
at worksite flu clinics at beginning and end of
the project period
Review District Profile flu vaccine rates at | bar: 2011-01-01; 2012-10-01
beginning and end of the project period