Template updated 03/2012

| District: York | Date: December 13, 2012 |
| --- | --- |
| Brief review of decisions and outcomes from Executive Committee and DCC meetings held since the last SCC meeting. For agendas and copies of minutes, please see district’s website at: http://www.maine.gov/dhhs/boh/olph/lphd/index.shtml Two Executive Committee (EC) meetings and one Full District Coordinating Council meeting for York District Public Health Council (YDPHC) were held since the last SCC meeting. The Executive Committee meetings were held on September 19th, 2012, and October 10t, 2012, and the District Coordinating Council meeting was held on November 14th 2012. The September 19th meeting focused on the Community Transformation Grant (CTG) and Healthy Maine Partnership (HMP) activities. This included status in the District; next steps on District Public Health Improvement Plan (DPHIP) implementation; and preliminary planning for the September 19th York District Public Health Council (YDPHC) Quarterly Meeting. The October 10th meeting focused planning for the upcoming Full District Coordinating Council meeting. Also discussed and review was criteria for membership, and how communications should be sent. The November 14th meeting focused on the State health assessment roll out for the York district data, and working reviewing the current district priorities and nominating possible new ones. |
| Ongoing or upcoming projects or priority issues: Continued Recruitment of faith-based, business and private sector membership Implementation of the Community Transformation Grant Initiative DPHIP alignment with CTG activities Reenergizing DPHIP Focus Work groups Continued development of the Council’s strategic work plan Revisiting & Strengthening the Council's Governance & Structure |
| Progress with District Public Health Improvement Plan: Activities planned for completion during the quarter: All three DPHIP focus areas work groups continue to meet to guide the work outlined in the DPHIP's focus areas work plans. Considering there are no new or additional resources available to do this DPHIP work, work group leaders have kept the momentum going and have judiciously delegated tasks to partners and participating community members. Workgroup leaders have been successful in obtaining resources and support from community partners and local business. The new District Liaison will make every effort to attend or call into workgroup sessions to offer guidance and support. Presently the Obesity and Immunization Workgroups are on schedule and the Access workgroup held a phone conference over this period as well. Successes achieved Obesity Workgroup has met once during this quarter on August 15th. The group continues to work with community members and to revisit and update their plans and logic model activities in alignment with CTG activities for the upcoming year. The Access work group held a phone conference in October for updates. Barriers encountered-Time & resources |
| Progress with Community Transformation Grant: -Held CTG kick off on September 19th; 31 stakeholders were in attendance -Year 2 work plan and Budget developed and submitted to state - CTG Oversight Committee met November 7th - Continued to train childcare providers in Active Play: Physical Activities for Young Children. Over 30 childcares have received training this fall. Trainings will resume in January 2013 - CTG Coordinator, in partnership with the Let’s Go Dissemination Partners in York County, have been enrolling childcares and schools under CTG. Currently there are five schools and fifteen childcares enrolled. - Partnered with the Let’s Go Home Office and Cumberland County CTG to provide crediting training to York County Nutrition Directors on November 29th. -Attended CTG Coordinators Regional Meeting in Bangor October 26th - CTG Coordinator active member of the Partners for a Hunger Free York County collaborative; working with coordinator on farm to school work. - Trained York County Head Starts on the Let’s Go model on November 26th - Participated in all CTG TA calls |
| Structural and Operational changes, including updates in membership. |
| In-district or multi-district collaborations: Noble High School is supporting the Making Change training by providing a free location for the training and also purchasing food for the attendees. |
| Other topics of interest for SCC members: Discerning potential public health forums for YDPHC to host. |