## Slide 1: SIM Program Status
FFY Q1, 2014

## Slide 2: SIM Program FFY 14 Q1 Status
SIM Program Overall Status and Description: |  | 
Overall Status |  | Key delays and issues in evaluation and concern regarding SIM contract completion create the ‘caution’ in overall status
Status by Objective | Status | Status Description
Objective 1: SIM Governance Process/Structure |  | All Governance meetings have been held in FFY14 1Q, with strong attendance and engagement Governance process, decision making continues to be refined w/ experience with actual development and issue escalation All Partners have reported subcommittee governance in green status
Objective 2: SIM Operational Plan |  | Main processes – project reporting, invoicing, on track Governance decision making/informational flow process in process of being documented SIM Budget/Contract Coordinator role filled Moving forward w/ hiring of SIM Project Coordination Administrative assistance secured Evaluation Award is in appeal process Significant delays and risk to effective SIM evaluation are risk
Objective 3: SIM Program Plan |  | Great progress made in plan synchronization in 1st Quarter which led to project plan adjustments and deeper understanding of integration
Objective 3: SIM Budget |  | Budget Coordinator hire has tremendously moved budget management capability forward Through 1st Q, finished approx. 95% of budget

## Slide 3: SIM Program FFY 14 Q2 Outlook
Objective | Outlook | Outlook Narrative
Objective 1: SIM Governance Process/Structure |  | SIM Governance processes better aligned and organized so that information reporting and committee ‘ask’ should be clearer and effectively organized
Objective 2: SIM Operational Plan |  | Updated 30 month partner contracts to be submitted to AG for full review. Need to have them approved by the AG by March 15 to ensure no interruption in SIM services Evaluation process at risk of significant delay due to appeal Additional SIM contracts for later starting SIM objectives need to be further defined and RFP process started Risk Mitigation Process to be developed and implemented SIM hiring process scheduled to be completed in 2Q
Objective 3: SIM Program Plan |  | SIM Plans have been baselined and reporting process developed and implemented which should enable effective plan monitoring and communication
Objective 3: SIM Budget |  | SIM funds effectively unrestricted which will enable State to meet invoicing requirements through 2Q

## Slide 4
Chart: Testing Phase Year 1, Quarter1 10/1/13 -12/31/13
| State | Other | MHMC | QC | HIN | LG | Total
Budget | 169226.5 | 31250 | 934059 | 405543 | 956187 | 0 | 2496265.5
Spent | 98532.05 | 31249.97 | 878519 | 405546.51 | 956187 | 0 | 2370034.53

## Slide 5: SIM Program Activities
Appendix

## Slide 6: SIM Program Status FFY 14 Detail
Objective | Status | Status Description
SIM Staffing Plan |  | SIM Budget/Contract Coordinator role filled Administrative assistance secured Moving forward w/ hiring of SIM Project Coordination
SIM Process Development |  | Main processes – project reporting, invoicing, on track Governance process, decision making continues to be refined w/ experience with actual development and issue escalation Governance decision making/informational flow process in process of being documented
Contracting |  | - Updated 30 mo contracts to be submitted to AG for full review. - Need to have them approved by the AG by March 15 to ensure no interruption in SIM services
Evaluation Process and Contracting |  | Award is in appeal process Significant delays and risk to effective SIM evaluation are at risk