## Slide 1: SIM- Data Infrastructure Subcommittee
December 4, 2013

## Slide 2: Agenda Overview
Agenda review | 5 min
Review and adoption of minutes | 10 min
Feedback adopted from previous meeting: Behavioral Health RFP Patient Portal (PHR) Blue Button Pilot BH RFP Criteria (word document hand out) Criteria- Patient Portal (PHR) Blue Button Pilot | 10 min 40 min 20 min
January Meeting: –Focus on other SIM subcommittee activities Meetings beyond January 2014 Interested Parties Public Comment | 5 min 10 min 10 min

## Slide 3: Data Infrastructure Charge Statement
“The SIM Data Infrastructure Subcommittee will advise key projects and objectives within the scope of SIM towards improving data infrastructure systems and technology across the state of Maine.
Specifically, advising on technical capabilities related but not limited to data infrastructure investments, use of national data standards and clinical and administrative data availability and interoperability. The Subcommittee will advise the SIM partners and the Steering Committee on areas of alignment of SIM data and analytics infrastructure activities with other public and private projects underway across the State.”
Notes: Elevator speech

## Slide 4: Behavioral Health RFP: Updates
Language:
  Incentive vs. Reimbursement**
  Grant vs. participant awardees**
Size: Intention to select a variety of sizes of organizations who meet the requirements of the RFP (small/medium/large)
Organizations targeted: removed reference to substance abuse specific programs, aligned services provided language with MaineCare’s BHHO RFP language
Emphasized:
  Quality milestone, more financial weight
  Aligned quality milestone with other SIM activities
  Participation of awardees in BH SIM workgroup activities related to quality

## Slide 5: Behavioral Health RFP Milestones- Updated
Milestone 1- EHR- $35,000
  $10,000 out of $35,000 paid for being awarded, $25,000 due at milestone attestation (self attestation with established criteria)
  MU certifications is not the priority in this context (but is recognized)
  EHR version, upgrade, optimization and interoperability is the priority focus
  Must demonstrate by end of Milestone one test message for HL7-ADT at minimum
Milestone 2-HIE data connection- $10,000
  HIE Participant agreement in place (fees waived under SIM)
  Onboarding and education process completed
  Go live with ADT Interface, testing and go live ACTIVE
  Project plan for ORU (Labs) data go live
  Plan and process for patient Opt-In
Quality Measure and Milestone 3- $25,000
  Must understand applicants resource and commitment to quality measurement
  Measure min. of 1 QI measure electronically using HIE, measure must be aligned with SIM activities (PTE BH workgroup, MaineCare BHHO)

## Slide 6: BH RFP Timeline
Timeline for RFP Process, (adjusted from original Project Plan)
  November- Data Subcommittee- introduce and discuss/input on criteria, introduce RFP for review
  December- Data Subcommittee- adopt RFP criteria, process in order to move forward
  January – Steering Committee Approval & RFP Released
  February – Review of Proposals, into March
  March – Announcement of Awards
Notes: Does DI subcommittee get a report out on the break down/impact of the BH orgs. selected?

## Slide 7: Patient Portal-Blue Button/Patient Health Record (PHR) Pilot
Provide Maine patients with access to their statewide HIE record by:
  Patients will be able to access a Clinical Summary of their statewide HIE record, via their provider’s web-based portal
  Information will be presented as a downloadable and printable PDF document
  Formatting of a draft document is in process and will be reviewed by HIN’s Consumer Advisory Board at the end of November
HIN will conduct a 12-month pilot with a selected community/provider(s) to test and modify technical requirements and test the patient education and engagement process to support future roll out
Projected start date of project is February 2014

## Slide 8: Pilot Selection Process
This is now a competitive process, however this is a voluntary process based on interest and required criteria to make it work. Intent is to roll out a state wide effort based on the results of the pilot.
Review today the:
Criteria

## Slide 9: PHR, Portal Pilot Criteria Process
With initial guidance from HIN stakeholders, including the Consumer Advisory Committee
Data Infrastructure input 11/14 and 12/4
HIN Consumer Advisory Committee input 11/26
Release of Letter of Intent with Selection Survey included once approved by D.I. Subcommittee
9

## Slide 10: PHR, Portal Pilot Criteria for Scoring
10
Topic | Criteria Component | Must Pass
HIE Participation Status | Currently participating in the HIE? | Yes
PHR Status | Active Patient Health Record Portal, currently in use, fully implemented? | Yes
 | Must be implemented in ambulatory primary care setting | Yes
 | Greater than 500 active registered Patient users of PHR | Yes
Access to care | Must accept payment from Medicaid/Medicare as eligible providers | Yes
 | Do you have services in critical access community? | No
 | Do you include FQHC's? | No
 | Providing Care Management Services in primary care, inpatient, CCT etc. where this tool can be used to engage the patient in care coordination? | No
 | Providing Continuity of Care Document's to patients currently? | No
Patient Engagement | Are you currently organized with Patient/Family Advisory groups/committees that could be used to support this pilot process? | No
Technical Requirements | Is your organization able to forward your OID (Organization ID) and patient MRN to HealthInfoNet when a clinical summary document (PDF) is requested? | Yes
 | Is your organization able to receive a clinical summary document (PDF) from HealthInfoNet into your patient portal? | Yes
Notes: What are we missing in the survey?

## Slide 11: Upcoming Meetings
Date & Time | Expected Project Agenda Items
Wednesday, January 8th, 2p-4p | SIM Subcommittee presentations of related work and update on projects: Payment Reform and Delivery System Reform
Wednesday, February 5th, 2p-4p | TBD
Notes: Data use request process from HIN? Notifications go live and impact on Delivery? IHOC? Report outs from MHMC and QC, Health Home Stage B focus, Quality reporting focus- SAMH reporting issues? CDC-Immpact reporting?

## Slide 12: Meeting Planning
Move to quarterly meeting after January
Special meeting could be called as needed
Meet in person (quarterly not to onerous)