LAND USE REGULATION COMMISSION

MAINE DEPARTMENT OF CONSERVATION

2009-2010 REGULATORY AGENDA

July 31, 2009

Amended September 16, 2009

AGENCY UMBRELLA - UNIT NUMBER: 04-061

AGENCY NAME: Land Use Regulation Commission

CONTACT PERSON: Eliza Townsend, 22 SHS, Augusta, ME 04333, 287-4901

EMERGENCY RULES ADOPTED SINCE LAST REGULATORY AGENDA: None

EXPECTED 2009-2010 RULE-MAKING ACTIVITY:

CHAPTER 10: Land Use Districts and Standards, Matters Concerning Expedited Wind Energy Development Areas

STATUTORY AUTHORITY: 12 MRSA §684

PURPOSE: P.L. 2009, ch. 415, “An Act to Correct Errors and Inconsistencies in the Laws of Maine”, Part D; effective June 17, 2009, which amended P.L. 2007, ch. 661, §6, requires the Commission to adopt certain rules amending the wind power expedited permitting area by June 1, 2010.

ANTICIPATED SCHEDULE: Issue proposed amendments by October 2009; adopt amendments by February 2010; submit for legislative review by March 2010.

AFFECTED PARTIES: Landowners and others who hold interests in lands under LURC

jurisdiction.

CONSENSUS-BASED RULE DEVELOPMENT: not contemplated

CHAPTER 10: Land Use Districts and Standards, Miscellaneous Changes

STATUTORY AUTHORITY: 12 MRSA §684

PURPOSE: These rules establish land use standards for lands under LURC jurisdiction. They need to be updated to address several issues which have become obvious through experience gained from applying current rules including: applying rules to the entire jurisdiction that now apply only to the Rangeley area, differentiating between different types of trails, clarifying clustering provisions for subdivisions, defining expansion of nonconforming structures, developing rules for special events, identifying situations where deer wintering areas may need to be protected through other than the normal procedure because of rapidly changing ownerships, promulgating rules to provide resource protection consistent with that provided under the NRPA in organized areas of the state, and revising flood plain management rules to comply with FEMA requirements.

ANTICIPATED SCHEDULE: Issue proposed amendments by December 2009; adopt amendments by April 2010; submit for legislative review by January 2011.

AFFECTED PARTIES: Landowners and others who hold interests in lands under LURC

jurisdiction.

CONSENSUS-BASED RULE DEVELOPMENT: not contemplated

CHAPTER 1: General Provisions

STATUTORY AUTHORITY: 12 MRSA §684

PURPOSE: These rules need to be revised to assess fees for all permitted activities disturbing areas within 25 feet of water bodies and within wetlands and for processing notifications, and to include water extraction and other activities in the schedule of fees.

ANTICIPATED SCHEDULE: Issue proposed amendments by December 2009; adopt amendments by April 2010; submit for legislative review by January 2011.

AFFECTED PARTIES: Landowners and others who hold interests in lands under LURC jurisdiction.

CONSENSUS-BASED RULE DEVELOPMENT: not contemplated

CHAPTER 4: Rules of Practice

STATUTORY AUTHORITY: 12 MRSA §684

PURPOSE: These rules need to be updated to address several issues including identifying when a request for a public hearing may be addressed by staff rather than the Commission.

ANTICIPATED SCHEDULE: Issue proposed amendments by December 2009; adopt amendments by April 2010; submit for legislative review by January 2011.

AFFECTED PARTIES: Landowners and others who hold interests in lands under LURC

jurisdiction.

CONSENSUS-BASED RULE DEVELOPMENT: not contemplated

CHAPTER 5: Rules for the Conduct of Public Hearings

STATUTORY AUTHORITY: 12 MRSA §684

PURPOSE: These rules need to be revised to allow flexibility in the order of those testifying at public hearings and to correct typographical errors.

ANTICIPATED SCHEDULE: Issue proposed amendments by December 2009; adopt amendments by April 2010; submit for legislative review by January 2011.

AFFECTED PARTIES: Landowners and others who hold interests in lands under LURC

jurisdiction.

CONSENSUS-BASED RULE DEVELOPMENT: not contemplated

CHAPTER 10: Land Use Districts and Standards, Aquifer Protection

STATUTORY AUTHORITY: 12 MRSA §684

PURPOSE: The Commission established the Aquifer Protection Subdistrict many years ago, but, up until now, has not had the necessary information to apply the zone except in very limited situations. With the recent availability of sand and gravel aquifer mapping and the wellhead protection program, the issue of the Commission’s protection of groundwater supplies needs to be reviewed and revised as appropriate.

ANTICIPATED SCHEDULE: Issue proposed amendments by September 2010; adopt amendments by January 2010; submit for legislative review by January 2011.

AFFECTED PARTIES: Landowners and others who hold interests in lands under LURC jurisdiction.

CONSENSUS-BASED RULE DEVELOPMENT: not contemplated

CHAPTER 10: Land Use Districts and Standards, Rules to Implement Comprehensive Land Use Plan Recommendations

STATUTORY AUTHORITY: 12 MRSA §684

PURPOSE: The Commission anticipates adopting its revised Comprehensive Plan in 2010. It is expected there will be certain recommendations contained in the Plan that will require rule changes to implement.

ANTICIPATED SCHEDULE: Issue proposed amendments by June 2010; adopt amendments by October 2010; submit for legislative review by January 2011.

AFFECTED PARTIES: Landowners and others who hold interests in lands under LURC jurisdiction.

CONSENSUS-BASED RULE DEVELOPMENT: not contemplated