Request for Proposals

for the

Provision of Integrated Healthcare in Maine County Jails and the Department of Corrections

Timeline

DRAFT #3 3/8/10

| Date | Action | Responsible Party | Completed |
| --- | --- | --- | --- |
| March 2010 | Elicit conceptual support from CWG and BOC |  |  |
| March – April 2010 | Seek funding for RFP consultant e.g. MEHAF, BOC, DOC, other, and determine appropriate hiring mechanism e.g. sole source, RFP, state/county employee. One year position July 1, 2010 - June 31, 2011. (estimate 15 hrs per wk x 52 wks = 780 hrs ) |  |  |
| March 2010 | Issue standardized health care statistical form for state and county facilities Six (6) month data collection period April – September 2010. Focus group to determine other data needs. |  |  |
| May – July 2010 | Educate stakeholders to the scope and timeline for the RFP. Determine level of interest and potential participants in RFP development. |  |  |
| May – June | Begin review and revision of State and County medical, mental health and substance abuse policies as part of RFP project. |  |  |
| June 2010 –ongoing as needed | Solicit technical guidance from Division of Purchases on multijurisdictional RFP project |  |  |
| May – June 2010 | Interview and select RFP consultant. |  |  |
| July 2010 | Begin identification and drafting of RFP components |  |  |
| July 2010 | Begin identification of potential Bidders |  |  |
| August 2010 | Analyze and summarize DHHS Stand Down Data |  |  |
| September 2010 | Outline necessary administrative and clinical oversight structure that will be needed in order to manage a contract of this scope and cost. |  |  |
| October 2010 | Analyze and summarize six (6) month snapshot of Maine correctional health care statistics. |  |  |
| October 2010 | Finalize RFP participants |  |  |
| October 2010 | Determine the scope of RFP Bidders conferences and facility site visits. |  |  |
| October 2010 | CWG to present draft RFP to BOC for review |  |  |
| November 2010 | Complete drafting of RFP components. Finalize RFP and request review by Division of Purchases. |  |  |
| December 2010 | Release RFP |  |  |
| December 2010 – January 2011 | RFP Proposal response management |  |  |
| February 2011 | RFP Proposals due. Initiate RFP scoring/evaluation process. |  |  |
| March 2011 | Announcement of scoring results and selection of Vendor |  |  |
| March 2011 | Initiation of transition plan. |  |  |
| March – June 2011 | Negotiate multiple contracts resulting from the RFP |  |  |
| July – September 2011 | Implementation of transition plans. Vendor expected to have significant presence at facilities. |  |  |
| October 1st 2011 | Start date of new Vendor |  |  |