## Cover Sheet
revised 05 April 2021 | AdvantageME CT# | 0000
State of Maine
C O N S T R U C T I O N C O N T R A C T
Change Order
Project name |  | Change Order Number: | 1
location / school / campus
|  | Issue Date of this Document: | 2022-12-31
Contractor Company name
address |  | BGS Project No.: | n
city state zip code |  | Other Project No.: | x
Cost Change |  | Show Deduct as a negative number, e.g.: "-$850".
| Add | Deduct | Total
Net Amount of this Change Order | 0 | 0
Net Amount of Previous Change Orders | 0 | 0
Net of Change Orders to Date | 0 | 0 | 0
Original Contract Amount |  |  | 0
Revised Contract Amount |  |  | 0
Time Change |  | Show Deduct as a negative number, e.g.: "-8".
| Add | Deduct | Total
Net Calendar Days Adjusted by this Change Order | 0 | 0
Net Calendar Days Adjusted by Previous Change Orders | 0 | 0
Net of Change Orders to Date | 0 | 0 | 0
Original Contract Final Completion Date |  |  | 2023-12-31
Revised Contract Final Completion Date* |  |  | 2023-12-31
Consultant (Architect or Engineer)
Type firm name here
Type person's name, title here
| signature |  | date
Contractor
Type company name here
Type person's name, title here
| signature |  | date
Owner
Type contracting entity name here
Type person's name, title here
| signature |  | date
Type Entity, such as "Owner's Rep", or "not used"
Type entity name here
Type person's name, title here
| signature |  | date
Bureau of General Services
Division of Planning, Design & Construction
Type person's name, title here
| signature |  | date
Attach the "List of Change Order Items" sheet, plus all supporting documentation for each Change Order Item.
|  | Substantial Completion Date: the deadline for first beneficial use by Owner, as certified by Consultant. | 2023-12-01
|  | * Contract Final Completion Date: the Contractor's final completion deadline for contract work. | 2023-12-31
|  | Contract Expiration Date: the Owner's deadline for internal management of contract accounts; | 2024-02-29
Contract Expiration Date does not directly relate to any contract obligation of the Contractor.
Formulas:
n = SUM(D26,[n, row above])

## List of Items
revised 05 April 2021 |  |  |  |  | State of Maine Change Order
List of Change Order Items
Project name |  |  |  | C. O. Number: | 1
Contractor Company name
CO Item No. | CP No. | Item Name | Reason Code | Calendar Days* | Cost
1 | 1 | Type brief name of Change Order Item here |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  |  | 0 | 0
|  |  | Totals | 0 | 0
Reason Codes
EO | Error or omission of Consultant |  | * Calendar Days shows Contract Final Completion Date impact only.
UC | Unforeseen job site condition
OC | Owner-generated change
RC | Regulatory authority-generated change
CC | Contractor-generated change
Attach this sheet to the BGS "Change Order" cover sheet (with cost and time summaries, and signatures). Attach a "Details" sheet, and other supporting documentation, for each Change Order Item listed above.

## Details
revised 05 April 2021 |  |  |  | State of Maine Change Order
Details of Change Order Item
Project name |  |  | Change Order Item Number | 1
location / school / campus |  |  | CP (Change Proposal) Number | 1
|  |  | Issue Date of this Document: | 2021-10-31
Contractor Company name
address |  |  | BGS Project No.: | n
city state zip code |  |  | Other Project No.: | x
Change Order Item | Type name of Change Order Item here
Description of Work | Type brief description here of work scope here.
Reason or Necessity of Work | Type brief justification for change here.
Cost Breakdown | Work by Subcontractor only | Work by Sub and Contractor | Work by Contractor only
Subcontractor base cost | 0 | 0
Subcontractor markup | 0 | 0
Contractor base cost |  | 0 | 0
Contractor markup | 0 | 0 | 0
Subtotal | 0 | 0 | 0
Compensation | lump sum |  | Total Cost | 0
Initiated by | Consultant |  | Calendar Days* | 0
Reason Code | CC |  | Supporting Documentation | is attached
Owner's Rep | lump sum | Consultant | is attached
not used | cost plus a designated rate | Contractor | is not needed
| cost plus a fixed fee | Owner
unit prices
EO | UC | OC | RC | CC
Error or omission of Consultant | Unforeseen job site condition | Owner- generated change | Regulatory authority-generated change | Contractor- generated change
* Calendar Days shows Contract Final Completion Date impact only.
Consultant | Type firm name here
(Architect or Engineer) | Type person's name, title here
|  |  | signature | date
Contractor | Type company name here
Type person's name, title here
|  |  | signature | date
Owner | Type contracting entity name here
Type person's name, title here
|  |  | signature | date
Owner's Rep | Type entity name here
Type person's name, title here
|  |  | signature | date
Bureau of | Division of Planning, Design & Construction
General Services | Type person's name, title here
|  |  | signature | date