I. Project Title and Applicant’s Organization

| Project Title | Medomak River Watershed-Based Plan Development |
| --- | --- |
| Applicant’s Organization | Town of Waldoboro |

- Waterbody and Watershed Information

a.  Background

| Waterbody Name | Medomak River |
| --- | --- |
| Waterbody Size (e.g., lake acres, stream miles) | 32.3 miles |
| Watershed Area (acres or square miles) | 106 square miles |
| Watershed Town(s) | Liberty, Appleton, Washington, Union, Waldoboro, Bremen and Friendship |
| Comprehensive Plan Adoption (List watershed towns and whether they have adopted plans.) | Currently, none of the towns have consistent adopted plans. |

b.  Waterbody and Watershed Physical Characteristics

The Medomak River is a 32.3-mile-long river with its headwaters beginning in the Town of Liberty and flowing generally south through the towns of Appleton, Washington, and Union. The river then maintains its course through Waldoboro where it reaches head of tide just below Route 1. It is then bounded by the towns of Bremen and Friendship before entering Muscongus Bay. The entire watershed area is 106.1 square miles with 80 square miles in the freshwater watershed and 26 square miles below head of tide. The largest portion of the full watershed (45.3% or 48.1 square miles) and approximately the lower half is located in the Town of Waldoboro.

c.  Description of Waterbody Uses and Value

The Town of Waldoboro is the leading softshell clam producer in the State of Maine, despite experiencing frequent closures due to NPS pollution (primarily fecal bacteria). Combined, the towns of Waldoboro, Bremen, and Friendship caught 1,217,256 lbs. of softshell clams with a total value of $2,638,724 in 2016. Waldoboro alone caught 917,749 lbs. (valued at $2,001,459) from its 175 registered harvesters. In total, this is 16.9% of the total economic value of softshell clams in the state in 2016 (total value of $15,656,386).

In addition to the economic benefit, the diverse terrestrial and aquatic wildlife on the river provides a recreational and scenic destination for outdoor enthusiasts, local community members, and tourists. The Dutch Neck Boat Ramp provides a point of public access to the river. The public can also enjoy the river from multiple preserves maintained by the Medomak Valley Land Trust (MVLT) in both the estuarine and freshwater corridors of the river (e.g., Reef Point Preserve, Medomak River Corridor Preserve).

- NPS Pollution Problem / Need:

              - Water Quality Listing Status

| Is water quality listed as impaired? | Yes |
| --- | --- |
| If impaired, what is the listed cause(s) and/or impaired use? | Elevated fecal indicators, Dissolved oxygen |
| Name and date of any DEP TMDL report(s) for the waterbody. | Not applicable |

              - Water Quality Overview

The main stem of the river is categorized as Class A until Wagner’s Bridge Road in Waldoboro where it drops to Class B until Old Route 1 (head of tide). All freshwater tributaries in the watershed are Class A. The tidal section is Class SB.  The Medomak River Estuary is listed on the NPS Priority Watershed list as impaired. Maine DEP 2014 Integrated Water Quality Report lists the Medomak River as impaired for dissolved oxygen and elevated fecal indicators.  The cause of the dissolved oxygen impairment is a discharge which has been removed; it is still listed because no data exists yet to remove the impairment.  Several areas of the river are closed for shellfish harvest as described above.

The Maine DEP Integrated Report lists the Medomak River in two categories.  Although not related to this project, a 156 acre section is listed due to low dissolved oxygen under Category 4-B-1:  Estuarine and Marine Waters Impaired by Pollutants-Pollution Control Requirements Reasonably Expected to Result in Attainment.  The cause is a discharge (spray irrigation) that has been removed.  It is also listed in Category 5-B-1(a):  Estuarine and Marine Waters Impaired by Bacteria Only-TMDL Required.  This includes a 1,218 acre section (DMR Shellfish Closure areas) of the river impaired due to elevated fecal indicator bacteria.

The Maine Department of Marine Resources (Maine DMR) shellfish closure areas include prohibited (three areas), restricted (six areas), conditionally approved (two areas), and seasonally closed (one area). Depending on seasonal precipitation, these closures can account for more than half of the harvest year. The economic value of softshell clams from the Medomak River has the potential to double if these conditional closures are removed.

              - Summary of Past Watershed Assessments and Most Important Nonpoint Sources

Since 2013, the Medomak Task Force (see below) has conducted several assessments and surveys:

- Surveyed 210 properties in 2013 and 2014. Of these properties, 12 problem properties were identified and referred to the appropriate agency (either the Town’s Utility District, DACF, or DEP).

- High fecal coliform results at Winslows Mills led to the discovery that a cracked condenser at a local company was allowing river water to leak into the condenser water, where the bacteria from the river grew exponentially and were discharged back to the river at very high levels (E. coli in the 7,500 col/100mL range and total coliforms over 240,000 col/100mL). The company was very proactive and thorough in repairing and ultimately replacing the condenser.

- Based on a review of five years of DMR data, conducted a canine detection study in 2014 to focus on human sources of bacteria at 18 different sampling sites.

- Based on these findings, in 2015 the Task Force chose to focus on small streams that flow directly into the prohibited, restricted and conditional areas of the river, and sampled all 37 streams that fit this description.

- The small stream study informed the Task Force to focus on 21 priority streams in 2016 with the use of Microbial Source Tracking, an advanced sampling technique that identifies the source species (or species group) contributing to fecal pollution. Results have further narrowed the areas of concern; next steps involve further property surveying and closer, more intensive monitoring of high priority streams.

Based on the assessments conducted to date, agriculture, residential septic systems, industrial pollutants, and waterfowl appear to be the primary NPS sources associated with the Medomak River’s bacteria impairment.

              - Description of Watershed Activities to Address NPS Sources

With significant encouragement from the Shellfish Committee, the Town of Waldoboro petitioned the state to commit staff and resources to address fecal bacteria pollution on the Medomak River. Their efforts created a strong inter-agency collaboration (hereafter referred to as the ‘Medomak Task Force’) beginning in 2013 and included representatives from the Maine DMR, the Department of Environmental Protection (DEP), the Department of Agriculture, Conservation, and Forestry (DACF), the Shellfish Committee, the Town of Waldoboro, the Waldoboro Utility District, and the Medomak Valley Land Trust. This successful collaboration has worked tirelessly to eliminate sources of fecal bacteria from entering the river. This includes investigation and remediation of sources from agriculture, residential septic systems, industrial pollutants, and waterfowl.

Efforts to abate NPS pollution have proved successful, evidenced by a recent removal (October 2016) of Back River Cove from the prohibited list.  Despite these efforts, the Medomak River estuary still suffers from frequently elevated bacteria counts that cause significant portions of the river to remain on Maine DMR’s rainfall closure list.

- Purpose:

The purpose of the proposed project is to produce a detailed, user-friendly watershed-based management plan for the Medomak River Estuary, which will guide watershed restoration efforts to reduce fecal bacteria contamination and meet the ultimate goal of removing the conditional shellfish closures in the estuary. The plan will include the nine minimum elements considered by EPA to be critical for achieving improvements in water quality as required under the Nonpoint Source Program and Grants Guidelines for States and Territories (April 2013).

- Project Duration:

| Project Start Date | October 2017 |
| --- | --- |
| Project Completion Date | April 2019 |

- General Project Plan

The WBP will focus on the portion of the watershed located below Medomak Pond. This includes the small tributary area to the northwest of Medomak Pond. This focus area was created by merging the National Hydrography Dataset HUC12 boundary with the existing estuarine watershed boundary. This was done due to the significant bacterial contamination noted in this portion of the watershed that is causing a significant loss in access to shellfishing in the river.

The Town of Waldoboro will manage the overall project with the assistance of the Medomak Valley Land Trust. The Town will also retain a project consultant to assist with the technical aspects of the project. The consultant will be assisting the Town and project stakeholders with all of the project tasks. The project consultant (hired under the appropriate procurement practices outlined below), will retain the following key characteristics:

- Have significant experience with project management at the local level, including experience with landowner and stakeholder engagement, meeting facilitation, and project scheduling.

- Have a solid understanding of fecal indicator bacteria, bacteria fate and transport in estuarine environments, and water quality monitoring studies. The consultant will be familiar with using proper quality assurance (QAPP) State protocols.

- Be well-acquainted with Maine WBP development, writing, and follow-through.

The Town will use appropriate competitive procurement procedures to secure assistance with plan development by the aforementioned project consultant. All bids requested by the Town of Waldoboro are competitive in nature, and the Town makes every effort to utilize underrepresented businesses. Products and services paid for with grant funds will be carried out using procurement procedures as described under Section 4 of DEP’s Nonpoint Source Grant Administrative Guidelines. This project will be conducted to meet applicable quality assurance procedures in the DEP document “Maine Section 319 NPS Management Program Quality Assurance Program Plan, 2011” http://www.maine.gov/dep/water/grants/319.html.

The Medomak River WBP project will rely heavily on the input of a technical advisory committee (TAC) that will include and expand upon the current Medomak Task Force, including individuals who can help identify fecal bacteria sources and locations and provide input into developing a realistic and action-oriented WBP. The TAC will refine methodologies for all field assessment tasks and will oversee the development of the Sampling and Analysis Plan (SAP) for the Storm Event Sampling (Task 5).

Watershed education and outreach needs will be addressed by informing the public about the project and posting project updates on the Town’s website and through press releases. Press releases will contain information about the nature and scope of the project as well as information on NPS pollution.

All press releases, outreach materials, project signs, and plans will acknowledge that the project is funded in part by the United States Environmental Protection Agency (EPA) under Section 604(b) of the Clean Water Act. EPA’s logo will not be included on materials unless the Grantee receives prior instruction and approval from EPA. Refer to the Grant Agreement, Rider A. Section III. F. Acknowledgement.

VII. Tasks, Schedules and Estimated Costs:

Task 1 – Project Administration

The Town of Waldoboro will administer the project according to the grant agreement with DEP.  The Town of Waldoboro will be responsible for outlining project roles, responsibilities, and funding arrangements. The Town will also communicate with key partners, procure services and products, track project progress, expenses, matching funds, submit reports (semi-annual Progress Reports, Final Project Report) and other deliverables. The Town will sub-contract with a project consultant to assist with all tasks and coordinate communication with project stakeholders, landowners, and technical advisors.  DEP will approve sub-contract process and final contract.

| Start and Completion Dates | October 2017 – April 2019 |  |
| --- | --- | --- |
| Grant Cost: $3,000 | Match Cost: $2,400 | Total Cost: $5,400 |
| Breakdown of Grant by Budget Category: $3,000 (contractual) |  |  |
| Breakdown of Match by Budget Category: $2,000 (salary/fringe); $400 (supplies) |  |  |

Task 2 – Stakeholder Meetings / Landowner Participation

The Town of Waldoboro and project consultant will convene and facilitate two stakeholder meetings with the Shellfish Committee and the MVLT to garner input and support for the project. The first meeting will take place in the spring of 2018 and will include a presentation to be delivered by project staff to illustrate the water quality issues, gather input from stakeholders and discuss potential solutions to these issues. The second meeting will take place in the fall of 2018 and will focus on developing an action plan (see task 6) to address the NPS issues identified throughout the project. Both meetings will be facilitated in a manner so that public input will be allowed to guide particular elements of the plan, including the specifics of the watershed action plan. Additionally, two on-site landowner meetings will be organized to discuss BMP recommendations for high priority sites identified in the stormwater bacteria sampling (see Task 5).

| Start and Completion Dates | November 2017 – April 2019 |  |
| --- | --- | --- |
| Grant Cost: $3,800 | Match Cost: $400 | Total Cost: $4,200 |
| Breakdown of Grant by Budget Category: $3,800 (contractual) |  |  |
| Breakdown of Match by Budget Category: $400 (travel) |  |  |

Task 3 – Develop Technical Components through Technical Advisory Committee

The Town of Waldoboro (with project consultant assistance) will develop a Technical Advisory Committee (TAC) consisting of key stakeholders and agencies. This TAC group will consist of the current members of the Medomak Task Force, and will build upon this group as necessary.  The TAC will meet three times and will oversee the technical elements of the project. Responsibilities will include:

- Refining sampling locations and protocols for bacteria storm event monitoring;

- Provide input on water quality database development and maintenance

- Providing input on the WBMP strategies and action plan;

- Prioritizing sites and areas for stormwater mitigation and/or NPS source control;

- Helping identify a site for a local demonstration project; and

- Reviewing the draft WBMP.

| Start and Completion Dates | October 2017 – April 2019 |  |
| --- | --- | --- |
| Grant Cost: $3,100 | Match Cost: $1,816 | Total Cost: $4,916 |
| Breakdown of Grant by Budget Category: $3,100 (contractual) |  |  |
| Breakdown of Match by Budget Category: $1,816 (donated services) |  |  |

Task 4 – Data Management & Gap Analysis

The Town of Waldoboro proposes using grant monies to organize the large amount of bacteria data collected on the Medomak River. This will include creating a complete water quality database.

Subtask 4a: Database A complete database will be created using Microsoft Access or Excel (or similar program) to organize all pre-existing data collected in the Medomak River watershed. Data will be cataloged based on geographic location, parameter, time, laboratory analysis etc. The appropriate Maine DEP/Maine DMR classification thresholds will be used to flag data that is in exceedance of the state requirements. Once all data is cataloged, fecal bacteria data will be summarized and analyzed spatially to identify historical trends and patterns to lead to additional sampling and to guide the stormwater sampling event (Task 5). Data will be co-plotted with precipitation data to identify the response of FIB to both dry and stormflow conditions.

Subtask 4b:  Secondary Data Quality Assurance Guide  Development of the watershed plan depends on the use of pre-existing data (secondary data) that may come from a number of sources (other studies, publications, government, etc.).  Before using pre-existing data, project staff will evaluate the data to determine if the data is acceptable to use for this project. Staff will prepare a brief “Secondary Data Quality Assurance Guidance” describing how the data will be evaluated.  The evaluation will be documented in a table: data type; data source (originating organization, report title, date); how data will be used for the project; and limitations on data use, if any.

Subtask 4c: Gap Analysis Once the database is complete, and pre-existing data is synthesized, the qualified consultant will write a detailed Gap Analysis that outlines missing data. The Gap Analysis will be in the form of a detailed memorandum and will be used to inform the development of a specific monitoring regime, outlined in the final WBP.

| Start and Completion Dates | October 2017 – April 2018 |  |
| --- | --- | --- |
| Grant Cost: $3,200 | Match Cost: $0 | Total Cost: $3,200 |
| Breakdown of Grant by Budget Category: $3,200 (contractual) |  |  |
| Breakdown of Match by Budget Category: $0 |  |  |

Task 5 – Sampling and Analysis Plan; Bacteria Storm Sampling

Project staff will develop a Sampling and Analysis Plan (SAP) based on existing storm sampling Quality Assurance Project Plans (QAPPs). Project staff and volunteers will initiate a bacteria sampling ‘blitz’ during one qualifying storm event during the project duration in the Medomak River estuary. This sampling will be targeted during a rainfall event greater than one inch, the current conditional closure criteria for the Maine DMR. Project staff and volunteers will convene prior to the event to pre-determine sampling locations. Locations will be chosen based on (1) the primary hotspots for bacterial contamination, (2) available staff and volunteers to complete sampling, and (3) laboratory capacity for analysis within hold times. Sampling will occur prior to the storm event, during the storm event (at a minimum at peak discharge and once on the falling limb), and after the storm. The project consultant will organize and lead the sampling effort and will provide data analysis and a summary report. The goal of this effort is to isolate geographic areas contributing to bacteria as well as contributing flowpaths (i.e. surface runoff or groundwater contamination).

| Start and Completion Dates | May 2018 – October 2018 |  |
| --- | --- | --- |
| Grant Cost: $0 | Match Cost: $6,264 | Total Cost: $6,264 |
| Breakdown of Grant by Budget Category: $0 |  |  |
| Breakdown of Match by Budget Category: $5,664 (donated services); $600 (travel) |  |  |

## Task 6 – Hotspot Source Analysis and Action Plan Development

Project staff will compile and analyze the existing shoreline septic survey data available through the Town, the Maine DMR, the Maine DEP, and the Waldoboro Utility District (WUD) to identify potential FIB hotspots within the watershed focus area. These data will be compiled into a septic survey database that will be managed by the Town of Waldoboro. Following the compilation of survey data, the team will compare this information with the 2016 FIB results and the results of the gap analysis to further identify areas of high fecal contamination. With significant input from the TAC, the team will then develop an action plan for addressing these sources using both structural and non-structural best management practices (BMPs). These actions might include but are not limited to, additional septic surveys, bracket sampling, sewer and septic pipe inspection, remediation of identified bacteria sources, and landowner outreach.

| Start and Completion Dates | October 2018 - August 2018 |  |
| --- | --- | --- |
| Grant Cost: $4,500 | Match Cost: $0 | Total Cost: $4,500 |
| Breakdown of Grant by Budget Category: $4,500 (contractual) |  |  |
| Breakdown of Match by Budget Category: $0 |  |  |

## Task 7 – Education and Outreach

The Town of Waldoboro and its partners will keep the public informed of the grant project through a project-specific webpage and press releases (two minimum). Press releases will contain information about the nature and scope of the project as well as information on NPS pollution. Additionally, the project team will host a public presentation to the Waldoboro Board of Selectmen at the completion of the project. All press releases, outreach materials, project signs, and plans will acknowledge that the project is funded in part by the United States Environmental Protection Agency under Section 604(b) of the Clean Water Act. EPA’s logo will not be included on materials unless the Grantee receives prior instruction and approval from EPA.  Refer to the Grant Agreement, Rider A. Section III. F. Acknowledgement.

| Start and Completion Dates | October 2017 – April 2019 |  |
| --- | --- | --- |
| Grant Cost: $1,400 | Match Cost: $1,200 | Total Cost: $2,600 |
| Breakdown of Grant by Budget Category: $1,400 (contractual) |  |  |
| Breakdown of Match by Budget Category: $1,200 (donated services) |  |  |

## Task 8 – Develop Watershed-Based Plan

Project staff will develop a WBMP for the Medomak River estuary to guide stakeholders in addressing NPS contamination (specifically bacteria) in the estuary. The plan will be a dynamic document, with recommendations for actions over a ten-year period, but written to allow flexibility and adjustments as data is acquired. The plan will be developed to meet EPA’s nine minimum elements of watershed planning, including estimating current pollutant loads and the necessary pollutant load reductions needed for the river to comply with Maine DMR bacteria standards. Recommendations will include provisions for adaptive management to provide the flexibility needed to ensure efficient and successful plan implementation.

The plan will include prioritized and scheduled action items as well as identify the responsible parties for implementing said action items. Available funding strategies will be discussed in order to implement the action items. The draft plan will be reviewed by the TAC and any other interested parties for refinement and revision. The draft plan will also be submitted to DEP and EPA for review at least two months prior to project completion.

Key findings and recommendations from the plan will be presented to the Town Council and other relevant committees (i.e., Shellfish Committee), incorporating all relevant comments and suggestions to produce the final version.  The final plan will be submitted to DEP and EPA at least one month prior to project completion.  DEP and EPA comments will be addressed to produce the final approved plan.

| Start and Completion Dates | October 2018 – April 2019 |  |
| --- | --- | --- |
| Grant Cost: $3,000 | Match Cost: $3,000 | Total Cost: $6,000 |
| Breakdown of Grant by Budget Category: $3,000 (contractual) |  |  |
| Breakdown of Match by Budget Category: $3,000 (donated services) |  |  |

VIII. Deliverables

# Two copies of each deliverable will be provided to the DEP Agreement Administrator.  Each deliverable will be labeled according to procedures described in the DEP document "Nonpoint Source Grant Administrative Guidelines".

- Semi-annual Progress Reports, Final Project Report, Sub-contract (Task 1)

- Stakeholder/landowner meeting minutes (Task 2)

- Technical Advisory Committee meeting minutes (Task 3)

- Complete Database, Secondary Data Quality Assurance Guide, Gap Analysis (Task 4)

- Sampling & Analysis Plan (SAP), Final Sampling Report (Task 5)

- Hotspot Source Analysis and Action Plan (Task 6)

- Copies of education & outreach materials (Task 7)

- Final Watershed-based Plan (Task 8)

IX. Interagency Coordination, Roles and Responsibility

Town of Waldoboro. Will act as the project coordinator and be an active participant in all phases of the project.

Waldoboro Shellfish Committee. Will serve as a key member on the TAC and support sampling.

Waldoboro Utility District. Will serve as a key member on the Technical Advisory Committee.

Medomak Valley Land Trust. The Medomak Valley Land Trust will serve as assistants to the town with project management; specifically helping with landowner coordination.

Maine Department of Environmental Protection (Maine DEP). Will serve as technical advisors for the project, including a seat on the TAC. Maine DEP will administer the grant and will provide review and comment on all deliverables.

Maine Department of Marine Resources (Maine DMR). Will serve on the TAC and will provide technical input on the shellfish closures and historical data collected by Maine DMR.

University of Maine. Will serve as a member on the Technical Advisory Committee.

US Environmental Protection Agency (US EPA).  Will provide project funding and guidance.

Maine Department of Environmental Protection will administer project funding, serve as the project advisor and provide project and technical support.

X.  Project Coordinator

| Name | Julie Keizer, Town Manager |
| --- | --- |
| Organization | Town of Waldoboro |
| Mailing Address | 1600 Atlantic Highway, P.O. Box J Waldoboro, ME 04572 |
| Telephone Number | (207) 832-5369 |
| Email Address | townmgr@waldoboromaine.org |

Project Budget:

Part 1 Estimated Personnel Expenses

| Position Name & Title | Hourly Rate | Number of Hours | Salary & Fringe | Total Grantee Personnel Expenses |
| --- | --- | --- | --- | --- |
| Julie Keizer, Town Manager | $50/hour | 40 |  | $2,000 |

Part 2 Budget Estimates by Cost Category

| Cost Category | Federal Funds Section 604(b) | Non-Federal Match | Total Cost |
| --- | --- | --- | --- |
| Salary & Fringe (from Part 1) |  | $2,000 | $2,000 |
| Contractual | $21,000 | $7,600 | $28,600 |
| Subgrant |  |  |  |
| Donated Services – Labor |  | $5,480.50 | $5,480.50 |
| Travel (mileage total) | $600 |  | $600 |
| Supplies | $400 |  | $400 |
| Other (specify) |  |  |  |
| Indirect Costs |  |  |  |
| Totals | $22,000 | $15,080.50 | $37,080.50 |

Part 2 Notes:

Salary & Fringe ($2,000) includes 40 hours of in-kind match from Town Manager for project management (Task 1).

Contractual ($28,600) includes estimated 390 hours of labor at $70/hr ($27,300) and estimated $1,300 in lab fees ($21,000 requested; $7,600 non-federal cash match from Town of Waldoboro Shellfish Committee). Contractual work will be performed for all tasks.

Donated Services – Labor ($5,480.50) includes:

Medomak Valley Land Trust ($2,400 noncash match):

- Project management support (Task 1) - Estimated 10 hours @ $40/hr = $400

- Landowner / stakeholder meetings (Task 2) – Estimated 10 hours @ $40/hour = $400

- Participation in TAC (Task 3) - Estimated 10 hours @ $40/hour = $400

- Additional outreach & education (Task 7)- Estimated 30 hours @ $40/hr = $1,200

Town of Waldoboro Shellfish Committee ($1880.50 noncash match):

- Participation in TAC (Task 3) - Estimated 10 hours @ $21.61/hour = $216.10

- Volunteer sampling efforts (Task 5) – Estimated 40 hours @ $21.61/hour (rate established by Independent Sector 2016 ) = $864.40

- Private boat services (Task 5) – Estimated 8 hours @ $100/hour = $800

University of Maine, Darling Marine Center ($600 noncash match):

- Participation in TAC (Task 3) - Estimated 10 hours @ $60/hour = $600

Department of Marine Resources ($600 noncash match):

- Participation in TAC (Task 3) - Estimated 10 hours @ $60/hour = $600

Travel costs are estimated at $600 at rate of ($0.44/mile)

Field supplies are estimated at $400.

Part 3  Sources of Non-federal Match and Estimated Amounts

| Sources of Non-federal Match | Amount |
| --- | --- |
| Town of Waldoboro | $2,000 |
| Town of Waldoboro Shellfish Committee | $9,480.50 |
| Medomak Valley Land Trust | $2,400 |
| University of Maine, Darling Marine Center | $600 |
| Department of Marine Resources | $600 |
| Totals | $15,080.50 |

Prohibited areas are completely closed for shellfish harvesting. Restricted areas require a Maine DMR permit. Conditionally Approved areas are closed for nine days following precipitation events greater than one inch in 24 hours. At this point, the closure areas are automatically re-opened. However, if days seven through nine receive cumulative rainfall totals of greater than or equal to 0.75 inches, the areas remain closed for three additional days. Seasonally Approved areas are closed from May 1st to September 30th.