## Slide 1: SIM Maine CDC Status
FFY Q1, 2014

## Slide 2: SIM Maine CDC Status Driven by the Maine CDC FFY Q1, Oct – Dec 2013
Objective | Status | Status Description
CHW Pilot | Yellow | Steering Committee has formed a subcommittee to talk about priority setting, with a potential tool to be developed. This tool is still in development, so is bumping up against our plan to release a RFP for community health worker pilots by first week of January. The RFP is one month behind schedule.
NDPP | Green | Have met with Maine Health Management Coalition to discuss tests for reimbursement of the Diabetes Prevention Program. US CDC is providing technical assistance and connecting us to other states that have successfully addressed reimbursement.

## Slide 3: SIM Maine CDC Status Driven by the Maine CDC Outlook for FFY14 2Q, Jan - Mar
Objective | Outlook | Associated Narrative (include information on expected Milestones or Accountability Targets )
CHW Pilot | Yellow | By March, 2014 we will have met with the Delivery System Reform Subcommittee to gain insights into barriers and opportunities as well as education about the value to CHWs. The RFP will be finalized.
NDPP | Green | By March, 2014 we will have met with the US CDC and identified partners to support our work with the NDPP, including identification of possible alternate payment models and recruitment strategies for businesses and purchasers as reimbursement pilots for the program.