## Slide 1: SIM Data Infrastructure Status
FFY Q1, 2014

## Slide 2: SIM Data Infrastructure Status Driven by HealthInfoNet
Overall Data Infrastructure Status: | Mixed
Status Summary MaineCare Notification Project (Objective 1) – Yellow - HIN has completed preliminary workflow requirements for the notification process with both the Care Management team as well as the Data team. MaineCare needs to sign a BAA with HIN before MaineCare eligibility/claim files can be sent to HIN and the project can enter the testing phase. And MaineCare will need to sign a Data Access Agreement with HIN before data can be sent to MaineCare care managers from HIN’s HIE database. Data file exchange workflows are established, ready to begin testing with the approval of the contract. Behavioral Health RFP (Objective 2) – Green - HIN revised the BH RFP draft with input from the November and December DI Subcommittee input and will present the findings of the BH RFP to the January Steering meeting for final approval to move forward with the release slated for 1/31/14. Clinical Dashboard (Objective 4) – Yellow - HIN presented and initiated the project timeline and goals for the Dashboard analytic tool to MaineCare leadership, next steps include a presentation to the Senior Management Team at MaineCare/DHHS to align various departments who will participate in the project. Recurring meetings with MaineCare stakeholders will be scheduled for 2014 once the stakeholders are confirmed. Awaiting Data Access Agreement sign off to begin implementation with real data. Patient Portal/ “Blue Button” Project (Objective 5) – Yellow - Utilizing input from the November & December DI Subcommittee as well as the HIN Consumer Advisory Committee; HIN launched the pilot selection criteria and will release an Request for Interest in January. Data Infrastructure (DI) subcommittee (Objective 6) – Green - HIN will continue to chair the DI subcommittee. Several HIN projects were presented at the December meeting, group consensus and active participation continues without any risks identified for Steering at this time. Feedback from the group is positive. | 
Risks/Issues Contract delays impact on timeline for Objectives 1 and 4. All HIN projects have been set back approximately 1 quarter from original project timeline due to unavoidable contract and committee structure processes. | 

## Slide 3: SIM Data Infrastructure Status-1Q Driven by HealthInfoNet
Objective | Status | Status Description
MaineCare ER Notifications (Obj. 1) | Yellow | Need BAA signoffs from MaineCare to receive eligibility data to begin testing phase of the project.
BH Incentives and HIE Access to BH Providers (Obj. 2 & 3) | Green | BH RFP on track for release on 1/31/2014.
Clinical Dashboard from the HIE to MaineCare (Obj. 4) | Yellow | HIN is waiting for MaineCare to sign off on DAA in order to move forward into the design phase of the project. Project timelines have been reviewed and agreed upon with MaineCare leadership.
PHR Patient Portal ‘Blue Button’ Development (Obj. 5) | Yellow | Project required stakeholder input including the members of the DI Subcommittee and the HealthInfoNet Consumer Advisory Committee regarding pilot selection criteria and content planning. This committee work has led to successful collaborative project input that allows the project to pursue a ‘Request for Information’ to select the pilot partner and begin the 12 month pilot. There are no barriers, however a timeline expansion is required.
Data Infrastructure Subcommittee (Obj. 6) | Green | 12/4 meeting went very well. DIS operating smoothly, no identified risks for Steering at this time, out side of the delays in contracting.

## Slide 4: SIM Data Infrastructure Status Driven by HealthInfoNet FY14-2Q Outlook
Objective | Status | Associated Narrative (include information on expected Milestones or Accountability Targets )
MaineCare ER Notifications (Obj. 1) | Green | “Data release authorization” was successfully obtained from the participating providers. With the BAA finalized with MaineCare as of January 2014, HIN will receive the monthly eligibility/claim data and begin the testing process with MaineCare. Year 1 acct. targets are on track.
BH Incentives and HIE Access to BH Providers (Obj. 2 &3) | Green | The BH RFP will be released to the public on 1/31/14 with a application deadline of 3/3/14. HIN will review applications in March and announce awardees by 4/4/14. The project remains aligned with the BHHO MaineCare implementation (Stage B Health Homes). Year 1 acct. targets are on track.
Clinical Dashboard from the HIE to MaineCare (Obj. 4) | Green | The DAA is finalized as of January 2014 with MaineCare, the project can move forward into testing and development. HIN staff have met and discussed the project details to best align the project to meet MaineCare’s ‘use case’ of the dashboard and will schedule recurring meetings with department level stakeholders identified by MaineCare.
PHR Patient Portal ‘Blue Button’ Development (Obj. 5) | Yellow | HIN’s launch of the Request for Information in early January will lead to the final pilot provider partner selection. The impact on original target of pilot partner selection is a 2 quarter delay, as explained in the status summary above. Once the pilot partner is selected, the new pilot launch is the 3rd quarter of year 1. This impacts the timeline for the completion of the deliverable by 2-3 quarters in total, with a new end date of 2nd-3rd quarter of grant year 2 . This time change allows the pilot partner the full 12 months to complete the implementation and findings for this work. These changes do impact the original year 1 acct. targets by moving the pilot completion date out, and therefore the measurement target of 5% CCD download out as well, to match the new pilot end date. The goals themselves however have not changed.
Data Infrastructure Subcommittee (Obj. 6) | Green | 2014 Meeting schedule has been determined and scheduled with subcommittee members. Topics for meetings have been discussed and will continue to be an on-going discussion.