## Slide 1: SIM Delivery System Reform Status
FFY Q1, 2014

## Slide 2: SIM Delivery System Reform Driven by Maine Quality Counts
Overall Delivery System Reform Status: | Green
Status Summary -The implementation of the HH Learning Collaborative is well underway and on track with the stated work plan. Our projection for the deliverables due in January 2014 looks good as well. -The chairing and support for the SIM Delivery System Reform Subcommittee is also progressing well. We are establishing meeting process and structure, and developing an approach to balance the diverse scope of the Subcommittee with the monthly meeting schedule. We have identified content for both the January and February DSR Subcommittee meetings. - Other major initiatives, (Behavioral Health Home Learning Collaborative, Patient Provider Partnerships) are not yet scheduled yet to begin | 
Risks/Issues -The primary issues we face in the HH Learning Collaborative include the ability of the HH practices to meet their participation requirements, such as the NCQA recognition process. This is being worked in conjunction with the State to ensure that practices who do successfully meet requirements are appropriately supported and that those who are not able to sustain participation receive appropriate communication from the State. We will know the final status of the NCQA recognition of the HH practices that applied in 2013 by early to mid January 2014. At that time we will be working in conjunction with the State to appropriately communicate the status and next steps for the practices. Additionally, we are concerned about the ability of the HH practices to meet their must pass expectations and are currently assessing their status toward their annual goals; working with the State as appropriate to communicate and monitor practice status. -Year two screening requirements are a risk as there is currently a lack of clarity on approach to the additional screening requirements and we are working with the State to clarify and communicate these to the practices for 2014, and to provide appropriate technical assistance for their success in meeting these requirements. -The Delivery System Reform Subcommittee continues monthly meetings. The December meeting occurred on 12/6/13 and addressed the HH primary care model, Community Care Teams, the HH Learning Collaborative and the Community Health worker pilot. Risks for that Subcommittee are tracked in each meeting and reported to the SIM Project management, and tracked and escalated appropriately. One major issue is the large size and diverse scope of the Subcommittee, which challenges meeting process and member experience. We continue to receive progressively improved meeting evaluation scores and to refine the approach and process with the Members. | 

## Slide 3: SIM Delivery System Reform Driven by Maine Quality Counts Status for Oct – Dec, 2013
Objective | Status | Status Description
Objective 1: Stage A Health Homes Quality Improvement Support |  | Well underway and on schedule
Objective 2: Provide support for SIM Delivery System Reform Subcommittee |  | Well underway and on schedule
Objective 3: Provide QI Support for Behavioral Health Homes Learning Collaborative | N/A | Not scheduled to work on in 1Q work plan
Objective 4: Provide QI Support for Patient-Provider Partnership Pilots (P3 Pilots) | N/A | Not scheduled to work on in 1Q work plan

## Slide 4: SIM Delivery System Reform Driven by Maine Quality Counts Status Outlook for FY142Q
Objective | Status Outlook (Green, Yellow, Red) | Associated Narrative (include information on expected Milestones or Accountability Targets )
Objective 1: Stage A Health Homes Quality Improvement Support |  | The objective is proceeding as planned. We are on track with our stated milestones and accountability targets with 100% of the HH practices that met the entry requirements participating. Termination of 7 practices was a result of those practices inability to meet their entry requirements (ie., NCQA recognition) of the HH Initiative. We anticipate to meet our next quarter goals.
Objective 2: Provide support for SIM Delivery System Reform Subcommittee |  | The objective is proceeding as planned, with good participation of Subcommittee members in all meetings, and progressively improving meeting evaluation scores We anticipate success with our next quarter goals
Objective 3: Provide QI Support for Behavioral Health Homes Learning Collaborative |  | Progressing well, staff are hired and deployed. We anticipate meeting our next quarter goals
Objective 4: Provide QI Support for Patient-Provider Partnership Pilots (P3 Pilots) |  | Progressing well, staff are hired and deployed. We anticipate meeting our next quarter goals.

## Slide 5: Appendix
Maine Quality Counts Accomplishment Detail

## Slide 6: SIM Delivery System Reform Status Driven by Maine Quality Counts
Objective | Status | Status Description
Stage A Health Homes Quality Improvement Support |  | 
Conduct initial QI outreach to all HH practices |  | We project that this will be accomplished by 12/31/13; this will also include Action Planning on the prioritized items from the onsite Assessments
Identify and orient QI coaching support for HH practices |  | If external coaches are not available, quality coaching will be provided by QI Specialist staff
Conduct ongoing QI support to HH practices |  | Recurring deliverable throughout SIM
Implement HH Education Plan |  | Education plan includes monthly webinars; newsletters; and ongoing communicaiton; during 2014 the HH practices will be folded into the Learning Sessions with the multipayer Patient Centered Medical Home practices, to facilitate additional networking and peer support for transformation
Conduct Learning Session 1 for HH practices |  | Planning well underway for Feb 7 Learning Session
Deploy transformation clinical, leadership and technical assistance to HH practices |  | Deployment of technical assistance includes ongoing assessment of HH practice progress, challenges, barriers and needs
Ensure data management for HH transformation |  | Data management includes ongoing refinement of data management plan, data collection, tracking, storage,data quality procedures, and database maintenance and support; also includes ongoing data analysis and reporting
Support QI Coaching of HH practices |  | Support of QI Coaching includes ongoing identification of external and internal QI coaches, training, support, communication and deployment of coaches to HH practices