## Slide 1: SIM Payment Reform Status
FFY Q1, 2014

## Slide 2: SIM Payment Reform Status Driven by Maine Health Management Coalition
Overall Payment Reform Status: | Green
Status Summary Progress on SIM goals and work plan continues to move ahead, with progress being made on each of the key objectives. Work around Objective 1 – tracking health care costs – proceeded as planned, including the enhancement and maintenance of the robust database required to support the SIM measurement, analytics and reporting work. Work on value based benefit design was also underway, with the launch of educational efforts focusing on VBID, including a large public meeting featuring one of the nation’s leading thinkers on this policy issue, and the development of a VBID curriculum for brokers and HR specialists. Objective 3 work on accountable care implementation also progressed, with the convening of the ACI workgroup and a series of PTE activities related to physician care and health care systems’ performance measurement. A great deal of work related to Objectives 4 and 5, provider access to data, was also undertaken, particularly as related to the refinement of practice reports for all primary care practices in the state. Work on refining provider portals also occurred. Efforts related to consumer engagement occurred on an on-going basis throughout the duration of the quarter, including the first “take” of a video focused on explaining VBID to a general audience. Finally, work to generally support the administration of the SIM grant was undertaken, including increasing the scope of work of the MHMCF to include development and implementation of a grant-wide communications plan. | 
Risks/Issues - One substantial hurdle encountered is the ability to recruit staff with the appropriate skills set. This is related not simply to the need to adhere to the budget established for the SIM grant but also to a more fundamental challenge of finding highly qualified, experienced candidates for our open positions. This is a particular challenge with regard to health data analysts; other similarly situated organizations are experiencing the same difficulties in finding high quality analytic staff. We are compensating by pulling other MHMC staff off of other Foundation work and redirecting them to SIM activities. That strategy works in the short term, but we need a longer term solution. - Certain issues have arisen related to the timely availability of complete and valid data sets from the Maine Health Data Organization. It is incumbent upon the MHDO to resolve these issues, but there is a risk posed to our work if data are not available in a timely manner. | 

## Slide 3: SIM Payment Reform Status Driven by Maine Health Management Coalition
Objective | Status | Status Description
1. Track Health Care Costs - This is a central activity supporting work related to the primary driver of Payment Reform. Tracking costs requires the construction and on-going maintenance of a robust, valid data set, and sound data analytics employing that data set, which are part and parcel of the work of this objective. | Green | Progress on this objective is moving along nicely. Work related to fulfilment of all of the requirements of QE status continues; CMS subcontractors supporting the QE security clearances made a site visit to MHMCF in December. During this quarter we defined scope of work with our data vendor, HDMS and feeds of statewide claims data were received on our behalf by the vendor. HDMS received a first load of MaineCare data and implemented processes around that database so that it is usable for analytic purposes. Several key hires were also made in this quarter, including a programmer and the Cost of Care Manager, who on-boards in January.
Value Based Benefit Design – Work related to VBID also falls under the Payment Reform primary driver and is intended to create momentum within the market to plan designs that incentivize use of high value services and high value providers. | Green | Work on VBID is progressing and during Q1 included the start of a concerted educational effort around value based design at the Coalition’s annual meeting. A video of the VBID session featuring Dr. Mark Fendrick is available to all interested persons on our website. A broker/ HR specialist VBID curriculum has been developed and educational credits have already been awarded.
4. Provide Primary Care providers access to claims data for their patient panels – This work falls under the scope of the delivery system reform primary driver and aims to facilitate provider access to their patient panel’s claims data to assist them in better understanding their panel experience. | Yellow | Provider portals are designed and are ready to be implemented. However, the work of identifying practices interested in having a portal deployed for their practice remains on-going.

## Slide 4: SIM Payment Reform Status Driven by Maine Health Management Coalition
Objective | Status | Status Description
5. Provide practice reports reflecting practice performance on outcomes measures – This work supports delivery system reform by providing practices with detailed information regarding risk adjusted cost and use of their patients, benchmarked against peers. | Green | This work is progressing well with regard to the development of practice reports incorporating commercial data; MaineCare data and Medicare data will be added to the reports as those data become available. The first round of data reports were received and put through quality control; a subsequent re-run of the reports was submitted to the data vendor to resolve particular issues.
6. Consumer engagement and education regarding payment and system delivery reform – Consumer engagement is both a primary driver and specific objectives supporting delivery system reform. This work focuses on efforts to raise awareness across the broader community of payment reform and value based strategies. | Green | A campaign strategy around value based “education” has been mapped out as contemplated in the workplan.
7. Ensure effective management of SIM Payment Reform Subcommittee to promote sustainability of reform developed through SIM – This work supports the efficient and effective administration of the SIM grant. | Green | We successfully populated and stood up the Payment Reform Governance Subcommittee, with the membership specified by the Commissioner and the Steering Committee. We participated in all SIM Partners activities and all public meetings and submitted all required reports.

## Slide 5: SIM Payment Reform Status Driven by Maine Health Management Coalition
Objective | Sub-Obj | Status | Status Description
3. Provide primary care providers access to their patient panels (portals) – This objective supports work focused on the provision of health information to manage care, plan provider and patient-level interventions. The intent of the effort is to enhance providers’ ability to better understand how patients in their practices utilize health care, so they might improve the management of those patients and, in turn, improve outcomes, cost of care and resource use. |  | Green | The PTE work group met during this quarter and discussed the interplay of the SIM work with their own. This PTE work relates to the formulation of reporting on Advanced Primary Care Recognition status as well as metrics related to specialty care. These efforts all require a significant investment in analytics, work with small groups of providers to test feasibility and validity of metrics and work with other vendors who are involved with data collection and measure development. All of this work is underway and on-going.
 | APC | Green | See comments above re: Advanced Primary Care.
 | PTE Systems | Green | This PTE group also met during this quarter and discussed the intersection of the SIM work with their own “regular” work. In addition to developing, vetting and recommending metrics related to health care systems, this group will also vet recommendations coming from the ACI group for ACO metrics. The work this quarter centered on preparing the group for this responsibility.
 | ACI Metrics | Green | The ACI group met on several occasions during this quarter, discussing the work that falls to them under the SIM grant. One of the functions of this group is to act as a learning collaborative. To that end, Michael Bailit, a national expert on performance improvement conducted a session with ACI participants to help kick start this process. The group also laid our working rules for the group process and mapped out the work needed to grapple with constructing a core ACO metric set.
 | PTE Behavioral Health | Green | We have solicited interested parties to participate in this new PTE effort. Those on the list have been contacted on a number of occasions, with preparatory resource/reading materials being sent to them as background materials. A clinical consultant has been identified, and candidates to lead this workgroup have been interviewed. We have experienced difficulty in identifying an appropriate candidate to fill this role, thus delaying the standing up of this group until Q2.
 | Report on Patient Experience of Care | Green | Data collection efforts for this activity were sponsored and overseen by the Maine Quality Forum. For various reasons, that data collection effort (which does not involve the Coalition) ran into significant problems, delaying the availability of the data to us. We have been participating in numerous meetings and strategy sessions regarding how to improve and make more usable the CG-CAHPS data collected as part of this state effort and believe there will be usable data available to us in Q2.

## Slide 6: SIM Payment Reform Status Driven by Maine Health Management Coalition Outlook for FY14Q2
Objective | Status Outlook | Associated Narrative (include information on expected Milestones or Accountability Targets )
1. Track Health Care Costs - This is a central activity supporting work related to the primary driver of Payment Reform. Tracking costs requires the construction and on-going maintenance of a robust, valid data set, and sound data analytics employing that data set, which are part and parcel of the work of this objective | Green | We anticipate all of the work related to tracking health care costs to proceed smoothly during Q2. A Cost of Care Manager was hired and started working in early January. Planning has begun to convene the cost workgroup, as has planning for production of a new Health Care Cost Fact Book and the next CEO summit. We expect to satisfy all of the QE security requirements in this quarter, which paves the way for the first Medicare data feeds. The issues with the data feeds from the MHDO appear to be resolving and data feeds from Molina are working well.
2. Value Based Benefit Design – Work related to VBID also falls under the Payment Reform primary driver and is intended to create momentum within the market to plan designs that incentivize use of high value services and high value providers. | Green | We anticipate work related to VBID to proceed quickly. A VBID manager was hired in early January and began work the 3rd week of January. One of her first orders of business will be to develop and implement a strategy to survey plans for information regarding VBID characteristics they employ in their plan offerings.
4. Provide Primary Care providers access to claims data for their patient panels (portals) – This work falls under the scope of the delivery system reform primary driver and aims to facilitate provider access to their patient panel’s claims data to assist them in better understanding their panel experience. | Yellow | While the portal structure is completed and ready to deploy, work will be undertaken this quarter to identify practices wishing to have such a tool implemented for their practice. As MHMCF staff disseminate the individualized practice reports (see below), they will solicit interest in the portal option, which is voluntary. We will work toward a goal of 50 participating practices by the end of Q4.

## Slide 7: SIM Payment Reform Status Driven by Maine Health Management Coalition Outlook for FY14Q2
Objective | Status Outlook | Associated Narrative (include information on expected Milestones or Accountability Targets )
5. Provide practice reports reflecting practice performance on outcomes measures – This work supports delivery system reform by providing practices with detailed information regarding risk adjusted cost and use of their patients, benchmarked against peers. | Green | The first run of practice reports for all primary care practices in the state have been received, subjected to q/c, rerun and run through q/c a second time. They will be deployed over the course of Q2 by staff hired on specifically under SIM for this purpose. These reports are restricted to commercial data at this point; MaineCare and Medicare data will be added as those databases become more robust and reliable for our use. The reports do include total cost of care and resource use measures.
6. Consumer engagement and education regarding payment and system delivery reform – Consumer engagement is both a primary driver and specific objectives supporting delivery system reform. This work focuses on efforts to raise awareness across the broader community of payment reform and value based strategies. | Green | Outreach and education efforts will continue throughout Q2. We have a goal of reaching 200 people in the first year of the testing grant.
7. Ensure effective management of SIM Payment Reform Subcommittee to promote sustainability of reform developed through SIM – This work supports the efficient and effective administration of the SIM grant | Green | We will continue to participate in all Partners’ activities, all governance activities, and meet all reporting and contracting requirements, as requested. We are responsible for support and leadership of the Payment Reform Subcommittee, which is already established. This collection of activities also includes implementation and support of a grant-wide communications plan, which we have developed and submitted to the Steering Committee for review and feedback; we anticipate that the Steering Committee will take up the proposed communications plan at its February meeting.

## Slide 8: SIM Payment Reform Status Driven by Maine Health Management Coalition Outlook for FY14Q2
Objective | Sub-Obj | Status Outlook | Associated Narrative (include information on expected Milestones or Accountability Targets )
3. Identify common metrics across payers for public reporting and alignment with payment – This work relates to the provision of health information to influence markets and inform policy decisions. It figures prominently in efforts around the payment and delivery system reform drivers. | PTE Physicians | Green | Work on development/vetting of advanced primary care recognition metric will continue with testing of data, work with PTE subcommittee focused on APC recognition; working toward target of Q4 for provider review and reporting out recommendations for public reporting. Group is also working on total cost of care metrics, which are currently slated for reporting in Q4. The provider database now includes specialty providers, so work will begin on testing the viability of applying Prometheus quality and cost measures to datasets.
 | APC | Green | See above
 | PTE Systems | Green | Systems group work will focus on total cost of care (commercial) at the systems level, with staff engaged in analytic work and the development of potential “cut” points for benchmarking. Similar work is slated to begin during the course of this quarter. Hospital readmission measures will be in progress for commercial pay patients; similar work with MaineCare patients will begin during this quarter. Similar work plan pertains to measures for ED use for ambulatory sensitive conditions and for admissions for ASCs, as well. Work will continue on testing and refinement of ED OP metrics and on the Leapfrog safety scores.
 | ACI Metrics | Green | Work on surveying of plans for “universe” of ACO metrics used will be completed; ACI workgroup to form working subcommittee to begin to review those metrics to formulate recommendations for a core measure set that is foundational to the development of performance targets and related measurement. This exercise is also related to the learning collaborative aspects of the ACI group.
 | PTE Behavioral Health | Green | New PTE BH Director hired in January, on-boarded in February. Clinical consultant has been identified and workplans will be developed during the early portion of this quarter. MHMCF will continue to cultivate interested parties and continue to prepare those parties for work by providing them with background materials. Workgroup to be convened by quarter’s end.
 | Report on Patient Experience of Care | Green | CG-CAHPS data has been received from the state’s contractor; reporting formats are in development, as are discussions regarding how to sustain this effort over the longer term.

## Slide 9: Payment Reform Status
Appendix

## Slide 10: SIM Payment Reform Status Driven by Maine Health Management Coalition
Objective | Status | Status Description
Receive documented QECP security finding. | Green | 
Respond to QECP security audit findings | Green | 
Discussions with ResDAC and IMPAQ on DUA for Medicare data | Green | 
Completion of QECP DUA and data requests | Green | 
Onboard Cost of Care Director | Green | 
Receipt and processing of statewide commercial claims | Green | 
Continuing work on MaineCare data implementation | Green | MHMC will be providing certain analytic support for the MaineCare ACO initiative. However, the exact scope of such activities will not be totally definable until at least March 2014, when the Department and Deloitte are able to share data with the Coalition.
Continue to plan for CEO round table | Green | 
Onboard VBID hire | Yellow | Onboarding the new hire is contingent upon the acceptance of an offer by the candidate. We are still negotiating with the candidate
Provide updated recognition reports to PHOs based on new January RDE file import | Green | 
Import and process January recognition data | Green | 
In addition to ongoing demographic communications with practices, the recognition file import process generates an exception report. Practices are contacted to determine if providers on the report are actually at the practice. | Green | 

## Slide 11: SIM Payment Reform Status Driven by Maine Health Management Coalition
Objective | Status | Additional Status Information
Prepare presentation status update materials for the Feb PTE Physicians group | Green | 
Examine options for the behavioral health recognition component of APC as well as evaluate Patient Experience results | Green | 
Prepare presentation status update materials for the Feb PTE Physicians group | Green | 
Receive Leapfrog and ACM measures | Green | 
Calculate new Leapfrog and ACM recognitions | Green | 
Hold ACI Meeting and consider any new possible PTE related measures | Green | 
ID behavioral health clinical consultant; on board BH PTE staff | Red | Risk: Finding qualified resources for behavioral health consultants
Convene PTE-BH workgroup | Red | 
ID Viable Performance Measures for PTE-BH | Red | 
Continue to explore and refine new report formats based on the new data | Green | A PTE subcommittee has been formed and is working on defining cut points for value assignment to allow tagging of performance to good/better/best. It is anticipated that the recommendations from this subgroup will be brought to the full PTE committee at the February meeting.
Continue to refine the Patient Experience reporting process with support of CG CAHPS workgroup | Green | The data for specialty practices is likely not suitable for publication, as most of the practices do not have sufficient data in one or more of the four domains of CG-CAHPS to allow for reporting of valid findings. 21 of the 170 primary care practices reporting CG-CAHPS data have too few observations to allow for valid reporting.
Continue to refine the plan to continue the reporting process beyond the first year. | Green | 

## Slide 12: SIM Payment Reform Status Driven by Maine Health Management Coalition
Objective | Status | Status Description
Begin roll out process for practice reports reports | Green | 
Review of and revisions to state-wide commercial practice reports | Green | Data for approx. 700 providers received. Quality checking revealed issues with data; reports will need to be re-run. Note that there are issues with recent data submitted to the MHDO by Anthem that need to be resolved; this, combined with the fact that the MHDO has a new data vendor may impact the timely receipt of data from the APCDB.
Coordination with Muskie on MaineCare reporting production | Green | 
Coordination with Quality Counts for distribution of Commercial practice reports. | Green | 
Continue to fine tune and develop VBID media campaign | Green | 
Onboard admin assistant and accountant | Green | 
Create SIM Acronym library, communication plan and newsletter template ( Trevor) | Green | 
Data team’s work with MaineCare Finalize measure set for accountable community reporting | Green | 
Participate in finalization of Accountable Community methodology | Green | 

## Slide 13: SIM Delivery System Reform Status Driven by Maine Quality Counts
Objective | Status | Status Description
Begin roll out process for practice reports reports | Green | 
Review of and revisions to state-wide commercial practice reports | Green | Data for approx. 700 providers received. Quality checking revealed issues with data; reports will need to be re-run. Note that there are issues with recent data submitted to the MHDO by Anthem that need to be resolved; this, combined with the fact that the MHDO has a new data vendor may impact the timely receipt of data from the APCDB.
Coordination with Muskie on MaineCare reporting production | Green | 
Coordination with Quality Counts for distribution of Commercial practice reports. | Green | 
Continue to fine tune and develop VBID media campaign | Green | 
Onboard admin assistant and accountant | Green | 
Create SIM Acronym library, communication plan and newsletter template ( Trevor) | Green | 
Data team’s work with MaineCare Finalize measure set for accountable community reporting | Green | 
Participate in finalization of Accountable Community methodology | Green |