## Identified Maine SIM Risks
Risk # | Risk Name | Impacted SIM Objectives | IF…. | THEN… | Accountability Target Impacts | Drivers Impacted | Risk Owner (Project Manager Name) | Status (Open, In Progress, Resolved, Closed): | Creator | Date created | Updated by (name) | Date last updated | Weighted Priority (1= Low, 2= Med, 3 = High) | Probability 1-3 1=Low, 2= Med 3=High | Impact 1-3 (1=Low, 2= Med 3=High) | Risk Calc | Risk Details | Risk Sympts- | Mitigation plan (free form) | Impact Des | Associated Risks | Associated Issues
6 | Behavioral Health (BH) EHR data functionality constraints across the vendors used in Maine | HIN Objective 2&3 | If the RFP top scoring applicants/ participants have significant data interface constraints due to vendor constraints… | 1. HIE data interface goals will be diminished greatly. 2. There will be a lack of discrete, reportable, and or measureable data in the HIE which; 3. Leads to the decreased ability to perform quality measurement | Milestone 2 and 3 delays and/or a reassessment of milestone requirements will be necessary | Data Informed Policy, practice and payment decisions related to BH Data | Katie Sendze | Open | Katie Sendze | 2014-02-21 | Katie Sendze | 2014-02-21 | 2 | 2 | 3 | 12 |  |  | Proactive communication with RFP participants about interface constraints and plan for data capture alternatives within funding available. | See column D.
25 | Gap in connection of primary care (including PCMH and HH practices) to the Health Information Exchange and the associated functions (e.g. notification and alerting) will limit capability of primary care to attain efficiencies in accordance with the SIM mission/vision and DSR charge. | MQC Objective 1 - LC for MaineCare HH's HIN Obj #1, 2 and 3 | If the HIT functions under SIM (HIE notifications, HIE access, related cost reports etc.) are not unavailable to support enhanced primary care/Health Homes… | Inefficient and duplicative processes will remain, cost savings will suffer and patient health outcomes will not be positively impacted by such care coordination functionality as intended | n/a | Data Informed Policy, practice and payment decisions related to BH Data | Katie Sendze | Open | Lisa Tuttle | 2014-02-24 |  |  | 2 | 2 | 2 | 8 |  |  | HIN is proactively working with groups to reduce barriers within their control. Some org.s have prioritized large initiatives such as ICD-10 above HIE connectivity and data integration. Some orgs. may be unaware of HIE functionality and benefits and thus HIN will be leveraging Health Home forums/webinars to educate the community about the services available, as well as reaching out directly.
9 | HIE Data Use Case Rejection by the Data owners (HIE Participants, Provider organizations) | HIN Objective 4 | If HIE participants reject the authorization request to release PHI data within the MaineCare Dashboard tool… | The Dashboard tool will be limited in it's usefulness, however, how much is yet to be determined | None | Data Informed Policy, practice and payment decisions related to BH Data | Katie Sendze | Open | Katie Sendze | 2014-02-22 | Katie Sendze | 2014-02-21 | 2 | 1 | 3 | 6 |  |  | Develop Use Case request with strategic thoughtfulness and transparency using specific education to providers so that no false barriers to the work are created. | See column D.
8 | Provider organizations interpretation of a clinician as subject to 42 CFR Part 2 rules | HIN Objective 2& 4 | If a clinician (eg. PCP, BH provider) is deemed subject to Part 2 rules | Entire provider (PCP) panels or mental health data will be withheld from the HIE; and may not be available for quality measurement under SIM program goals | None for obj. 4, Milestone delay for obj. 2 | Data Informed Policy, practice and payment decisions related to BH Data | Katie Sendze | Open | Katie Sendze | 2014-02-22 | Katie Sendze | 2014-02-21 | 1 | 2 | 2 | 4 |  |  | Proactive communication with participants about SAMSHA CFR-42 Part 2 FAQ guidance related to Primary Care and program definitions and HIN's stance. | See column D.
7 | Behavioral Health EMR implementation delays | HIN Objective 2&3 | If RFP participants without a implemented EMR do not meet implementation timelines and resources allocated…. | Milestone achieved will be delayed or unachieved | Milestone 2 and 3 delays and/or a reassessment of milestone requirements will be necessary | Data Informed Policy, practice and payment decisions related to BH Data | Katie Sendze | Open | Katie Sendze | 2014-02-21 | Katie Sendze | 2014-02-21 | 1 | 2 | 2 | 4 |  |  | Proactive communication with RFP participants about implementation plans. | See column D.
10 | PHR Patient Portal Pilot Partner unable to align resource allocation with SIM timelines | HIN Objective 5 | If the selected pilot partner cannot align with the 12 month timeline (6/14-6/15) determined under SIM quarterly report (1/2014)… | The project deliverables will be delayed. | Delayed completion, timing issue only | None | Katie Sendze | Open | Katie Sendze | 2014-02-22 | Katie Sendze | 2014-02-21 | 1 | 1 | 1 | 1 |  |  | Proactively engage pilot candidate with timeline in March to ensure expectations and realistic response are out on the table and adjustments to timelines can then be determined. | See column D.
Note on N1: Chenard, Randal: Weighted priority appropriately weights the risk based on the objectives that are potentidally impacted by the risks. If higher priority objectives are impacted by the occurance of the risk, then the risk would receive a higher Priority rating than if the risk may impact a less impactful objective. Refer to the Objecive weight assignments for determination, which is located on the 'weighted objective' tab in the spreadsheet. For example, a risk that may impact, the blue button pilot (HIN objective 5), will not be weighted as heavily as a risk that may impact the MaineCare Accountabile Community model development (MaineCare Objective #1)
Note on R1: Chenard, Randal: Free form, can capture additional descriptive info or any updates Chenard, Randal:
Note on U1: Chenard, Randal: Impact Description: (free form) - detailed description of impact risk will have on the project / program / release - further detail for "then" statement

## Instructions-Guidance
Guidance for Risk Mitigation Planning Templates
Prior to initiating risk mitigation planning activities, CMMI Project Officers and State leads should review and finalize the accountability targets developed as part of the Operational Plans. These milestones should be as granular as possible, because they will be used to guide the risk mitigation planning activities, particularly those planned for Years 1-2 (short-term). In the attached example, the original accountability target was defined more specifically by defining five milestones that contribute to the overall target. This same process should be followed for longer term milestones (Year 3+) as they approach.
Recommended risk mitigation activities include the following steps:
Step 1 - Evaluate Risks and Risk Factors: [Refer to Tab #1]
As a first step in the risk mitigation planning process, State teams can use the attached template to assess which accountability milestones have the greatest likelihood or risk for failure, and the greatest potential negative impact on achieving their SIM goals.
For each accountability target, the level of associated risk should be mapped out in the tables included on Tab #1, based on each target’s relative likelihood of failure (low, medium, or high) AND its potential impact on the success of the state’s SIM work (low, med, or high). The shaded boxes in the template indicate the recommended areas of focus for a state’s risk management activities, given that these activities have a relatively high risk of failure, and failure may significantly affect the state's SIM progress. If there is little or no likelihood of the risk event occurring, the risk may not warrant inclusion in the state's Risk Management process.
States can begin by including an "X" in the appropriate box/cell in the template to indicate the relative likelihood of each of the accountability targets not being achieved (or failing) and the potential impact this failure could have on overall project success. It may be helpful to also include a brief statement elaborating on the risk and potential impact (as included in the attached example).
The state should then evaluate the factors that may contribute to not meeting milestones using a three-tiered logic scheme:
- What factors contribute to the risk?
A given risk may have multiple factors that contribute to its occurrence across various risk categories, as noted above.
- Which of these factors poses the greatest total risk?
It will be helpful to focus on the risk factors that will have the greatest impact on total risk. This may be easiest to complete once all factors have been listed out
for a given set of accountability targets.
- Which factors are within the state’s control?
For the purposes of developing a risk mitigation strategy, it will be important to identify upfront which factors can be impacted by the policy/regulatory levers at
a state’s discretion.
The state can first list the factors contributing to the risk of not meeting each milestone. Given the focus on the medium and high impact/likelihood risks, there may be multiple risk factors under each Accountability Target that should be considered and prioritized.
Step 2 - Develop and prioritize risk mitigation options: [Refer to Tab #2]
a. Based on the risk factor analysis, states develop potential strategies tailored to each moderate and high risk milestone. These mitigation strategies will be detailed and specific to each milestone, but can be broadly categorized as:
- Communication and outreach strategies
- Operational and human resource strategies
- Technical strategies (e.g. increase functionality testing)
- Policy/legislative strategies
When considering these various strategies, states should also think about the general approaches they can use to address identified risks, including:
- Identify ways to reduce the probability or the impact of the risk
- Define actions/contingencies to be taken in response to risk
- Avoid the threat or condition by eliminating the cause
b. Second, the state can prioritize which strategies:
- Are likely to have the greatest impact and
- Fit within an acceptable set of resource parameters/constraints.
Using the template on Tab #2, states can list the relevant risk mitigation options associated with each risk factor previously identified (on Tab #1). For each option/strategy, it will be helpful for states to consider the following (as noted in Columns E and F):
(1) The feasibility of the strategy based on current resources (i.e. funding, staffing, time) – this should be ranked as low, medium or high feasibility based on current level of resources at the state’s discretion, and;
(2) The potential impact of this strategy on the success of the SIM work – this can also be rated as low, medium, or high.
Once these two components of each strategy have been considered, states can use this information to prioritize the complete list of risk mitigation options based on their rankings in each cateogry (feasability and impact). For example, options ranking as High in both components may want to be considered first, as compared to options ranking Low in both components. In the example listed on Tab #2, there are six risk mitigation options. When the state prioritizes this list, options that rank as most important (i.e. High and High for both components) should be given more priority than items ranking as less important (i.e. Low and Low for both components). States can also prioritize options within a given risk factor to ensure that each risk factor is addressed through at least one mitigation strategy.
Step 3 - Select risk mitigation strategies: [Refer to Tab #3]
Once the full set of mitigation options has been identified and prioritized, the TA team and PO will meet with the state to confirm the proposed strategies identified as likely to have the greatest impact and to fit within the state’s resource parameters. The state and POs will discuss the extent to which milestones may need to be adjusted to reflect the risk analysis.
The risk mitigation plan can be simplified as noted in the template attached (Tab #3), including a list of the prioritized Risk factors, the related mitigation strategies, the priority category (based on total number of options considered) and any relevant contingencies or activities the state needs to consider before implementing the strategy. Identifying project contingencies will be helpful when linking activities to one another, particularly if select priorities change. States may also find it helpful to include the lead entity who will be involved in the specific strategy, any relevant timelines for a particular option and any relevant workgroups that should be involved.
Revisit and finalize Accountability Targets: [Refer back to Tab #1 as needed]
Based on state’s analysis above, state should work with their PO to revisit original accountability targets and adjust them for potential risks identified.
Alternatively, states may choose to change the target to a more relevant and predictable indication of their SIM progress. Once accountability targets have been finalized, states should plan to re-visit their risk mitigation plan on a quarterly basis to assess new risks and re-prioritize relevant risk mitigation strategies.

## Accountability Targets
Finalized Accountability Milestones
Updated on: [insert date when targets are finalized with CMMI]
Sample accountability milestones included below for example purposes only.
| Accountability Objectives | Accountability Targets for Objectives | End of FY2014 Key Milestones
1 | PCMH | 1. Approval of PCMH SPA | 1. 55% of primary care providers participating in PCMH for one or more payers
|  | 2. Performance reports developed/approved | 2. 60% of Medicaid beneficiaries and 25% of state population enrolled in PCMH
|  | 3. Providers trained on reports and treatment guidelines | 3.
|  | 4. Medicaid provider participation | 4.
|  | 5. Participation from all payers | 5.
2 | BH Health Homes | 1. | 1. 30% of BH population identified for assessment
|  | 2. | 2. 40% of eligible BH providers participating
|  | 3. | 3.
|  | 4. | 4.
|  | 5. | 5.
3 | ACOs | 1. | 1. RFP finalized
|  | 2. | 2. SPA approved
|  | 3. | 3.
|  | 4. | 4.
|  | 5. | 5.
Note on A1: Amy J Anderson: It may flow better to have the accountability targets and key milestones in separate columns?

## 1-Evaluate Risks_Risk Factors
Step 1 - Evaluate Risks within Accountability Target timeline and Define Relevant Risk Factors
Complete the following template by indicating with an "X" the likelihood of each of the accountability target not being achieved (or failing) and the potential impact this failure would have
on the overall project success. It may be helpful to include brief statement elaborating on risk and potential impact.
For each identified medium to high risk below (those events where "X" falls within shaded area), list all relevant risk factors (i.e. factors that lead to the identified risk) in relevant column.
Risk factors can be listed for less significant events if helpful, but this is optional.
States can then prioritize those risk factors that are most in state's control to mitigate (using various levers at their discretion). These can be called out in the third column below (Column Q).
Objective 1 - 55% of primary care providers enrolled in PCMH for one or more payers
Accountability Target #1 |  | 1. Approval of PCMH SPA |  |  | List all relevant risk factors:
|  | Likelihood of Failure |  |  | Risk Factor 1 | Challenging to connect with CMCS to address issues with SPA language
|  | Low | Medium | High | Risk Factor 2 | Approval process is long and somewhat unpredictable
Potential Impact on Project Success | Low |  |  |  | Risk Factor 3 | SPA submission process is time-consuming and complex
| Medium |  |  |  | Risk Factor 4 |  | Prioritized Risk Factors
| High |  |  | X | Risk Factor 5 |  | SPA submission process is time-consuming and complex
Rationale: Fairly lengthy and unpredictable approval process without which payments to providers cannot be formalized. | [6 empty] | Conflicting priorities may delay development of reports as resources are dedicated to shorter term data needs
Upfront costs of implementing program may impede Medicaid providers from participating
Accountability Target #2 |  | Performance reports developed/approved |  |  | List all relevant risk factors:
[5 empty] | Risk Factor 1 | Implementation of supporting reporting system is long and complex (delays are likely)
|  | Likelihood of Failure |  |  | Risk Factor 2 | Conflicting priorities may delay development of reports as resources are dedicated to shorter term data needs | Training consultants hired for training on PCMH are reallocated to other projects
|  | Low | Medium | High | Risk Factor 3 | IT system that supports reporting of provider performance is corrupted/ undermined
Potential Impact on Project Success | Low |  |  |  | Risk Factor 4 | PHI issues impede sharing of relevant data for reporting
| Medium |  | X |  | Risk Factor 5 | IT resources to produce reports are depleted
High
Rationale: Given the complexity of building standardized performance reports across multiple providers, there may be delays in this target.
Accountability Target #4: |  | Medicaid provider participation |  |  | List all relevant risk factors:
|  | Likelihood of Failure |  |  | Risk Factor 1 | Lack of demonstrated cost savings may not encourage Medicaid providers to participate
|  | Low | Medium | High | Risk Factor 2 | Medicaid practices may not be able to sustain both the ongoing care needs of patients and the additional PCMH transformation work
Potential Impact on Project Success | Low |  |  |  | Risk Factor 3 | Alternative delivery system/payment mechanism is developed that appeals to Medicaid
| Medium |  |  |  | Risk Factor 4 | Upfront costs of implementing program may impede Medicaid providers from participating
| High |  | X |  | Risk Factor 5
Rationale: Assuming that PCMH participation is generally voluntary, Medicaid providers may not choose to enroll, at least initially.
Accountability Target #3: |  | Providers trained on reports and treatment guidelines |  |  | List all relevant risk factors:
|  | Likelihood of Failure |  |  | Risk Factor 1 | More providers than anticipated show interest/need in training
|  | Low | Medium | High | Risk Factor 2 | Training consultants hired for training on PCMH are reallocated to other projects
Potential Impact on Project Success | Low |  |  |  | Risk Factor 3 | Funding for coaching/training is reduced/eliminated
| Medium |  |  |  | Risk Factor 4
| High | X |  |  | Risk Factor 5
Rationale: Training needs may be fairly predictable although the impact of incomplete training can be significant.
Accountability Target #5: |  | Participation from all payers |  |  | List all relevant risk factors:
|  | Likelihood of Failure |  |  | Risk Factor 1 | Funding to support PCMH operations/transformation, beyond savings incurred, is limited/reduced
|  | Low | Medium | High | Risk Factor 2 | Savings incurred by providers following guidelines are not significant enough to incentivize payers to participate
Potential Impact on Project Success | Low |  |  |  | Risk Factor 3 | Alternative delivery system/payment mechanisms are developed that appeal to payers
| Medium |  | X |  | Risk Factor 4
| High |  |  |  | Risk Factor 5
Rationale: Assuming participation from non-Medicaid payers is optional, there is a fair likelihood that they will not participate, at least in Yr 1, which will have some impact on the proportion of participating primary care providers.
Note on A14: DBrown: Impact on Project Success – refers to the relative impact the event would have on the progress of the state’s SIM model.
Note on C12: DBrown: Risk of Failure – refers to the relative likelihood of not meeting each accountability target.

## 2 - Risk Mitigation Options
Step 2: Develop and Prioritize Risk Mitigation Options
List all risk mitigation options for each risk factors identified from Tab 1. Rate each mitigation option based on: (1) its feasibility given current resources and (2) its potential impact on
the project using Low, Medium or High. Once all options have been rated, rank the state's overall priority of each strategy. The states should consider the overall priority level based
on the total number of options available.
In this example, there are six risk mitigation options identified. The option that scored as Low (feasibility of resources) and Low (potential impact on SIM progress) is
given the lowest priority level of 8, while the option scoring as High in both feasibility and impact is scored as 1, or the top priority.
Objective 1 - 55% of primary care providers enrolled in PCMH for one or more payers
Prioritized Risk Factors (carried over from previous tab) |  | Risk Mitigation Options | Feasiblity of resources (Low/Med/High) | Potential Impact on SIM progress (Low/Med/High) | Overall Priority Level
Approval of PCMH SPA
SPA submission process is time-consuming and complex | 1 | Temporarily assign additional staff to support SPA process upfront | L | M | 5
Performance reports developed/approved
Conflicting priorities may delay development of reports as resources are dedicated to shorter term data needs | 1 | Manual reporting mechanisms available if automated are not activated on time | M | H | 3
| 2 | Define workarounds for PHI upfront and review appropriate PHI requirements with providers | H | H | 1
| 3 | More frequent check-ins to ensure progress within budget | L | L | 8
Medicaid Provider Participation
Upfront costs of implementing program may impede Medicaid providers from participating | 1 | Coordinate for additional clinical staffing to support Medicaid practices with patient care while practices pursue PCMH transformation work | M | H | 2
| 2 | Link providers with established PCMH practices to support shared learnings/best practices | M | M | 6
Providers trained on reports and treatment guidelines
Training consultants hired for training on PCMH are reallocated to other projects | 1 | Dedicated trainers identified/prioritized for PCMH-related training | M | H | 7
| 2 | Lower cost modalities (remote) for training are introduced to ensure providers are adequately trained; i.e. potential partnership with other organizations with established relationships with providers | M | M | 4

## 3 - Risk Mitigation Plan
Step 3 - Select Risk Mitigation Strategies
Based on the prioritization identified on Tab #2, State teams can select those strategies they plan to focus on and finalize their risk mitigation plan,
as illustrated below.
These strategies and all relevant risk factors should be revisited regularly to ensure that the plan remains up-to-date and accurate.
As such, strategies may be re-prioritized over time. To facilitate logical re-prioritization and ensure appropriate sequencing of activities,
state can include any activities upon which strategies are contingent or necessary precursors as well as relevant timeline, lead entity, and relevant workgroups that should be involved.
Objective 1 - 55% of primary care providers enrolled in PCMH for one or more payers
| Risk Factors | Prioritized Risk Mitigation Strategies | Priority | Lead Entity/Person | Relevant Workgroups | Next Steps | Timeline | Impact on Risk Factor
1 | Conflicting priorities may delay development of reports as resources are dedicated to shorter term data needs | Define workarounds for PHI upfront and review appropriate PHI requirements with providers | 1 | Office of HIT | HIT | Identify upfront PHI concerns based on provider/payer stakeholder input | Feb-Mar 2014
2 | Upfront costs of implementing program may impede Medicaid providers from participating | Coordinate for additional clinical staffing to support Medicaid practices with patient care while practices pursue PCMH transformation work | 2 | DOH | Workforce Development | Identify staffing needs given PCMH requirements | Mar 2014
3 | Conflicting priorities may delay development of reports as resources are dedicated to shorter term data needs | Manual reporting mechanisms available if automated are not activated on time | 3 | DHS/Office of HIT | Payment Improvement/HIT | Define report specs and required data from each participating payer/provider | Mar-Apr 2014

## SIM Issue Log
Issue ID | Issue | Issue Category | Issue Owner (Project Manager) | Status: | Creator (Originator) | Owner | Date created | Updated by (name) | Date last updated | Target resolution date | Priority (H, M, L) | Issue Details (free form) | Impact Description (free form) | Primary Domain Impacted | SIM Objective(s) Impacted | Resolution | Resolution Results | Resolution Date
| CHW Pilot RFP development needs to progress through SIM Governance |  |  | Open | Randy Chenard | Deb Wigand | 2014-02-13 | Randy Chenard | 2014-02-13 |  | L |  |  |  | CDC Obj 2 - CHW Pilot
Molina CR-t

## Weighted Objectives
SIM Objective | Weight Score | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | SIM Objective | Weight Score | SIM Objective | Weight Score | SIM Objective | Weight Score | SIM Objective | Weight Score
HIN Objective 1: | 3 | [12 empty] | MHMC Objective 1: | 3 | MQC Objective 1: | 2 | MaineCare Objective 1: | 3 | Maine CDC Objective 1: | 2
Provide real-time notifications from the HIE to MaineCare and Health System Care Managers when MaineCare members are admitted or discharged from impatient and emergency room settings across all provider organizations connected to the HIE | [13 empty] | Track health care costs to influence the market and inform policy - Construction and maintenance of robust valid data set and ongoing analytics |  | Provide learning collaborative for MaineCare Health Homes |  | Implement MaineCare Accountable Communities Shared Savings ACO Initiative |  | NDPP: Implementation of the National Diabetes Prevention Program (NDPP)
HIN Objective 2: | 3 | [12 empty] | MHMC Objective 2: | 2 | MQC Objective 3: | 3 | MaineCare Objective 2: | 3 | Maine CDC Objective 2: | 1
Provide HIT and HIE adoption incentives to up to 20 Behavioral Health provider sites/organizations | [13 empty] | Value based benefit design: Incentivize use of high value services and high value providers |  | Provide QI Support for Behavioral Health Homes Learning Collaborative |  | Implement MaineCare Behavioral Health Homes Initiative |  | Community Health Workers Pilot Project
HIN Objective 3: | 3 | [12 empty] | MHMC Objective 3: | 3 | MQC Objective 4: | 1 | MaineCare Objective 3: | 1
Provide Health Information Exchange access to Behavioral Health providers | [13 empty] | Identify common metrics across payers for public reporting and alignment with payment – This work relates to the provision of health information to influence markets and inform policy decisions. It figures prominently in efforts around the payment and delivery system reform drivers. |  | Provide QI Support for Patient-Provider Partnership Pilots (P3 Pilots) |  | Develop and implement Physical Health Integration workforce development component to Mental Health Rehabilitation Technician/Community (MHRT/C) Certification curriculum.6
HIN Objective 4: | 1 | [12 empty] | MHMC Objective 4: | 2 |  |  | MaineCare Objective 4: | 1
Provide a clinical dashboard to MaineCare from the HIE enabling MaineCare to clinically monitor MaineCare members’ health care utilization and outcomes at the population and individual level. Develop and deploy real-time discrete data feeds for MaineCare Prescription data to HIN. | [13 empty] | Provide Primary Care providers access to claims data for their patient panels (portals) |  |  |  | Provide training to Primary Care Practices on serving youth and adults with Autism Spectrum Disorder and Intellectual Disabilities.7
HIN Objective 5: | 1 | [12 empty] | MHMC Objective 5: | 2
Provide Maine patients with access to their statewide HIE record leveraging the “Blue Button” standards promoted by the Office of the National Coordinator for HIT (ONC). HIN will conduct a twelve month pilot with a provider organization to make the patient chart available via a certified EHR portal administered by the pilot site. | [13 empty] | Provide practice reports reflecting practice performance on outcomes measures
[14 empty] | MHMC Objective 6: | 1
Consumer engagement and education regarding payment and system delivery reform
|  | Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs |  |  |  | Year 2 Targets: 1) Refined metrics, as appropriate, based on trends and on market experience 2) Increase in number of covered lives enrolled in plans incorporating narrowly contstructed VBIC, to include alignment of copays/deductibles, utilization of high value providers as determined by MHMC Gent Better Maine rankings or ACI metrics and use of shared decision making of all preference senstives services. Enrollment in plans with such designs will grow from 0 to 10k in Year 1. |  |  |  | Year 3 Targets: 1- Refined metrics, as appropriate, based on trends and on market experience 2- increase in number of covered lives enrolled in plans incorporating VBID from 10 k to 30k
|  | Year 1 Target: Complete design of portal and required analytics;.50 practices will adopt the portals in the first year. |  |  |  | Year 2 Targets: Deliver portal functionality to all requesting providers. Estimated additional uptake: est. additional 20%, bearing in mind that adoption is voluntary |  |  |  | Year 3 Targets: Deliver portal functionality to all requesting providers. Estimated additional uptake: est. additional 20%, bearing in mind that adoption is voluntary
Produce practice reports for all primary care practices indicating their interest in receiving them. While we will be able to produce reports for any primary care practice that serve a critical mass of patients, practices themselves must make the decision to actively request, review and use the reports. PCMH practices represent approximately 25% of primary care practices; all receive the reports. We estimated 10% of non-PCMH practices will choose to receive reports in Year One. Each new practice will receive an outreach visit.
Go Live Target: Year 1 Target: Educate brokers, patient advocates, HR Specialists, union leaders on merits of VBID. Outreach to 200 people.
|  | Launch enrollment of up to 80 new HH practices in PCMH/HH Learning Collaborative to provide QI support for current 75 PCMH & new HH primary care practices, with total of up to 150 participating practices; determine final NCQA status of high risk practices (may not meet participation requirements by 12/31/13). |  |  |  | Year 2 Targets: Facilitate Learning Collaborative for HH practices; sustain PCMH/HH Learning Collaborative offering support for 100% of Year 2 participating primary care practices. |  |  |  | Year 3 Targets: Sustain PCMH/HH Learning Collaborative offering support for 100% of Year 3 participating practices.
|  | Year 1 Target: Launch enrollment of up to 35 new BHHs into BHH Learning Collaborative to provide QI support for BHH organizations. |  |  |  | Year 2 Targets: Facilitate BHH Learning Collaborative for up to 35 BHHs; sustain BHH Learning Collaborative offering support for 100% of Year 2 participating BHH organizations |  |  |  | Year 3 Targets: Sustain BHH Learning Collaborative for up to 35 BHHs; sustain BHH Learning Collaborative offering support for 100% of Year 3 participating BHH organizations
|  | Year 1 Target: Launch 3 Patient Provider Partnership (P3) Pilots with 9 provider sites. |  |  |  | Year 2 Targets: Support and facilitate learning across 9 provider sites in P3 Pilots; sustain support for 100% of participating provider organizations
|  | Year 1 Target: Implement Accountable Communities that impact 50,000 patient lives above and beyond those impacted through Medical Homes, 3.8% of Maine's 1.3M population. Patients are not limited to MaineCare members attributed under Accountable Communities, since all patients, regardless of attribution status and payer, should be impacted through improved care coordination incented under model. Achieve participation from 6 Accountable Communities, including providers under current Medicare and commercial ACOs within the State (all 4 major health systems plus group of FQHC's). Achieve 25,000 MaineCare lives to Accountable Communities, 8.9% of the 281,000 MaineCare population. |  |  |  | Year 2 Targets: Provide all Accountable Communities with monthly utilization reports drilled down to the Primary Care practice level, and quarterly reports on actual TCOC to date and quality benchmark achievement. Achieve participation by all MaineCare Accountable Communities in 90% of bimonthly ACI learning collaborative meetings. Implement Accountable Communities that impact an additional 5,000 patient lives above and beyond those impacted through Medical Homes, reaching 4.2% of Maine's population. Achieve participation from 2 additional Accountable Communities. Achieve attribution of additional 2,700 MaineCare lives to Accountable Communities, 9.8% of the MaineCare population. |  |  |  | Year 3 Targets: Provide all Accountable Communities with monthly utilization reports drilled down to the Primary Care practice level, and quarterly reports on actual TCOC to date and quality benchmark achievement. Achieve participation by all MaineCare Accountable Communities in 90% of bimonthly ACI learning collaborative meetings. Implement Accountable Communities that impact an additional 5,500 patient lives above and beyond those impacted through Medical Homes, reaching 4.6% of Maine's population. Achieve participation from 2 additional Accountable Communities. Achieve attribution of additional 2,000 MaineCare lives to Accountable Communities, 10.5% of the MaineCare population.
|  | Year 1 Target: Successfully recruit 15 Behavioral Health Home organizations (BHHOs) with 7000 enrolled members with SMI/ SED. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED. |  |  |  | Year 2 Targets: Increase enrolled members to 7700. 3 in-person learning sessions annually, monthly working group, monthly phone and webinar support for 15 BHHOs and partnering practices. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED. |  |  |  | Year 3 Targets: Increase enrolled members to 8500 total. 3 in-person learning sessions annually, monthly working group, monthly phone and webinar support for 15 BHHOs and partnering practices. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED.
|  | Go Live Target: Year 1 Target: Curriculum and training plan developed for Physical Health Integration component to Mental Health Rehabilitation Technician/Community Training |  |  |  | Year 2 Targets: 500 direct service behavioral health individual providers trained in physical health integration. |  |  |  | Year 3 Targets:
|  | Go Live Target: Year 1 Target: Curriculum and training plan developed for Adult Practice Sites Curriculum piloted at 5 Adult Practice Sites Training conducted at 15 pediatric sites There are over 400 primary care practice sites in Maine. |  |  |  | Year 2 Targets: Training conducted at 30 pediatric sites Training conducted at 55 adult practice sites There are over 400 primary care practice sites in Maine. |  |  |  | Year 3 Targets: Training conducted at 15 pediatric sites Training conducted at 60 adult practice sites There are over 400 primary care practice sites in Maine.
|  | Year 1 Target: 5 out of 15 NDPP provider sites have written agreements and are delivering NDPP to MaineCare beneficiaries. |  |  |  | Year 2 Targets: 1) Policy developed by MaineCare and Maine CDC to support the sustainable structure for NDPP reimbursement. 2) PCMH/ACO care delivery structures are utilizing pre-diabetes/diabetes algorithm to support/enhance patient care. |  |  |  | Year 3 Targets: 1) Over 15 NDPP provider sites have written agreements and are delivering NDPP to MaineCare beneficiaries. Multiple payers are engaged in payment test demonstration linked to program outcomes. 2) 300 out of 29,312 NDPP eligible beneficiaries have completed program over 3 years of SIM Grant.
|  | Year 1 Target: 1. Contracts for 5 CHW Pilot sites in place. 2. The 5 CHW pilot sites will have formal referral mechanisms with at least one and up to 3 providers. |  |  |  | Year 2 Targets: 1. CHW clients identified with a caseload of 15-20 clients for intensive service, and 30-50 clients for less intensive service. 9 |  |  |  | Year 3 Targets: 1. CHW clients identified with a caseload of 15-20 clients for intensive service, and 30-50 clients for less intensive service.
Note on C31: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on C39: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on C41: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3

## Issues
Issue ID | Issue | Issue Category | Issue Owner (Project Manager) | Status: | Creator (Originator) | Owner | Date created | Updated by (name) | Date last updated | Target resolution date | Priority (H, M, L) | Issue Details (free form) | Impact Description (free form) | Primary Domain Impacted | SIM Objective(s) Impacted | Resolution | Resolution Results | Resolution Date
3 | Health Home Practice increase |  | MQC is unable to support additional health homes | Open | Randy Chenard | Michelle Probert | 2014-03-03 | Randy Chenard | 2014-03-03 |  | M | 25 new provider sites are joining HH program in Spring 2014. there was no budgeted support for these practices. | MaineCare is out of compliance with MaineCare rule requiring provision of learning collaborative and providers are less likely to succeed in meeting program requirements and achieving triple aim, if unable to support these additional Health Homes | 3 | MQC Objective 1 - LC for MaineCare HH's MaineCare Objective 1 - Implement ACCs | Assess whether funds can be reallocated within SIM.