## FY 1Q14
Quarter | 7/1/2013 - 9/30/2013
ME Innov Model Entity | Goal for Quarter | Probability of Accomplishing Goal |  | Quality Counts
SIM Program | Complete RFP Process for 10 remaining entities | 75-100%
| Complete establishment of sub-committees | 75-100%
| Hire and establish additional SIM State of Maine roles | 75-100%
| Complete driver diagram detail, focused on inclusion of core measures from CMMI | 75-100%
| Evolve overall SIM project plan, creating traceability from Project Plan to Driver diagrams | 25-75%
| Establish sub-committee reporting process, including risk/issue log population and process for escalation of items to Steering Committee and State of Maine leadership team | 75-100%
CDC | National Diabetes Prevention Program: |  | 75-100% | HealthInfoNet
| Maine CDC will re-engage with MaineCare staff in early August to complete planning and implamentaitons of payments structure, rule making, and program oversitestructure for successful implamentations tracking, and evaluation. | 75-100% | 25-75% | MHMC
| Community Health Worker Pilot |  |  | CDC
| Maine CDC staff will begin regularly scheduled meetings with the CHW Project Manager to ensure timely completion of contract deliverables. | 75-100%
HealthInfoNet
| Obtain provider release of information approvals and begin MaineCare contract | 75-100%
| Complete and Release RFP to Behavioral Health Providers | 75-100%
None this quarter
| Schedule and meet with MaineCare, MMIS, and Gould staff to obtain technology details and determine dashboard elements | 75-100%
| Determine PHR Pilot Site | 75-100%
Quality Counts
| Launch HH practice communication plan | 75-100% | in progress | High
| Recruit, train and deploy team of quality improvement (QI) professionals and technical assistance (TA) providers | 25-75% | in progress | Meduim
| Collect, track and manage HH practice key demographics and characteristics | 75-100% | in progress | High
| Implement data management structure to support HH practice transformation | 25-75% | in progress | Meduim
| Assess HH practice current state | 25-75% | in progress | Assessment will continue into the Operational Phase, due to magnitude of the task
| Develop and implement HH Education Plan | 25-75% | in progress | Meduim
| Collect HH practice Baseline measures on Core Expectations | 75-100% | in progress | High
| Participate in SIM Governance Structure; Develop SIM Workgroup Support Approach; Participate in SIM Evaluation Requirements; Report on HH Progress | 75-100% |  | High
MHMC
| Partner with the State to finalize an Operational Phase contract | 75-100%
| Establish advance infrastructure (hiring staff, securing tools) aligned with detailed budget proposals to ensure a state of readiness to execute on defined deliverables | 75-100%
| Build plan to launch and lead the Payment Reform SIM Work Group to include: | 75-100%
*Defining membership
*Reaching common agreement on scope of work
*Establishing meeting norms (standing agenda, meeting frequency)
*Process to provide required input to build an overall SIM status report for Governance groups
*Define in partnership with the State the issue escalation process
| Iteratively develop a detailed work plan for defined SIM Operational Phase deliverables | 75-100%
| Actively contribute to development of the SIM Operational Plan due to CMMI on 8/1/13, including completion of specific assigned plan sections, work plans and driver diagram components | 75-100%
| Provide on-going support to SIM Program Manager over the course of the Planning Phase | 75-100%
| Complete established work plan submilestones during Planning Phase to ensure readiness for early Operational Phase deliverables. This includes but is not limited to execution of all necessary BAAs and DUAs; modification of existing contract with HDMS; outreach to additional participants for PTE, ACI, and Health Care Cost Workgroups; schedule Q4 meetings of all work groups; begin construction of provider portals and practice reports; initialize improvements to provider database; receive data and begin to run analytics | 75-100%