## Exec Status Summary
SIM Domain
Time Period | SIM Program | Payment Reform | Delivery System Reform | Data Infrastructure | Evaluation
Planning Phase Accomplishments | Operational Plan Approval | Established scope of work | Detailed work plan developed | Established scope of work | Develop Evaluation RFP
7/1/13 - 9/30/13 | Executive Level Program Plan Development | Finalized PR subcommittee | Plan developed to launch and lead the Service Delivery Reform Subcommittee | Finalized DI subcommittee
| Governance, including Subcommittees, established | MHMC ramp up of staffing to begin SIM testing and development | Established advance infrastructure | HIN ramp up of staffing to begin SIM testing and development
Initial convening of ACI/PTE workgroups
|  | Begin Accountable Care | Community Implementation
Begin Behavioral Health Home Implemenation
Testing Phase Quarterly Goals | Hiring additional SIM resources | Execute DUA’s w/ MaineCare | Est Health Home Learning Collaborative infrastructure | Clinical Dashboard: Meet with stakeholders to confirm analytics | Launch RFP and contract with evaluation contractor
10/1 /13 – 12/31/13 | Budget Finalization | SOW between MHDO/MHDS | Launch and manage HH Cmn Plan | MaineCare Discrete Medication Data Capture
| Year 1 contract finalization | Onboard staff for data activities | Launch and Manage HH Education Plan | Begin Blue Button Pilot Implementation
| Program Plan Synchronization | Reconvene Healthcare Cost Workgroup and convene new Behavioral Healthcare Cost Workgroup | Launch and Manage HH Data Mnmt Plan | Begin Providing HIE access to BH Providers
| Reporting Process Finalization | Identify metrics for public reporting through the work of the PTE Workgroups | Assess NCQA status of HH Practices | HIT/HIE Adoption Incentives Awardees determined
| SIM Metric Development | Define and adopt ACO standards | Clarifiy MaineCare requs for measure reporting | Begin building and testing MaineCare ED notificaitons
|  | Id BH clinical consultant | Est participation requirements
|  | Dev VBID and PR media campaign | Ensure CCT connection
Provide practice reporting to PCPs
Id PCP interested in claims portals
Begin Patient Exp of Care Reports
|  | Continue Accountable Care | Community Implementation
|  | Continue Behavioral | Health Home | Implementation
|  | Release ACC | RFA and select applicants
|  | Develop Behavioral | Health Hom Enrollment | Provider Portal
|  | Progress on CMS | SPA Approval for BHH and ACC
|  | Draft MaineCare | Rule for Behavioral Homes
Execute NDP State Capacity Assessment
Outlook (Green, Yellow, Red) | Challenge in building metric consensus | Lack of confidence in dependencies | Lack of confidence in dependencies | Lack of confidence in dependencies | Degree of complexity

## Budget Summary
| Budget for Period | Spent | Remaining
State | 266824 | 167966 | 98858 | 54119
MHMC | 980360 | 980360 | 0 | 41276
QC | 171671 | 142883 | 28788 | 47488
HIN | 863335 | 863335 | 0 | 142883
Total | 2282190 | 2154544 | 127646
0.055931