## Program
Maine SIM Grant SST - Executive Level Project Plan with Accountability Targets
SIM Partner Organization: SIM Program Management |  |  |  |  | Lead/Point for Organization: Randy Chenard |  |  |  |  | Milestone Timeline | [11 empty] | Risks & Dependencies |  |  | Known Risks Associated With Task | Dependencies Comments Link to ID#
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | SIM Funding Fully Supports, Enhances, or Accelerates this Activity | Planning Period 7/1/13-9/30/13 | Year 1 10/1/13-9/30/2014 |  |  |  | Year 2 10/1/14-9/30/15 |  |  |  | Year 3 10/1/15-9/30/16 |  |  |  | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
N/A | X | X | X | Objective 1: Manage SIM Governance Process/Structure
[6 empty] | PG 1 | Develop and facilitate Steering Committee meetings and process | x | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 2 | Develop and Facilitate Leadership meetings and process | x | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 3 | Develop and oversee Subcommittee meetings and process | x | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 4 | Execute Risk/Issue escalation and mitigation process | x | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
Objective 1: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target: Establish all governance groups including membership, accountabilities,; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Governance structure developed and operational at beginning of test Year 1 Target: Manage governance structure and facilitate collaboration across stakeholder groups; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Manage governance structure and facilitate collaboration across stakeholder groups; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Manage governance structure and facilitate collaboration across stakeholder groups
Objective 1: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 12750; Year 1 10/1/13-9/30/2014 Q1: 72684; Year 2 10/1/14-9/30/15 Q1: 72684; Year 3 10/1/15-9/30/16 Q1: 72684
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | SIM Funding Fully Supports, Enhances, or Accelerates this Activity | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
N/A | X | X | X | Objective 2: Develop, Manage, and adjust SIM Operational Plan
[6 empty] | PG 6 | Develop Operational Plan | X | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 7 | Adjust Operational plan | X | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 8 | Begin SIM Communication Plan Development | X | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 9 | Execute SIM Communications Plan | X | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 10 | Begin and Execute Risk/Issue Management Process | X | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 11 | Begin and execute SIM status reporting process | X | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
Objective 2 Accountability Targets: | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Develop Operational Plan and gain CMMI approval; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Operational Plan Approved Year 1 Target: Manage Operational Plan; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Manage Operational Plan; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Manage Operational Plan
Objective 2: Annual Cost | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 17000; Year 1 10/1/13-9/30/2014 Q1: 135172; Year 2 10/1/14-9/30/15 Q1: 96912; Year 3 10/1/15-9/30/16 Q1: 96912
N/A | X | X | X | Objective 3: Manage SIM Project Plans and Overall Budget
[6 empty] | PG 12 | Developed required SIM Contracts | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 13 | Require and facilitate the development project plan for all SIM partners | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | PG 14 | Manage project plans, adjust and report as required | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
Objective 3: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Develop integrated project plan; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Project Plan Developed Year 1 Target: Manage project plan; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Manage Project Plan; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Manage Project Plan
Objective 3: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 12750; Year 1 10/1/13-9/30/2014 Q1: 72684; Year 2 10/1/14-9/30/15 Q1: 72684; Year 3 10/1/15-9/30/16 Q1: 72684
Note on BC2: Chenard, Randal: Include dependencies on tasks inside AND outside your organization. Any dependencies should include Notes for greater explanation
Note on A3: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B3: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E3: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F3: If available
Note on G3: Numbering convention important to tie dependencies together in column X
Note on H3: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I3: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A10: Targets must be quantifiable. Examples: - # of providers reached - # of patients touched - # of reports developed - # of programs developed etc.
Note on J10: Main accomplishments expected during planning period
Note on K10: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on A12: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B12: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E12: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F12: If available
Note on G12: Numbering convention important to tie dependencies together in column X
Note on H12: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I12: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding

## HealthInfoNet
Maine SIM Grant - Executive Level Project Plan with Accountability Targets
SIM Partner Organization: HealthInfoNet |  |  |  |  | Lead/Point for Organization: Shaun Alfreds, Katie Sendze |  |  |  |  | Milestone Timeline | [11 empty] | Risks & Dependencies
Secondary Driver | Subcommittee |  |  | Key Objective | Link to DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 | Year 1 10/1/13-9/30/2014 |  |  |  | Year 2 10/1/14-9/30/15 |  |  |  | Year 3 10/1/15-9/30/16 |  |  |  | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice, and payment decisions |  | X | X | Objective 1: Provide real-time notifications from the HIE to MaineCare and health system Care Managers when MaineCare members are admitted or discharged from inpatient and emergency room settings across all provider organizations connected to the HIE.
[5 empty] | VI.A VIII. G V XI.A | HIN 1 | Obtain PHI 'Data Release Authorization' with HIE participating Providers | [14 empty] | Provider site (38 hospitals) could deny release of PHI | Current provider participants in HIE | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 2 | Establish DUA with MaineCare for PHI access | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 3 | Convene MaineCare partners to build data feeds | [14 empty] | Delay in contract process or agreement | MaineCare contract process and rules | 1,2 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 4 | Build and test production of notifications technology and workflow | [14 empty] | Delay in ability for MaineCare to provide eligibility data | Dependent on MaineCare resources and participation | 3 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 5 | Implement use of notifications. Work with MaineCare stakeholders and provider participants to provide content and process improvements related to notifications that supports SIM initiatives. This includes education about and related to notifications process and workflow. | [14 empty] | Care manager and provider engagement in workflow | MC and provider org. leadership engagement to implement new workflows | 4 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 1: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target 1) Establishment of a new user class of the HIE (originally provider based) as a Payors - Starting with Medicaid. 2) Create Data Use Argent (DUA) for MaineCare, Request Permissions for Sharing of PHI with New HIE Participant Class.; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: As of October 1, 2013, make notifications available to 1,6001 Medicaid Providers and Care Managers across the state. Year 1 Target: Increase from 4502 to an average of 550 unique provider organization users either accessing the ED notifications or the HIE portal per week.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: 1) Increase making notifications available to 1,800 Medicaid Provider and Care Managers/Care Coordinators. 2) Increase to an average of 600 unique provider organization users either accessing the ED notifications or the HIE portal per week.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: 1) Increase making notifications available to 2,000 Medicaid Provider and Care Managers/Care Coordinators. 2) Increase to an average of 800 unique provider organization users either accessing the ED notifications or the HIE portal per week.
Objective 1: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 45616.9; Year 1 10/1/13-9/30/2014 Q1: 164863.6; Year 2 10/1/14-9/30/15 Q1: 195813.508; Year 3 10/1/15-9/30/16 Q1: 186674.9349
Secondary Driver | Subcommittee |  |  | Key Objective | Link to DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice, and payment decisions |  | X | X | Objective 2: Provide HIT and HIE adoption incentives to up to 20 Behavioral Health provider sites/organizations.
[5 empty] | V.A VI.A X.A | HIN 6 | Develop RFP for HIT and HIE adoption incentives | [15 empty] | Subcommittee start dates and process | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 7 | Release the RFP | [16 empty] | 6 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 8 | Announce awardees | [16 empty] | 7 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 9 | Support Quality Measure development and reporting via the HIE for awardees; Participate in ensuring quality reporting measures are defined with feedback from BH providers to include EHR capacity for submitting discrete data that supports specific quality measures as determined by the SIM Steering and Sub Committees through the statewide HIE. | [14 empty] | Variable and complex technical and process barriers to enable data for quality reporting | Stakeholder participation/consensus, technology | 11 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 10 | RFP Milestone 1: EHR purchase, implementation, optimization, and/or upgrade - $35,000 per awardee | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 11 | RFP Milestone 2: Active interfaces with the statewide HIE- $10,000 per awardee | [14 empty] | Legal risks: 1) 42 CFR-Part 2 limitations as it relates to MH integration, provider side patient education to opt-in to their MH data 2) Contract timelines and delays for participation | Provider technology resources beyond the grant, patient education to opt-in | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 12 | RFP Milestone 3: Quality Reporting/eMeasurement with the HIE- $25,000 per awardee | [14 empty] | Barriers to data integration and interoperability | Bidirectional data integration, provider participation, patient's opting-in | 12 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 2 Accountability Targets: | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Establishment of Data Infrastructure Subcommittee (DIS) charge and membership. Determine parameters for behavioral health participation in the incentive program based on expectations of EHR adoption and capability to participate in data activities in years 2 and 3. Draft RFP for presentation to the DIS in October.; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: RFP requirements prepared for presentation to DIS. Year 1 Targets: 20 Behavioral health organizations3 demonstrate live use of EHR and milestone 1 incentive delivered.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: 20 organizations have access to the HIE portal and notifications and milestone 2 incentive delivered.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: All 20 organization's participating in e-quality measurement using the data submitted to the HIE and milestone 3 incentive delivered.
Objective 2: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 46764.58; Year 1 10/1/13-9/30/2014 Q1: 957058.3; Year 2 10/1/14-9/30/15 Q1: 632670.05; Year 3 10/1/15-9/30/16 Q1: 478837.61
Secondary Driver | Subcommittee |  |  | Key Objective | Link to DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice, and payment decisions; Improved continuum of care |  | X | X | Objective 3: Provide Health Information Exchange access to Behavioral Health providers
[5 empty] | V.A VI.A X.A XI.A | HIN 13 | HIN will create access to the HIE Year 1: HIE access, up to 10 year 1 | [14 empty] | Legal risks: 1) 42 CFR-Part 2 limitations as it relates to Mental Health integration, provider side patient education to opt-in to their MH data 2) Contract timelines and delays for participation | Provider technology resources beyond the grant, patient education to opt-in | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 14 | Year 2: HIE access, up to 15 year 2 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 15 | Year 3: HIE access, up to 15 year 3 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 16 | HIN will bi-directionally connect up to 10 organizations to the HIE over three years: Year 1: Connect up to 5 bi-directional HIE sites | [16 empty] | 13 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 17 | Year 2: Connect up to 7 bi-directional HIE sites | [16 empty] | 16 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 18 | Year 3: Connect up to 10 bi-directional HIE sites | [16 empty] | 17 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 19 | Provide Clinical Quality Measurement as developed in Objective 2 to participating sites through HIE tools. | [16 empty] | 12,16,17,18 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 3: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Establish HIE participant agreement parameters for new BH HIE participants. Determine RFP requirements for presentation to DIS in October for approval.; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: RFP requirements prepared for presentation to DIS. Year 1 Targets: Up to 5 sites go live with bi-directional HIE participation.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Up to 7 sites go live with bi-directional HIE participation.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Up to 10 sites go live with bi-directional HIE participation.
Objective 3: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 64968.9; Year 1 10/1/13-9/30/2014 Q1: 478771.7; Year 2 10/1/14-9/30/15 Q1: 569067.85; Year 3 10/1/15-9/30/16 Q1: 590673.41
Secondary Driver | Subcommittee |  |  | Key Objective | Link to DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice, and payment decisions |  |  | X | Objective 4: Provide a clinical dashboard to MaineCare from the HIE enabling MaineCare to clinically monitor MaineCare members’ health care utilization and outcomes at the population and individual level. Develop and deploy real-time discrete data feeds for MaineCare Prescription data to HIN.
[5 empty] | V.A VI.A | HIN 20 | Collaborate with MaineCare to develop and define specific “Use Case” for MaineCare staff to access PHI through the HIN dashboard. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 21 | Send letters to all HIN provider participants informing them of the project and requesting approval for sharing PHI with MaineCare; confirm approval from each participant for this “use Case” PHI release. | [14 empty] | Provider participants of the HIE could deny their authorization to support the Use Case for PHI release to MaineCare. | Communication support with MaineCare as a partner. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 22 | Clinical Dashboard: Meet with stakeholders during the pre-testing period to demonstrate current functionality and identify and confirm specific analytic needs that might be met by HIN’s data warehouse. | [15 empty] | Current unknown data requirements and questions associated are undetermined at this time | 1,2, 3 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 23 | Develop recurring meetings (quarterly) with appropriate SIM teams to evaluate measures, address data deficiencies, adjust metrics etc. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 24 | Develop and deploy the Dashboard: | [15 empty] | The dashboard will be dependent upon the monthly submission of the MaineCare eligibility file as described in objective 1. | 20 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 25 | Review the capability of HIN’s HIE data warehouse to calculate and define quality measures that support MaineCare’s Health Homes program. Establish criteria and specifications for warehouse enhancements as needed and within budget. | [15 empty] | Partnership with MaineCare leadership related to quality measures work, definitions, and implementation within SIM. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 26 | MaineCare Discrete Medication Data Capture: During pre-testing phase, meet with MaineCare MMIS and Goold staff and develop project plan for deploying real-time discrete medication data feeds from MaineCare. [Note- this activity will be necessary to support analytics for MaineCare patients on prescription use.] | [14 empty] | Medicaid and state vendor, Molina HealthCare, resources available to the project and timeline of those resources | Dependent on ID 41 and the work around state requirements and support available to make this happen | 26, 3 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 27 | Begin technical implementation of discrete medication feeds in October 2013 with go-live targeted for no later than March 2014. [Note: this timeline is dependent on the availability of resources at MaineCare to support this activity] | [14 empty] | Medicaid and state vendor, Molina HealthCare, resources available to the project and timeline of those resources | Dependent on ID 41 and 48 the work around state requirements and support available to make this happen | 20
Objective 4: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Build, test and establish HIE dashboard and data warehouse in secure data center (shared by HIE). Work with legal team to develop HIPAA Business Associate Agreements (BAA) and Data Use Agreement (DUA) with MaineCare.; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Provide MaineCare BAA and DUA for AAG review and approval. Year 1 Targets: 1. Consistent meeting with MaineCare established for MaineCare IT staff to facilitate discrete medication feeds and roles for the dashboard access. 2. DIS approval of data access strategy. 3. Go-Live with real-time medication feeds 4. Establishment of VPNs for MaineCare to access dashboard. 5. Provide training for MaineCare staff in Dashboard use. 6. Make 291,000+ population data available in HIN Dashboard.4; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: 1. Continued provision of Dashboard to MaineCare. 2. Consistent data flow for MaineCare medication information into the HIE.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: 1. Continued provision of Dashboard to MaineCare. 2. Consistent data flow for MaineCare medication information into the HIE.
Objective 4: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 319276.1; Year 1 10/1/13-9/30/2014 Q1: 607204.4; Year 2 10/1/14-9/30/15 Q1: 620833.53; Year 3 10/1/15-9/30/16 Q1: 605171.54
Secondary Driver | Subcommittee |  |  | Key Objective | Link to DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice, and payment decisions; Improved continuum of care; Consumer Engagement; Patient and Family Centered Care |  | X | X | Objective 5: 50-57, Provide Maine patients with access to their statewide HIE record leveraging the “Blue Button” standards promoted by the Office of the National Coordinator for HIT (ONC). HIN will conduct a twelve month pilot with a provider organization to make the patient chart available via a certified EHR portal administered by the pilot site.
[5 empty] | V.A VIII.G | HIN 28 | During pre-testing phase, identify criteria for community pilot site for “Blue-Button” deployment. |  | Planning Period 7/1/13-9/30/13 2013-10-01: ü; Year 2 10/1/14-9/30/15 Q1: n/a |  | Provider participant that can meet the required criteria for implementation must be willing to volunteer to the pilot.
[6 empty] | HIN 29 | Submit project criteria to the DIS and proceed to select pilot site volunteer. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q4
[6 empty] | HIN 30 | Confirm agreement with Pilot Partner and proceed to conduct the 12-month pilot to test and modify technical requirements for PHR-HIE access using national standards | [14 empty] | Provider volunteer could not be able to prioritize this project | Provider volunteer | 24 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 2 10/1/14-9/30/15 Q2
[6 empty] | HIN 31 | Engage health care delivery communications and administration teams at pilot site on educating patients on the new PHR "Blue Button" technology. | [14 empty] | Provider volunteer could not be able to prioritize this project | Site engagement | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q4
[6 empty] | HIN 32 | Engage Care Managers/health care delivery staff of pilot site on educating patients on how to access and use their record. | [14 empty] | Provider volunteer could not be able to prioritize this project | Site engagement | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q4
[6 empty] | HIN 33 | Determine specifications that would support future statewide PHR roll out using best practice learning's from the pilot | [16 empty] | 26,27,28 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q4
Objective 5: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target: 1. Testing of CCD export by HIN (using green CCD established by Mitre/ONC under previous contract), 2. Finalize licensing costs/contracts for IT vendor partners and establish audit and authorization profiles at HIN for end users. 3. Establishment of criteria for choosing PHR CCD export pilot site for presentation to the DIS in October.; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: As of October 1, 2013, criteria for PHR pilot prepared and finalized for presentation to the DIS in October. Year 1 targets: Establishment of contract with pilot site, establish project management process for implementation, implementation of PHR CCD export by month 6. Demonstrated download of CCD by 5%5 of the pilot sites active PHR users w/in go-live period of project.
Objective 5: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 387410.51; Year 1 10/1/13-9/30/2014 Q1: 416642.05; Year 2 10/1/14-9/30/15 Q1: 0; Year 3 10/1/15-9/30/16 Q1: 0
Secondary Driver | Subcommittee |  |  | Key Objective | Link to DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice and payment decisions/Multi-Stakeholder Coalition Building and Support |  |  | ü | Objective 6: Ensure effective management of SIM Data Infrastructure Subcommittee to promote sustainability of reform developed through SIM
[5 empty] | A, T | HIN 34 | Identify and finalize Subcommittee membership | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 35 | Convene Subcommittee | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | HIN 36 | Ensure participation and process according to established protocols | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 6 Accountability Targets: | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target: establish infrastructure, membership for Data Infrastructure Subcommittee; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: identify membership for Payment Reform Subcommittee Year 1 Target: Provide support for Subcommittee in manner that supports active participation of membership; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Provide support for Subcommittee in manner that supports active participation of membership; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Provide support for Subcommittee in manner that supports active participation of membership
Objective 6: Annual Cost | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 0; Year 1 10/1/13-9/30/2014 Q1: 0; Year 2 10/1/14-9/30/15 Q1: 0; Year 3 10/1/15-9/30/16 Q1: 0
Commitments from HIN/MHMC during Plan Synchronization: • Insuring a synergistic and integrative approach to the work of PTE- BH and the HIN BH RFP Quality work. • Clearly outlining and communicating the process for a collaboration between HIN, health care provider(s) (Covered Entity(is)) and MHMC in integrating clinical and administrative claims data for a possible proof of concept.
Note on A3: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B3: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E3: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F3: If available
Note on G3: Numbering convention important to tie dependencies together in column X
Note on H3: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I3: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A11: Targets must be quantifiable. Examples: - # of providers reached - # of patients touched - # of reports developed - # of programs developed etc.
Note on J11: Main accomplishments expected during planning period
Note on K11: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on A13: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B13: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E13: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F13: If available
Note on G13: Numbering convention important to tie dependencies together in column X
Note on H13: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I13: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A25: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B25: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E25: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F25: If available
Note on G25: Numbering convention important to tie dependencies together in column X
Note on H25: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I25: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A37: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B37: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E37: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F37: If available
Note on G37: Numbering convention important to tie dependencies together in column X
Note on H37: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I37: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A50: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B50: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E50: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F50: If available
Note on G50: Numbering convention important to tie dependencies together in column X
Note on H50: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I50: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A61: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B61: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E61: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F61: If available
Note on G61: Numbering convention important to tie dependencies together in column X
Note on H61: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I61: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding

## Maine CDC
Maine SIM Grant - Executive Level Project Plan with Accountability Targets
SIM Partner Organization: Maine CDC |  |  |  |  | Lead/Point for Organization: Deb Wigand |  |  |  |  | Milestone Timeline | [11 empty] | Risks & Dependencies
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 | Year 1 10/1/13-9/30/2014 |  |  |  | Year 2 10/1/14-9/30/15 |  |  |  | Year 3 10/1/15-9/30/16 |  |  |  | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Aligned payment models, Patient-family centeredness of care, Consumer engagement, Improved continuum of care | x | x |  | Objective 1: NDPP: Implementation of the National Diabetes Prevention Program (NDPP).Need to discuss the targets with new direction that does not include MaineCare reimbursement during tests.
[5 empty] | VA IIIC XIIIA IIIA IIIB VB | CDC 1 | State capacity assessment. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | CDC 2 | Formal S-Code reimbursement structure defined and established. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | CDC 3 | Trained supported Lifestyle Coach Workforce. | [14 empty] | Delay in contract process or agreement to release SIM funds | DHHS releases funds for NDPP Lifestyle Coach Trainings | MC 1,2 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | CDC 4 | CDC-Recognized NDPP providers complete annual written agreement with Maine CDC to provide NDPP to qualified MaineCare beneficiaries. | [14 empty] | Can not limit to just MaineCare beneficiaries. | Multiple payer involvement in SIM. | MC | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | CDC 5 | Policy/Statutes amended to support sustainable NDPP delivery/reimbursement. | [14 empty] | Needed for Maine CDC to accomplish the SIM accountability target of “Sustainable NDPP payment structure recognized by all payers in Maine”. | Future policy change options post SIM demonstration on sustainable NDPP payment structure. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | CDC 6 | NDPP payment tests developed with SIM partners (MaineCare, MHMC, MQC) guidance/support and TA from U.S. CDC. | [14 empty] | NDPP payment reform tests must demonstrate value to payers. | Inclusion in VBID development, tests, payer engagement. ACI committee engagement. | MHMC 16, 17, 18, 19, 22, 37 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | CDC 7 | NDPP payment tests evaluation developed with SIM partners (MaineCare, MHMC, MQC, HIN) guidance/support and TA from U.S. CDC. | [14 empty] | MaineCare direct support/assistance needed to help shape and redirect NDPP payment tests to align with new/emerging trends with public and private payers (VBID, HH, PCMH/ACO, etc.) involved in SIM & other MaineCare activities. | MaineCare provides guidance/support/input at key milestones over the 3 years of SIM grant. | MC 1,2 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q3; Year 2 10/1/14-9/30/15 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | CDC 8 | RFP for NDPP payment tests developed and released. | [14 empty] | Delay in contract process or agreement to release SIM funds | Funds released for payment tests RFP awardees/renewals | MC | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 1: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target 1) MaineCare completed research on feasibility of retired S-Code assignment for NDPP Core & Post Core. 2) MaineCare will reimburse for NDPP delivery to beneficiaries 18 y/o and older who are at high risk or with pre-diabetes according to U.S. CDC DPRP standards.; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: NDPP delivery reimbursement for contracted NDPP provider sites to MaineCare beneficiaries. NDPP payment tests RFP released. Year 1 Target: 5 out of 15 NDPP provider sites have written agreements and are delivering NDPP to MaineCare beneficiaries.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: 1) Policy developed by MaineCare and Maine CDC to support the sustainable structure for NDPP reimbursement. 2) PCMH/ACO care delivery structures are utilizing pre-diabetes/diabetes algorithm to support/enhance patient care.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: 1) Over 15 NDPP provider sites have written agreements and are delivering NDPP to MaineCare beneficiaries. Multiple payers are engaged in payment test demonstration linked to program outcomes. 2) 300 out of 29,312 NDPP eligible beneficiaries have completed program over 3 years of SIM Grant.
Objective 1: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Year 1 10/1/13-9/30/2014 Q1: 130500; Year 2 10/1/14-9/30/15 Q1: 85500; Year 3 10/1/15-9/30/16 Q1: 85500
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Aligned payment models, Patient-family centeredness of care, Consumer engagement, Improved continuum of care | x | x |  | Objective 2: CHW Pilot Project |  |  |  | Would not occur without SIM funding, which provides 100% of the funds for the CHW Pilot.
[5 empty] | III.B, IV.A, V.B,V.C, VII.A, VII.B, XI.A,B,C,XIII.A, XV.A, | CDC 6 | RFP issued for CHW Pilot Sites | bar: 2013-10-01 to 85500 Q4
[6 empty] | CDC 7 | CHW Pilot Site contract approval | bar: 2013-10-01 to 85500 Q4
[6 empty] | CDC 8 | 3 CHWs hired at pilot sites. | [14 empty] | CHW effectiveness on interdisciplinary teams is dependent on providers' familiarity with CHW model and best practices for integration. | Successful integration of CHWs into HH/PCMH/CCTs relies on providers having knowledge and awareness (i.e. education) on how to best integrate, utilize and support CHWs ( i.e. Inclusion as key learning within QC/MC Collaboratives) | QC1/MC1 MC19 | bar: 2013-10-01 to 85500 Q4
[6 empty] | CDC 9 | CHW clients identified | bar: 2013-10-01 to 85500 Q4
[6 empty] | CDC 10 | CHW services will commence | bar: 2013-10-01 to 85500 Q4
[6 empty] | CDC 11 | Recommendations for sustainability and use of CHW model in Maine | [14 empty] | Future sustainability dependent on payment models other than self-funding | 1.MC modeling of total cost of care should be inclusive of CHW services as part of bundled payments 2. Healthcare Cost Workgroup metrics should include costs/savings related to integration of CHW services into health care teams. | MC 5 MHMC 12 | bar: 2013-10-01 to 85500 Q4
Objective 2: Accountability Targets | [8 empty] | 2013-10-01: Planning Period Target 1. Vendor selected for Project Management, Workgroup meting to define scope and approach.; 130500 Q1: Go Live Target: Transformed healthcare system integrates community health workers through a pilot that demonstrates CHWs as an effective, sustainable element. Year 1 Target: 1. Contracts for 5 CHW Pilot sites in place. 2. The 5 CHW pilot sites will have formal referral mechanisms with at least one and up to 3 providers.; 85500 Q1: Year 2 Targets: 1. CHW clients identified with a caseload of 15-20 clients for intensive service, and 30-50 clients for less intensive service. 9; 85500 Q1: Year 3 Targets: 1. CHW clients identified with a caseload of 15-20 clients for intensive service, and 30-50 clients for less intensive service.
Objective 2: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | 2013-10-01: 389620; 130500 Q1: 779239; 85500 Q1: 779239; 85500 Q1: 389620
Consumer education /access to information |  | x |  | Objective 3: Patient engagement communication Project Remove from SST - Not conducting this strategy at this time |  |  |  | Would not occur w/out SIM funding; leveraging experience with tobacco communications.
[5 empty] | VIII F | CDC 12 | Communications vendor is selected | bar: 130500 Q1
[6 empty] | CDC 13 | Workplan and strategy developed | bar: 130500 Q2 to 130500 Q3
[6 empty] | CDC 14 | Develop and roll out four separate patient engagement media/communication campaigns | bar: 130500 Q4 to 85500 Q1; 85500 Q3; 85500 Q1
Objective 1: Accountability Targets | [8 empty] | 2013-10-01: Planning Period Target; 130500 Q1: Go Live Target: Public supported with health communication messages that promote appropriate use of healthcare services and value of CHWs. Year 1 Target: 1 campaign Contract; 85500 Q1: Year 2 Targets: 2 campaigns; 85500 Q1: Year 3 Targets: 1 campaign
Objective 3: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | 130500 Q1: 250000; 85500 Q1: 500000; 85500 Q1: 500000
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Note on BC2: Chenard, Randal: Include dependencies on tasks inside AND outside your organization. Any dependencies should include Notes for greater explanation
Note on A3: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B3: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E3: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F3: If available
Note on G3: Numbering convention important to tie dependencies together in column X
Note on H3: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I3: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A14: Targets must be quantifiable. Examples: - # of providers reached - # of patients touched - # of reports developed - # of programs developed etc.
Note on J14: Main accomplishments expected during planning period
Note on K14: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on A24: Targets must be quantifiable. Examples: - # of providers reached - # of patients touched - # of reports developed - # of programs developed etc.
Note on J24: Main accomplishments expected during planning period
Note on K24: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on A32: Targets must be quantifiable. Examples: - # of providers reached - # of patients touched - # of reports developed - # of programs developed etc.
Note on J32: Main accomplishments expected during planning period
Note on K32: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3

## Maine Quality Counts
Maine SIM Grant - Executive Level Project Plan with Accountability Targets
SIM Partner Organization: Maine Quality Counts |  |  |  |  | Lead/Point for Organization: Lisa Letourneau; Lisa Tuttle |  |  |  |  | Milestone Timeline | [11 empty] | Risks & Dependencies
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 | Year 1 10/1/13-9/30/2014 |  |  |  | Year 2 10/1/14-9/30/15 |  |  |  | Year 3 10/1/15-9/30/16 |  |  |  | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Improved Continuum of Care | ü | ü |  | Objective 1: Provide Learning Collaborative for MaineCare Health Homes
[5 empty] | XIV | QC 1 | Establish organizational infrastructure for HH Learning Collaborative | A. This objective/activity would not occur without SIM funding | [13 empty] | Maine workforce shortage of QI professionals | Gap in connecting HH primary care practices to the HIE and functions | VI.A, VIII.G, V, XI.A | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 2 | Launch and manage HH Communication Plan | A. This objective/activity would not occur without SIM funding | [14 empty] | Clarification of HH Screening Tool requirements required for 2014 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 3 | Launch and Manage HH Education Plan; support PCMH/HH Learning Collab | A. This objective/activity would not occur without SIM funding | [13 empty] | Maine workforce shortage of QI professionals | Clarification of HH Screening Tool requirements required for 2014 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 4 | Launch and Manage HH Data Management Plan | A. This objective/activity would not occur without SIM funding | [13 empty] | State infrastructure may not support automated colln of clinical measures | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 5 | Assess NCQA status of HH practices | A. This objective/activity would not occur without SIM funding | [13 empty] | HH practices may not meet NCQA PCMH requirements | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 6 | Assess baseline Core Expectation status; Assess HH practices onsite | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 7 | Clarify MaineCare requirements for HH quality measure reporting | A. This objective/activity would not occur without SIM funding | [13 empty] | Lack of clarity on approach may delay | Dependent upon State ability to collect HH quality measures | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 8 | Establish HH participation requirements | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 9 | Finalize HH practice participation based on requirements | A. This objective/activity would not occur without SIM funding | [13 empty] | Practice may not be able to accomplish requirements of NCQA and meet Must Pass elements | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC9.1 | Provide Quality Improvement support to HH practices, supporting and monitoring their transformation to implement the HH model | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 10 | Ensure connection to CCT structure | A. This objective/activity would not occur without SIM funding | [13 empty] | Potential confusion between CCT, CHW, Care Mgt and Case Mgt functions - clarity in functional appropriateness essential for success | Critical to ensure Medicaid enhance payment structure in order to sustain HH model | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 11 | Prepare for Sustainability of HH/CCT model | [14 empty] | Enhanced payment model required to sustain | Critical to ensure Medicaid enhance payment structure in order to sustain HH model | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 1: Accountability Targets | [7 empty] | Work would not be funded without SIM | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Establish organizational infrastructure to support and staff Learning Collaborative; Establish baseline assessments on status of HH practices; Perform onsite assessments on up to 80 new HH Practices; Develop HH Communications Plan; Develop HH Education Plan; Develop HH Data Management Plan.; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Launch enrollment of up to 80 new HH practices in PCMH/HH Learning Collaborative to provide QI support for current 75 PCMH & new HH primary care practices, with total of up to 150 participating practices; determine final NCQA status of high risk practices (may not meet participation requirements by 12/31/13). Year 1 Target: Support PCMH/HH Learning Collaborative, offering supporting for 100% of participating practices; provide QI support to ensure that ≥75% of the new HH practices reach Must-Pass elements; and ≥75% practices implement HH Year 2 MaineCare screening requirements. [Note: PCMH & HH practices est'd to provide care for approx. 432,000 patients]; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Facilitate Learning Collaborative for HH practices; sustain PCMH/HH Learning Collaborative offering support for 100% of Year 2 participating primary care practices.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Sustain PCMH/HH Learning Collaborative offering support for 100% of Year 3 participating practices.
Objective 1: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 171670.8031; Year 1 10/1/13-9/30/2014 Q1: 938933; Year 2 10/1/14-9/30/15 Q1: 968356; Year 3 10/1/15-9/30/16 Q1: 983607 | Obj. subtotal | 3062566.8031
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Improved Continuum of Care |  | ü |  | Objective 2: Provide support for SIM Delivery System Reform Subcommittee
[5 empty] | XIV | QC 12 | Identify and finalize Subcommittee membership | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 13 | Convene Delivery System Reform Subcommittee | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 14 | Ensure participation and process according to established protocols | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 2 Accountability Targets: | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target: establish infrastructure, membership for Delivery System Reform Subcommittee; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: identify membership for Delivery System Reform Subcommittee Year 1 Target: Provide support for Subcommittee in manner that supports active participation of membership; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Provide support for Subcommittee in manner that supports active participation of membership; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Provide support for Subcommittee in manner that supports active participation of membership
Objective 2: Annual Cost | [8 empty] | Year 1 10/1/13-9/30/2014 Q1: 29689; Year 2 10/1/14-9/30/15 Q1: 29731; Year 3 10/1/15-9/30/16 Q1: 41440 | Obj. subtotal | 100860
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Improved Continuum of Care |  | ü |  | Objective 3: Provide QI Support for Behavioral Health Homes Learning Collaborative
[6 empty] | QC 15 | Identify & support BHHs multi-stakeholder advisory committee (e.g. QC Behavioral Health Comm) | A. This objective/activity would not occur without SIM funding | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 16 | Launch and manage BHH Communication Plan | A. This objective/activity would not occur without SIM funding | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 17 | Establish organizational infrastructure for BHH Learning Collaborative; hire BHH Program Manager & contract with BH consultant | A. This objective/activity would not occur without SIM funding | [13 empty] | Maine workforce shortage of QI professionals | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 18 | Identify & manage plan for integrating peer support into BHH curriculum & Learning Collab | [14 empty] | Financial resources for peer support | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 19 | Launch and Manage BHH Education Plan, including BH & PCMH/HH curriculum; support BHHs Learning Collaborative | A. This objective/activity would not occur without SIM funding | [13 empty] | Maine workforce shortage of QI professionals | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 20 | Identify & manage plan for integrating BHH Education Plan with PCMH/HHs Education Plan | [14 empty] | Number of potential new HH practices unknown; learning needs will vary | Dependent on coord with PCMH/HHs | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 21 | Launch and Manage BHH Data Management Plan | A. This objective/activity would not occur without SIM funding | [13 empty] | State infrastructure may not support automated collection of clinical measures | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 22 | Assess baseline status of BHHs on Core Expectation | A. This objective/activity would not occur without SIM funding | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 23 | Clarify MaineCare requirements for BHH quality measure reporting | A. This objective/activity would not occur without SIM funding | [13 empty] | Lack of clarity on approach may delay | Dependent upon State ability to collect BHH clinical quality measures | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 24 | Establish BHH participation requirements | A. This objective/activity would not occur without SIM funding | [13 empty] | Lack of clarity on approach may delay | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 25 | Ensure connection to CCT structure | A. This objective/activity would not occur without SIM funding | [13 empty] | Potential confusion between CCT, CHW, Care Mgt and Case Mgt functions - clarity in functional appropriateness essential for success | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
Objective 3 Accountability Targets: | [8 empty] | Year 1 10/1/13-9/30/2014 Q1: Year 1 Target: Launch enrollment of up to 35 new BHHs into BHH Learning Collaborative to provide QI support for BHH organizations.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Facilitate BHH Learning Collaborative for up to 35 BHHs; sustain BHH Learning Collaborative offering support for 100% of Year 2 participating BHH organizations; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Sustain BHH Learning Collaborative for up to 35 BHHs; sustain BHH Learning Collaborative offering support for 100% of Year 3 participating BHH organizations
Objective 3: Annual Cost | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 0; Year 1 10/1/13-9/30/2014 Q1: 317560; Year 2 10/1/14-9/30/15 Q1: 387088; Year 3 10/1/15-9/30/16 Q1: 323460 | Obj. subtotal | 1028108
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Improved Continuum of Care |  | ü |  | Objective 4: Provide QI Support for Patient-Provider Partnership Pilots (P3 Pilots)
[6 empty] | QC 26 | Identify priorities for focus of P3 Pilots | A. This objective/activity would not occur without SIM funding | [13 empty] | Need direction from DSR Subcomm, SIM Steering Comm | Coordinate with VBID efforts | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 27 | Identify & support P3 multi-stakeholder advisory committee (e.g. ME Choosing Wisely Leadership Grp) | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 28 | Launch and manage P3 Communication Plan | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 29 | Establish organizational infrastructure for P3 Pilots; contract with P3 Program Manager & hire staff | A. This objective/activity would not occur without SIM funding | [13 empty] | Maine workforce shortage of QI professionals | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 30 | Establish & manage process for selecting provider sites for participation in P3 Pilots | A. This objective/activity would not occur without SIM funding | [13 empty] | Sufficient interest from provider grps | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 31 | Identify & secure formal SDM tools | [14 empty] | Must be able to support costs of formal SDM tool | Coordinate with VBID efforts | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 32 | Establish & manage process for providing technical assistance & facilitating collaborative learning across provider Pilot sites | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 33 | Launch & manage 1st P3 Pilot (e.g. Choosing Wisely) with 3 provider sites | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 34 | Launch & manage 2nd P3 Pilot (e.g. SDM) with 3 provider sites | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | QC 35 | Launch & manage 3rd P3 Pilot (TBD) with 3 provider sites | A. This objective/activity would not occur without SIM funding | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 4 Accountability Targets: | [8 empty] | Year 1 10/1/13-9/30/2014 Q1: Year 1 Target: Launch 3 Patient Provider Partnership (P3) Pilots with 9 provider sites.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Support and facilitate learning across 9 provider sites in P3 Pilots; sustain support for 100% of participating provider organizations
Objective 4: Annual Cost | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 0; Year 1 10/1/13-9/30/2014 Q1: 336003; Year 2 10/1/14-9/30/15 Q1: 178629.7179; Year 3 10/1/15-9/30/16 Q1: 0 | Obj. subtotal | 514632.7179
Totals | [7 empty] | Yearly Totals | Planning Period 7/1/13-9/30/13 2013-10-01: 171670.8031; Year 1 10/1/13-9/30/2014 Q1: 1622185; Year 1 10/1/13-9/30/2014 Q2: 0; Year 1 10/1/13-9/30/2014 Q3: 0; Year 1 10/1/13-9/30/2014 Q4: 0; Year 2 10/1/14-9/30/15 Q1: 1563804.7179; Year 3 10/1/15-9/30/16 Q1: 1348507 | 4706168.5211
QC budget totals
Note on BC2: Chenard, Randal: Include dependencies on tasks inside AND outside your organization. Any dependencies should include Notes for greater explanation
Note on A3: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B3: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E3: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F3: If available
Note on G3: Numbering convention important to tie dependencies together in column X
Note on H3: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I3: Potential input: A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A18: Targets must be quantifiable. Examples: - # of providers reached - # of patients touched - # of reports developed - # of programs developed etc.
Note on J18: Main accomplishments expected during planning period
Note on K18: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3
Note on A20: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B20: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E20: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F20: If available
Note on G20: Numbering convention important to tie dependencies together in column X
Note on H20: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I20: Potential input: A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A29: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B29: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E29: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F29: If available
Note on G29: Numbering convention important to tie dependencies together in column X
Note on H29: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I29: Potential input: A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A45: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B45: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E45: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F45: If available
Note on G45: Numbering convention important to tie dependencies together in column X
Note on H45: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I45: Potential input: A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding

## MaineCare
Maine SIM Grant - Executive Level Project Plan with Accountability Targets
SIM Partner Organization: MaineCare |  |  |  |  | Lead/Point for Organization: Michelle Probert |  |  |  |  | Milestone Timeline | [11 empty] | Risks & Dependencies
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 | Year 1 10/1/13-9/30/2014 |  |  |  | Year 2 10/1/14-9/30/15 |  |  |  | Year 3 10/1/15-9/30/16 |  |  |  | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Aligned Payment Models | X | X |  | Objective 1: Implement MaineCare Accountable Communities Shared Savings ACO Initiative
[5 empty] | B.7, C.9, G.15. G.17, H.22, H.23, S.46 | MC 1 | Conduct provider outreach and education, including regional forums on proposed model | SIM is funding the ACI and PTE workgroups, which are integral to the provider outreach and education strategy. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MC 2 | Work with Accountable Care Implementation (ACI) workgroup to educate and recruit providers, provide learning collaborative support, and achieve multi-payer alignment on quality measures and value-based payment models. | SIM is funding the ACI workgroup. | [16 empty] | May not belong here? Want to make the ACI connection with Accountable Communities explicit. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MC 3 | Develop and finalize quality framework | Development of the quality framework is benefiting from input by SIM partners, PTE, and SIM governance subcommittees. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MC 4 | Issue provider Request for Applications (RFA) and select eligible applicants | N/A | bar: Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MC 5 | Conduct AC attribution and develop benchmark Total Cost of Care (TCOC) amounts | N/A. The analytics for the initial benchmark TCOC amounts is already under subcontract with the State. SIM partner MHMC will be duplicating this analysis in order to provide data analytics support to Accountable Communities. | [13 empty] | Potential for problems with claims data | Timeliness of TCOC calculations by Accountable Community; replication of analysis for data analytics reports to providers | 4 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 6 | Develop Analytics Support For Accountable Communities | SIM partner MHMC will be providing the data analytics support for practices within Accountable Communities. Funding for the HIT infrastructure, staff, and report development are all coming through SIM. | [13 empty] | Ability to replicate actuaries' analysis | Replication of TCOC, attribution for analytic reports | 5 | Not sure if this should be a MHMC objective? | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 7 | Obtain CMS approval for State Plan Amendment | N/A (assistance from CMMI) | [13 empty] | Plan SPA submission for 11/1. SPA approval timeline dependent on CMS. CMS has been difficult to connect with. | Timely SPA approval | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 8 | Draft and adopt MaineCare rule for Accountable Communities | N/A | [15 empty] | 7 | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 9 | Finalization of Accountable Communities contracts, Implementation | N/A (see SIM contributions leading up to this milestone) | [15 empty] | 6, 7, 8 | bar: Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MC 10 | Provide Accountable Communities with analytic reports | SIM partner MHMC will be providing the data analytics support for practices within Accountable Communities. Funding for staff, report development and distribution, and assistance to practices are all coming through SIM. | [15 empty] | 6, 7 | bar: Year 1 10/1/13-9/30/2014 Q3 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MC 11 | Open Accountable Communities RFA for additional rounds of applications | N/A | bar: Year 1 10/1/13-9/30/2014 Q4; Year 2 10/1/14-9/30/15 Q4
Objective 1: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Issue RFA Year 1 Target: Implement Accountable Communities that impact 50,000 patient lives above and beyond those impacted through Medical Homes, 3.8% of Maine's 1.3M population. Patients are not limited to MaineCare members attributed under Accountable Communities, since all patients, regardless of attribution status and payer, should be impacted through improved care coordination incented under model. Achieve participation from 6 Accountable Communities, including providers under current Medicare and commercial ACOs within the State (all 4 major health systems plus group of FQHC's). Achieve 25,000 MaineCare lives to Accountable Communities, 8.9% of the 281,000 MaineCare population.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Provide all Accountable Communities with monthly utilization reports drilled down to the Primary Care practice level, and quarterly reports on actual TCOC to date and quality benchmark achievement. Achieve participation by all MaineCare Accountable Communities in 90% of bimonthly ACI learning collaborative meetings. Implement Accountable Communities that impact an additional 5,000 patient lives above and beyond those impacted through Medical Homes, reaching 4.2% of Maine's population. Achieve participation from 2 additional Accountable Communities. Achieve attribution of additional 2,700 MaineCare lives to Accountable Communities, 9.8% of the MaineCare population.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Provide all Accountable Communities with monthly utilization reports drilled down to the Primary Care practice level, and quarterly reports on actual TCOC to date and quality benchmark achievement. Achieve participation by all MaineCare Accountable Communities in 90% of bimonthly ACI learning collaborative meetings. Implement Accountable Communities that impact an additional 5,500 patient lives above and beyond those impacted through Medical Homes, reaching 4.6% of Maine's population. Achieve participation from 2 additional Accountable Communities. Achieve attribution of additional 2,000 MaineCare lives to Accountable Communities, 10.5% of the MaineCare population.
Objective 1: Annual Cost (Aligns with annual budget total's submitted with contract) | [24 empty] | Doesn't include any associated MHMC costs
Aligned Payment Models Improved Continuum of Care | X | X | X | Objective 2: Implement MaineCare Behavioral Health Homes Initiative
[5 empty] | B.7, C.9, G.15. G.17, H.22, H.23 | MC 12 | Conduct provider outreach and education, including regional forums on proposed model | Leveraging SIM-funded relationship with partner Maine Quality Counts to educate and provide outreach to existing Health Home Practices and Community Care Teams regarding the Behavioral Health Homes model. | bar: Planning Period 7/1/13-9/30/13 2013-10-01
[6 empty] | MC 13 | Issue provider Request for Applications (RFA) and select eligible applicants | N/A | bar: Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MC 14 | Obtain CMS approval for State Plan Amendment | N/A | [13 empty] | Plan to submit SPA on 11/15 with retroactive approval to 1/15. State would be at risk while SPA not approved. 90-day approval dependent on CMS comfort with draft SPA. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 15 | Draft and adopt MaineCare rule for Behavioral Health Homes | N/A | [13 empty] | Aggressive timeline. Challenging new area for AAG Office review. | Implementation of rule, initiative | 9 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 16 | Development of Behavioral Health Homes Enrollment System provider portal | N/A | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MC 17 | Eligible member identification and enrollment | N/A | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MC 18 | Contract with entity to implement Behavioral Health Home Learning Collaborative | SIM is fully funding the learning collaborative. | [13 empty] | Lengthy, burdensome State contracting process | Effective date of contract. | 8 | bar: Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MC 19 | Development and implementation of Behavioral Health Home Learning Collaborative | SIM is fully funding the learning collaborative. | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MC 20 | Implementation | N/A | bar: Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 21 | Provide Behavioral Health Homes with utilization and quality reports | SIM funding is being utilized for the development and distribution of multi-payer practice quality and utilization reports. | bar: Year 1 10/1/13-9/30/2014 Q2 to Year 3 10/1/15-9/30/16 Q4
Objective 2 Accountability Targets: | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Complete draft SPA and draft rule Initiate consultations with SAMHSA, CMS; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Year 1 Target: Successfully recruit 15 Behavioral Health Home organizations (BHHOs) with 7000 enrolled members with SMI/ SED. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Increase enrolled members to 7700. 3 in-person learning sessions annually, monthly working group, monthly phone and webinar support for 15 BHHOs and partnering practices. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Increase enrolled members to 8500 total. 3 in-person learning sessions annually, monthly working group, monthly phone and webinar support for 15 BHHOs and partnering practices. There are 75 Behavioral Health Organizations that currently provide services being transformed through Behavioral Health Homes, and about 24,000 members with SMI/SED.
Objective 2: Annual Cost | [8 empty] | Year 1 10/1/13-9/30/2014 Q1: 163636; Year 2 10/1/14-9/30/15 Q1: 218182; Year 3 10/1/15-9/30/16 Q1: 218182 |  |  |  | This doesn't include MHMC costs for utilization and practice reports.
Improved Continuum of Care Patient/Family Centeredness of Care |  | X |  | Objective 3: Develop and implement Physical Health Integration workforce development component to Mental Health Rehabilitation Technician/Community (MHRT/C) Certification curriculum.6
[5 empty] | L.32 | MC 22 | Finalize contract with selected vendor | N/A | bar: Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 23 | Development of curriculum | Funded by SIM | bar: Year 1 10/1/13-9/30/2014 Q2 to Year 1 10/1/13-9/30/2014 Q4
[6 empty] | MC 24 | Implementation of trainings/ curriculum | Funded by SIM | bar: Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
Objective 3: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Year 1 Target: Curriculum and training plan developed for Physical Health Integration component to Mental Health Rehabilitation Technician/Community Training; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: 500 direct service behavioral health individual providers trained in physical health integration.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets:
Objective 3: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Year 1 10/1/13-9/30/2014 Q1: 219357; Year 2 10/1/14-9/30/15 Q1: 342342
Improved Continuum of Care Patient/Family Centeredness of Care |  | X |  | Objective 4: Provide training to Primary Care Practices on serving youth and adults with Autism Spectrum Disorder and Intellectual Disabilities.7
[5 empty] | L.32 | MC 25 | Finalize contract with selected vendor | N/A | bar: Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MC 26 | Provide training to pediatric sites | SIM enables additional 60 pediatric sites to be trained utilizing existing curriculum. | bar: Year 1 10/1/13-9/30/2014 Q3 to Year 3 10/1/15-9/30/16 Q2
[6 empty] | MC 27 | Develop training for adult practice sites | SIM funds development curriculum to serve adults with Intellectual Disabilities and ASD. | bar: Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MC 28 | Implement Adult training at 5 pilot sites | SIM enables pilot of 5 adult practice sites to be trained. | bar: Year 1 10/1/13-9/30/2014 Q4
[6 empty] | MC 29 | Provide training to adult practice sites | SIM enables 115 adult practice sites to be trained. | bar: Year 2 10/1/14-9/30/15 Q1 to Year 3 10/1/15-9/30/16 Q4
Objective 4: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Year 1 Target: Curriculum and training plan developed for Adult Practice Sites Curriculum piloted at 5 Adult Practice Sites Training conducted at 15 pediatric sites There are over 400 primary care practice sites in Maine.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Training conducted at 30 pediatric sites Training conducted at 55 adult practice sites There are over 400 primary care practice sites in Maine.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Training conducted at 15 pediatric sites Training conducted at 60 adult practice sites There are over 400 primary care practice sites in Maine.
Objective 4: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Year 1 10/1/13-9/30/2014 Q1: 42239; Year 2 10/1/14-9/30/15 Q1: 88489; Year 3 10/1/15-9/30/16 Q1: 65738
Note on BC2: Chenard, Randal: Include dependencies on tasks inside AND outside your organization. Any dependencies should include Notes for greater explanation
Note on A3: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B3: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E3: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F3: If available
Note on G3: Numbering convention important to tie dependencies together in column X
Note on H3: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I3: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A17: Targets must be quantifiable. Examples: - # of providers reached - # of patients touched - # of reports developed - # of programs developed etc.
Note on J17: Main accomplishments expected during planning period
Note on K17: Go Live Target = What are we testing beginning on 10/1/3 Year 1 Target - How will we be expanding that test More information s/b provided for Year 1 versus year 2 or 3

## ME Health Mainagement Coalition
Maine SIM Grant - Executive Level Project Plan with Accountability Targets
SIM Partner Organization: Maine Health Management Coalition Foundation | [6 empty] | Lead/Point for Organization: Ellen Schneiter |  |  | Milestone Timeline | [11 empty] | Risks & Dependencies
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 | Year 1 10/1/13-9/30/2014 |  |  |  | Year 2 10/1/14-9/30/15 |  |  |  | Year 3 10/1/15-9/30/16 |  |  |  | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice and payment decisions | ü |  |  | Objective 1: Health information to influence market forces and inform policy: track health care costs
[6 empty] | MHMC 1 | Execute DUAs with CMS to ensure availability of Medicare data | SIM grant funds the processing of Medicare and MaineCare data. The SIM grant provides the financial support for this work, increasing staff resources at MHMC to include ___ FTEs which will work on support of these data. | [13 empty] | Precedent security audits of data vendor by CMS | Provider participants in HIE | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MHMC 2 | Execute BAA with MEDHHS to ensure access to MaineCare data. DUA is incorporated into SIM sub recipient contract between MHMC and MEDHHS. | bar: Planning Period 7/1/13-9/30/13 2013-10-01
[6 empty] | MHMC 3 | Execute/renew agreement with MHDO for receiving commercial claims on an ongoing basis | [14 empty] | Denial of access to claims data (highly unlikely) | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q2; Year 2 10/1/14-9/30/15 Q2; Year 3 10/1/15-9/30/16 Q2
[6 empty] | MHMC 4 | Establish/execute necessary BAAs and DUAs with participating commercial plans to access commercial claims data | bar: Planning Period 7/1/13-9/30/13 2013-10-01
[6 empty] | MHMC 5 | Execute new scope of work between MHMC and data vendor, HDMS | [14 empty] | Delays in processing agreements | Timely execution of SIM contract with DHHS | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MHMC 6 | Onboard additional staff to support data program activities and cost of care activities | [14 empty] | Ability to identify appropriate candidates to fill positions; timely execution of state contract | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MHMC 7 | Update statewide commercial claims on an ongoing, quarterly basis | [14 empty] | Timeliness of availability of datasets. MHDO is transitioning to a new data vendor, which could delay processing. Compliance of commercial claims submitters. | 3, 6 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 8 | Obtain initial Medicare claims data feed; FTP directly to HDMS, implement and QC Medicare data | [14 empty] | Delay in execution of DUA with CMS. Delay in transmission of data from CMS. | 1 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC 9 | Obtain subsequent Medicare claims data feeds to update database; FTP directly to HDMS, implement and QC Medicare data | [14 empty] | Delay in execution of DUA with CMS. Delay in transmission of data from CMS. | 1 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1; Year 2 10/1/14-9/30/15 Q3; Year 3 10/1/15-9/30/16 Q1; Year 3 10/1/15-9/30/16 Q3
[6 empty] | MHMC 10 | Update MaineCare data on a continuing basis; data feeds will be received monthly, but processing to occur on a quarterly basis | [14 empty] | Delays in transmission of data from Molina to HDMS | 2, 5 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 11 | Reconvene Healthcare Cost Workgroup and convene new Behavioral Healthcare Cost Workgroup - hold first meetings | The work around cost of care and, in particular, cost of behavioral health care, would not occur if it were not for SIM. SIM is providing financial support for not only the data management and analysis needed to track and benchmark trends in cost of care, but also for 1 FTE dedicated specifically to work with the Healthcare Cost workgroups. | [13 empty] | Inability to schedule meetings during month of December | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MHMC 12 | Convene regular meetings of Healthcare Cost Workgroups. Work to identify metrics to track cost of care, refining algorithm used in original grant proposal. Must ensure that metrics chosen complement payment reform strategies and benefit design strategies developing in Maine's health are environment. | [14 empty] | Ability to hold successful monthly meetings will hinge on participants' level of stamina for the task and their availability. Timely availability of claims data impacts ability to carry out work for these groups. | 6,09,10,11 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q2 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 13 | Publication of Healthcare Cost Fact Book | The SIM grant is supporting the development of the underlying analyses for the Fact Book, as well as its production and distribution, which would not occur without the grant. | [14 empty] | 12 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4; Year 2 10/1/14-9/30/15 Q2; Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q2; Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 14 | CEO Roundtables convened to inform business and opinion leaders re: cost of care in Maine, trends | The frequency of CEO Roundtables (approximately 2/year) is directly attributable to the grant. | [14 empty] | 12 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4; Year 2 10/1/14-9/30/15 Q2; Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q2; Year 3 10/1/15-9/30/16 Q4
[5 empty] | Sub objective 3.8 Accountable Communities and Related Initiatives | MHMC98 | Participate in MaineCare Accountable Community measurement methodology discussions | ü | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q2 to Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC99 | Replicate AC member attribution using the methodology specified by the Department’s consultant (Deloitte) and approved by the Department. The Department’s consultant (Deloitte) will work with the contractor in implementing the methodology the consultant develops, resolving any issues with the methodology. The Contractor will not carry out the attribution activity until the Department’s consultant and the Department certifies that the methodology is approved and ready for use. | [14 empty] | Consultant fails to complete work on methodology; errors or needed changes are identified during replication process | MC5 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC100 | Replicate AC benchmark PMPMs using the methodology specified by the Department’s consultant (Deloitte) and approved by the Department. The Department’s consultant (Deloitte) will work with the contractor in implementing the methodology the consultant develops, resolving any issues with the methodology. The Contractor will not carry out the calculation of PMPM benchmarks until the Department’s consultant and the Department certifies that the methodology is approved and ready for use. | [14 empty] | Consultant fails to complete work on methodology; errors or needed changes are identified during replication process | MC5 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC101 | Provide monthly utilization reports for ACs | [14 empty] | Consultants fail to complete work on methodology; data required for calculations not available; CMS fails to approve the DHHS State Plan Amendment; no providers participate in AC initiative | The timeline for this activity is dependent upon the actual launch date by the Department of the AC initiative. MHMC98, 99, MC9 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC102 | Provide quarterly quality, attribution, and TCOC reports for ACs | [14 empty] | Consultants fail to complete work on methodology; data required for calculations not available; CMS fails to approve the DHHS State Plan Amendment; no providers participate in AC initiative | The timeline for this activity is dependent upon the actual launch date by the Department of the AC initiative. MHMC 98, 99, MC9 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC103 | Measure and report final Year 1 Accountable Community scorecard and final savings or recoupment payments for each participant in the Department’s Accountable Communities initiative using the methodology specified by the Department’s consultant (Deloitte) and approved by the Department. Detailed requirements of quarterly attribution reconciliation, if needed, will be negotiated between the Contractor and the Department. Successful completion of this activity is predicated on the availability of completed performance year data for each participant in the AC initiative. | [14 empty] | Consultants fail to complete work on methodology, data required for calculations not available; CMS fails to approve the DHHS State Plan Amendment; no providers participate in AC initiative | The timeline for this activity is dependent upon the actual launch date by the Department of the AC initiative. MHMC 98, 99, MC9 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 3 10/1/15-9/30/16 Q1
[6 empty] | MHMC104 | Conduct AC member attribution based on consultant methodology for Year Two of the initiative | [14 empty] | Consultant fails to complete work on methodology | MHMC99 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q2
[6 empty] | MHMC105 | Calculate AC benchmark PMPMs based on consultant methodology for Year Two of the initiative | [14 empty] | Consultant fails to complete work on methodology | MHMC100 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q2
[6 empty] | MHMC106 | Provide monthly utilization reports for HHs | [14 empty] | Data required to run reports is not available | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC107 | Provide monthly utilization reports for BHHs | [14 empty] | Data required to run reports is not available; CMS fails to approve DHHS' State Plan Amendment; no providers enroll in BHH initiative | Actual timing of this activity is dependent upon the Department's ability to launch the BHH initiative. MC20 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC108 | Provide quarterly quality reports for HHs | [14 empty] | Data required to run reports is not available | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC109 | Provide quarterly quality reports for BHHs | [14 empty] | Data required to run reports is not available; CMS fails to approve DHHS' State Plan Amendment; no providers enroll in BHH initiative | Actual timing of this activity is dependent upon the Department's ability to launch the BHH initiative. MC20 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 3 10/1/15-9/30/16 Q4
Objective 1: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Targets: Development and, when feasible, execution of necessary legal agreements required to gain access to claims datasets; Year 1 10/1/13-9/30/2014 Q1: Year One Target: Build claims database that spans Medicare, MaineCare and commercial populations of Maine. This will represent approximately 900k covered lives who are eligible to receive services from Maine's provider community. Providers include all 39 Maine hospitals and all other non-hospital providers in the state who contract with one or more commercial carriers, Medicare and/or MaineCare. (2) Develop/refine appropriate metrics and approach to measuring and tracking cost of care over time. (3) Publish initial edition of Healthcare Cost Fact Book and convene CEO Roundtable.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: (1) Maintain access to broad-based dataset. (2) Publish two updated editions of Fact Book. (3) Convene 2 additional CEO Roundtables, increasing attendance from 20 to 30 opinion leaders.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: (1) Maintain access to broad-based dataset. (2) Issue two additional updates of Fact book. (3) Convene two additional CEO Roundtables, increasing attendance from 30 to 50 CEOs.
Objective 1: Annual Cost (Aligns with annual budget total's submitted with contract) | [9 empty] | 1537917 | 1161809 | 1161809 | 1318891 | 1367203 | 1161809 | 1318891 | 1161809 | 1371468 | 1318891 | 1161809 | 1161809
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice and payment decisions | ü |  |  | Objective 2: Health information to influence market forces and inform policy: value based benefit design
[6 empty] | MHMC 15 | Onboard VBID staff person | The SIM grant enables support for 1 FTE dedicated to the work around value based design | [13 empty] | Implementation contract with DHHS not signed timely, may delay hire | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q2; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q2
[6 empty] | MHMC 16 | Survey plans to document current or planned activity for payment based on quality performance and cost effectiveness. | The MHMC has been engaged in work around value based design for some time. In addition to providing a dedicated staff resource for this work, the presence of the grant provides important impetus and energy around this initiative which is a non-quantifiable asset. | [14 empty] | 1 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 17 | Identify and develop key elements of value based design, based on the work of the ACI and Healthcare Cost Workgroups. Specify measures of quality performance and cost effectiveness, giving special consideration to alignment with those measures being used by payers - including Medicare and MaineCare. | [15 empty] | 1, 2 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q3; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 18 | Convene VBID workgroup and explore opportunities to align patients' out of pocket costs such as copays and deductibles with the value of services provided, as well as opportunities identified by the Healthcare Cost Workgroups and the ACI workgroup focusing on patient incentives as well as provider incentives. Learning from the experiences of payers and provider communities to date. | [15 empty] | 1, 2 |  | we should try to set a benchmark here - how many people are enrolled in plans that employ VBID on October 1, and how that will change over time. | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q3; Year 2 10/1/14-9/30/15 Q1 to Year 3 10/1/15-9/30/16 Q1; Year 3 10/1/15-9/30/16 Q3
[6 empty] | MHMC 19 | Evaluate and test the operability of alternative designs with regard to legal constraints including confidentiality statues, the ability of provider systems to implement and align with features of desired designs and the ability of paymers to implement such designs. Adopt set of core measures | [15 empty] | 4 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q3 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 20 | Rank plans according to adopted VBID metrics; update on at least an annual basis | [15 empty] | 4, 5 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 21 | Publicly report VBID rankings, updating at least annually | [15 empty] | 6 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 22 | Advance change across payers by working with the ACI Workgroup, engaging consumers and employees around the issue of VBID and by engaging CEO decision makers around the potential of this type of benefit design. | MHMC works with employer leaders to advance this type of change in coverage. SIM is providing enhanced support for this type of effort by providing dedicated staff support to the work around VBID as well as funding to support additional CEO Roundtables, which will serve as forums and learning Collaboratives for the state's business leaders. | [14 empty] | 1-7 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 22.1 | MHMC will introduce the NDPP at the ACI workgroup. ACI may serve as a venue for the NDPP pilot to showcase its work, educate purchasers regarding the program, building familiarity with the NDPP across a broad community. One aspect of this effort will be to work with the purchasers in ACI to identify candidate measures that may be used to gauge the relative impact/success of the introduction of the NDPP in a pilot workplace. The MHMC will help the DCD recruit commercial plan sponsors to participate in the CDC's NDPP pilot. | The Coalition would likely not become actively involved in working with the State to identify potential business participants for the State's NDPP initiative, if not for the SIM project. | [13 empty] | Although the MHMC will provide the CDC with an opportunity to recruit ACI employer participants into the NDPP pilot and although the MHMC will work to encourage such participation, there is the risk that no participating employers will choose to enroll in the initiative. The MHMC cannot guarantee such participation. | The CDC is responsible for conduct of the NDPP pilot. If the pilot does not get off the ground, there will be no need for this discussion to occur at the ACI. Participation of the NDPP/CDC staff in the educational session(s). | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q2; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 22.2 | MHMC will provide the already compiled methodology and results of State of Maine TDES program evaluation. | The Coalition would share the information relative the to TDES evaluation even in the absence of SIM. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 1 10/1/13-9/30/2014 Q1; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 22.3 | Using data and information generated by the Maine CDC regarding the outcomes or performance of the NDPP in the pilot worksites, the MHMC will work with ACI participants to help identify possible alternate, sustainable payment models for the National Diabetes Prevention Program (NDPP) program. This work will be informed by the relative success of the pilot project - as marked against performance measures and anticipated outcomes. | The Coalition is not likely to have become actively involved with the State's NDPP initiative in the absence of SIM. | [13 empty] | The NDPP pilot effort may fail to collect data and information germane to the measures of success important to purchasers and payers participating in the ACI. Alternatively, outcomes may not be persuasive enough to encourage widespread adoption of the program in the workplace. The short time frame within which the grant occurs may not provide sufficient time to collect such convincing evidence. This will compromise the likelihood that participants will endorse or adopt any recommended funding strategies. | Successful conduct of the NDPP pilot in a timely manner, including collection of valid, reliable outcomes measures. | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 22.4 | MHMC will introduce the NDPP to the VBID workgroup, in an effort to recommend elements of value based insurance design that can be used to reinforce the tenets of the NDPP. | The Coalition is not likely to have become actively involved with the State's NDPP initiative in the absence of SIM. | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 22.5 | The Maine Health Management Coalition will introduce CDC's Community Health Worker (CHW) pilots to ACI steering committee, as well as seek input on the pilots from the Payment Reform Subcommittee, to inform and educate these participants on the CHW initiative being conducted by the Maine CDC. The pilot is slated to begin in the spring of 2014. If the CHW pilot proves successful, ACI participants will explore strategies to develop and implement sustainable funding mechanisms to support this service on an on-going basis. Due to the timing of the pilot and the need to allow it to run for some substantial period of time in order to prove itself, this discussion will not occur before the latter half of Year Three of the project. | The Coalition would not have become involved with the State's CHW initiative were it not for the SIM project. | [13 empty] | The CHW pilot is a project of the Maine CDC. As such, the CDC is wholly responsible for the pilot getting off the ground in a timely fashion and running smoothly. The CDC is also responsible for collecting valid, reliable data regarding the outcomes of the pilot. Purchasers, payers and providers will need to be provided good outcomes data in order to move the issue of sustainable funding forward in these MHMC workgroups. The risk of not having such data within the short timeframe of the SIM grant appears to be relatively high. | The CDC is responsible for conduct of the CHW pilot. If the pilot does not get off the ground, there will be no need for this discussion to occur at the ACI. Participation by the CHW/CDC staff in these work sessions. | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q3; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
Objective 2 Accountability Targets: | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target; Year 1 10/1/13-9/30/2014 Q1: Year 1 Targets: (1) Adoption of core set of metrics against which plan designs may be benchmarked (2) Publication of initial rankings of benefit designs; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: (1) Refined metrics, as appropriate, based on trends and on market experience (2) increase in number of covered lives enrolled in plans incorporating narrowly constructed VBID , to include alignment of copays/deductibles, utilization of high value providers as determined by MHMC Get Better Maine rankings or ACI metrics, and use of shared decision making of all preference sensitive services. Enrollment in plans with such designs will grow from 0 to 10k in Year 1.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: (1) Refined metrics, as appropriate, based on trends and on market experience (2) increase in number of covered lives enrolled in plans incorporating VBID from 10k to 30k.
Objective 2: Annual Cost | [9 empty] | 351107 | 232651 | 232651 | 216476 | 555130 | 232651 | 216476 | 232651 | 380333 | 216476 | 232651 | 232651
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice and payment decisions | ü | ü |  | Objective 3: Health information to influence market forces and inform policy: Identify common metrics across payers for public reporting and alignment with payment through the work of the PTE Workgroups
Sub objective 3.1: PTE Physician Sub objective 3.2: APC Subjective 3.3: PTE Systems Sub objective 4.2: PTE Systems | [5 empty] | MHMC 23 | Data Collection/Evaluation: Practice Clinical and Office System Evaluation Data. Physician, Practice Data - aggregation of data re: provider ratings for clinical recognition. Providers submit data to NCQA or BTE for selected metrics, or submit data directly to MHMCF | SIM provides critical support to this work, allowing for the scaling up of the volume of work that accompanies the grant initiative. This support comes in the form of additional FTE support dedicated to the PTE process itself, as well as data management and analytic support. Work on APC recognition would not occur in the absence of SIM | [13 empty] | Providers fail to submit data | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 24 | MHMCF downloads recognitions, or data for recognitions, from -- Bridges to Excellence (RDE file) -- CMS (meaningful use) -- IMPACT (pediatitec immunization) -- Practices (pediatric asthma data) | [14 empty] | Providers fail to submit data | 1 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 25 | Update Provider Database on a real time basis of the MHMC provider hierarchy. This includes tracking providers, their site(s) of practice, specialty, health plan affiliation(s), ACO affiliation, and so on. | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 26 | Publically Report Physician Practice Ratings - Reporting across practices | [14 empty] | PTE Workgroup fails to reach consensus re: metrics/reporting or Board fails to approve | 2 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 27 | PTE Physicians group to identify core metrics for APC recognition | [14 empty] | PTE Workgroup fails to reach consensus re: metrics/reporting or Board fails to approve | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q2; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 28 | Testing of identified metrics for feasibility | [14 empty] | Feasibility tests fail, triggering need to reconsider metrics set | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q2 to Year 1 10/1/13-9/30/2014 Q3; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 29 | PTE adoption of APC metrics including value assignment; board approval | [14 empty] | PTE Workgroup fails to reach consensus re: metrics/reporting or Board fails to approve | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 30 | Publication of APC metrics | [14 empty] | PTE Workgroup fails to reach consensus re: metrics/reporting or Board fails to approve | 7 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 31 | Updating of published metrics | [14 empty] | Updated data is not submitted timely | 8 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1 to Year 3 10/1/15-9/30/16 Q1; Year 3 10/1/15-9/30/16 Q3
[6 empty] | MHMC 32 | Data Collection/Evaluation, Hospitals and Systems - aggregation of data re: hospital and System ratings/recognition program. Obtain data for hospital evaluations from: -- CMS (appropriate care, patient experience) -- Onpoint ( Medication Safety) -- Leapfrog (patient safety, early deliverables) -- MHDO (Care transitions, falls with injury) | [14 empty] | Providers fail to submit data | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 33 | Compute, assignment of ratings, hospital review, governance review and update website - public reporting | [14 empty] | PTE Workgroup fails to reach consensus re: metrics/reporting or Board fails to approve | 11 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 34 | Publically Report Hospital Ratings - Reporting across hospitals | [15 empty] | 12 | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q4
Sub objective 3.4: ACI Metrics | [5 empty] | MHMC 35 | ACI Workgroup Meetings | The ACI Workgroup will undergo a revitalization and refocusing/redoubling of effort under SIM. The work of this group will expand to include the development of ACI metrics, to allow benchmarking of organizations; this effort is attributable to SIM. | [13 empty] | Group operates by consensus; may decide to meet every other month | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 36 | Define and adopt ACO standards, predicated on accepted principles of the group; vet reporting metrics up through PTE Systems to MHMC Board. | [14 empty] | Group fails to reach consensus on core set of metrics for public benchmarking | bar: Year 1 10/1/13-9/30/2014 Q1; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 37 | Identify performance targets and measure performance against targets | [14 empty] | Group fails to reach consensus on core set of metrics for public benchmarking | This work depends on the data management tasks outlined under Objective 1 above | bar: Year 1 10/1/13-9/30/2014 Q2; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 38 | Assess any change in readmission rates; care management of high cost/high utilizing patients; e-visits; and pharmacy management. Consideration of findings of the Healthcare Cost Workgroups (including BH cost group) and implications for ACO arrangements in Maine. | [15 empty] | This work depends on the data management tasks outlined under Objective 1 above | bar: Year 1 10/1/13-9/30/2014 Q3 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 39 | Identify additional metrics to be used for learning and contracting purposes, as opposed to public reporting and benchmarking.; these metrics may be used to inform and measure risk contracting arrangements with regard to both quality and cost. Track metrics over time. | [14 empty] | Group fails to reach consensus on set of metrics to be used for learning collaborative purposes | bar: Year 1 10/1/13-9/30/2014 Q2; Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q3
[6 empty] | MHMC 40 | Document progress toward alignment demonstrated by systems and practice-based initiatives through biannual reports vetted through the ACI Workgroup. | [15 empty] | 14-18 | bar: Year 1 10/1/13-9/30/2014 Q3; Year 2 10/1/14-9/30/15 Q1 to Year 3 10/1/15-9/30/16 Q1; Year 3 10/1/15-9/30/16 Q3
Sub objective 3.5: Behavioral Health PTE | [5 empty] | MHMC 41 | Outreach to potentially interested persons regarding participation in new PTE BH Workgroup | This work would not occur in the absence of SIM | bar: Planning Period 7/1/13-9/30/13 2013-10-01; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 42 | Identify behavioral health clinical consultant; on board BH PTE staff | bar: Year 1 10/1/13-9/30/2014 Q1; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 43 | Convene PTE BH Workgroup. At initial meeting provide orientation to PTE process, establish ground rules that will guide the work of the group. | [14 empty] | A critical mass of interested parties fails to be identified | 20, 21 | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 2 10/1/14-9/30/15 Q4; Year 3 10/1/15-9/30/16 Q2; Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 44 | Identification of Viable Performance Measures - candidate measures proposed by Committee members, staff | [14 empty] | Group fails to reach consensus | 22 | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 1 10/1/13-9/30/2014 Q2; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 45 | Candidate measures assessed against specification review criteria (importance, scientific acceptability, usability, feasibility, addresses gaps in performance) | [14 empty] | Identified metrics prove inappropriate due to lack of availability of valid data | 22 | bar: Year 1 10/1/13-9/30/2014 Q2 to Year 1 10/1/13-9/30/2014 Q3; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 46 | Clinical review of candidate measures that satisfy specification review criteria | [15 empty] | 22 | bar: Year 1 10/1/13-9/30/2014 Q2 to Year 1 10/1/13-9/30/2014 Q3; Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 47 | Surviving candidate measures to PTE Committee for value assignment (identify breakpoints for assignment of good/better/best ratings) | [14 empty] | Identified metrics prove inappropriate due to lack of availability of valid data | 24, 25 | bar: Year 1 10/1/13-9/30/2014 Q3 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 48 | Surviving candidate measures adopted by PTE BH workgroup and Board for review; ensures purchaser buy in | [14 empty] | Full group/board fail to adopt | 26 | bar: Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 49 | Approved metrics incorporated into rankings and published | [15 empty] | 26 | bar: Year 2 10/1/14-9/30/15 Q1 to Year 2 10/1/14-9/30/15 Q4
[6 empty] | MHMC 50 | Update measures/rankings as appropriate | [14 empty] | Data must be received from payers in timely manner | 28 | bar: Year 2 10/1/14-9/30/15 Q1 to Year 3 10/1/15-9/30/16 Q1
Sub objective 3.6: Reporting on Patient Experience of Care | [5 empty] | MHMC 51 | MHMCF obtains survey data from CMS-CG-CAHPS re: overall patient experience of care; data analyzed by Onpoint | SIM is funding the reporting work associated with patient experience of care surveying. | [13 empty] | Data must be received from vendors in a timely manner | bar: Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MHMC 52 | CG-CAHPS data incorporated into existing reporting database | [14 empty] | Data must be received from vendors in a timely manner | 30 | bar: Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MHMC 53 | Develop methods for updating CG-CAHPs for practices alternative the annual cycle of updates. | [14 empty] | Data set must contain valid observations to allow reporting | 31 | bar: Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MHMC 54 | Develop reporting processes for CG-CAHPs | [14 empty] | Data set must contain valid observations to allow reporting | 32 | bar: Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MHMC 55 | Develop plan to continue CG-CAHPS survey past the first year. | [14 empty] | Viability of plan will need to consider available resources; no budget for this activity. Continued MQF funding required. | bar: Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MHMC91 | Obtain initial clinical data feed; FTP directly to HDMS, implement and QC clinical data | bar: Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC92 | Clinical data first included in production data and available for reporting. | bar: Year 1 10/1/13-9/30/2014 Q4
[6 empty] | MHMC93 | Measure development, testing, and implementation using clinically enhanced claims data. | bar: Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q1
[6 empty] | MHMC94 | Submit application to HIN to request access to the clinical data. | bar: Year 2 10/1/14-9/30/15 Q1
[6 empty] | MHMC95 | Application approval and execution of any necessary DUAs. | bar: Year 2 10/1/14-9/30/15 Q1
[6 empty] | MHMC96 | Enhance reports to include measures derived from clinically enhanced claims data. | bar: Year 2 10/1/14-9/30/15 Q2
[6 empty] | MHMC97 | Update clinical data on a continuing basis; data feeds will be received monthly, but processing to occur on a quarterly basis. | bar: Year 2 10/1/14-9/30/15 Q3 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC98 | Participate in MaineCare Accountable Community measurement methodology discussions | bar: Year 1 10/1/13-9/30/2014 Q3
Objective 3: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target: Convene ACI group and discuss relationship of ACI Workgroup to SIM project, SIM governance subcommittee and PTE Systems. Set ground rules that will guide the consensus process the group will work with. Identification of interested parties who wish to participate in new PTE BH Workgroup; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Group will come into Testing Phase ready to work, having established ground rules Identified candidates for PTE BH workgroup Year 1 Target: Identification of core metrics for reporting, vetted and approved through PTE and Board. Publish initial benchmarked rankings Percent of Maine residents covered by alternative payment arrangement grows to 219,982 or 17% Identification of core metric set for Behavioral Health (integration and quality) Identification of core metrics for Adv Primary Care Recognition; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Learning collaborative tracking metrics identified not only for public reporting, but a separate set of metrics identified for use in learning. Number of Maine residents covered by an alternative payment arrangement grows to almost 462k, or 35.5% of population Finalization of metrics for BH; publish first set of metrics All metrics updated as appropriate; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Percent of Maine residents covered by alternative payment arrangements grows to 789,936 or 61%This puts on a trajectory to reach 80% coverage at the end of 5 years from start of test year. All metrics updated as appropriate
Objective 3: Annual Cost (Aligns with annual budget total's submitted with contract) | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: 25084; Year 1 10/1/13-9/30/2014 Q1: 1224396; Year 2 10/1/14-9/30/15 Q1: 1071942; Year 3 10/1/15-9/30/16 Q1: 1031855
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Health Information to manage care, plan provider and patient-level interventions |  | ü |  | Objective 4: Provide Primary Care providers access to claims data for their patient panels (portals)
[6 empty] | MHMC 56 | Identify primary care practices desiring claims portals. Prioritize implementation roll out with those practices participating in ACO arrangements having highest priority. | Provider portals are currently available to practices that are part of organizations that are members of MHMC. Expansion to non-member practices occurs as a function of the SIM grant. | [13 empty] | Practices fail to sign up for portal access | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 57 | Refine mechanics of portal | This work is occurring regardless of SIM | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 58 | Data analysis required to produce practice reports | The analytics associated with expanded access to provider portals would not be undertaken in the absence of SIM | [13 empty] | Data must be received from payers in timely manner | 1, 2 | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 59 | Roll out portal starting with highest priority practices | Provider portals are currently available to practices that are part of organizations that are members of MHMC. Expansion to non-member practices occurs as a function of the SIM grant. | [14 empty] | 3 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 4: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Build out portal; Year 1 10/1/13-9/30/2014 Q1: Year 1 Target: Complete design of portal and required analytics; data for MaineCare, Medicare and commercial populations will first be segregated with separate access due to challenges associated with the fundamental differences between the populations and the different risk profiles of the populations. Adoption by providers is voluntary, but it is estimated that 50 practices will adopt the portals in the first year.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Deliver portal functionality to all requesting providers. Estimated additional uptake: est. 20%, bearing in mind that adoption is voluntary; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Deliver portal functionality to all requesting providers. Estimated additional uptake: est. 20%, bearing in mind that adoption is voluntary
Objective 4: Annual Cost (Aligns with annual budget total's submitted with contract) | [9 empty] | 409007 | 578684 | 578684 | 630858 | 337600 | 578684 | 630858 | 578684 | 338713 | 630858 | 578684 | 578684
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Health Information to manage care, plan provider and patient-level interventions |  | ü |  | Objective 5: Provide practice reports reflecting practice performance on outcomes measures
[6 empty] | MHMC 60 | Extend offer of provider specific reports on risk adjusted cost and use metrics for benchmarking against peers by service category and clinical condition to all interested PCPs | Practice reports have been developed for practices in organizations that are participating in the primary care medical home pilot. SIM is enabling all other interested primary care practices to also receive practice reports | [13 empty] | Practices decide not to sign up to receive practice reports | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 61 | Data analysis required for new practice reports | [15 empty] | 1 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 62 | Roll out practice reports | [15 empty] | 2 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 2 10/1/14-9/30/15 Q2; Year 2 10/1/14-9/30/15 Q4 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 63 | Outreach to practices (working in conjunction with Quality Counts) to assist practices in gaining proficiency in reading and understanding reports and how to use the information they contain | [15 empty] | 3 | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
Objective 5 Accountability Targets: | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target Continue production of practice reports for currently enrolled practices; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Year 1 Target: Produce practice reports for all primary care practices indicating their interest in receiving them. While we will be able to produce reports for any primary care practice that serve a critical mass of patients, practices themselves must make the decision to actively request, review and use the reports. PCMH practices represent approximately 25% of primary care practices; all receive the reports. We estimated 10% of non-PCMH practices will choose to receive reports in Year One. Each new practice will receive an outreach visit.; Year 2 10/1/14-9/30/15 Q1: Year 2 Target: Produce practice reports for all primary care practices indicating their interest in receiving them. We estimate that there will be an incremental increase of 10% in take up of reports in Year Two. Each new practice will receive an outreach visit.; Year 3 10/1/15-9/30/16 Q1: Year 3 Target: Produce practice reports for all primary care practices indicating their interest in receiving them. Estimated new uptake is 15%, bringing "coverage" with practice reports to approx. 50% of PC practices. Each new practice will receive an outreach visit.
Objective 5: Annual Cost | [9 empty] | 457385 | 737054 | 737054 | 818857 | 406718 | 737054 | 818857 | 737054 | 408061 | 818857 | 737054 | 737054
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Health information for consumers | ü |  |  | Objective 6: Consumer engagement and education regarding payment and system delivery reform
[6 empty] | MHMC 64 | Develop and implement media campaign around benefits of value based insurance design as well as broader topic of payment reform | SIM provides critical support to the educational and consumer engagement campaign; resources to undertake such a campaign are not otherwise available. | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 65 | Develop a VBID curriculum eligible for continuing end credits for brokers and HR specialists | bar: Planning Period 7/1/13-9/30/13 2013-10-01 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 66 | Provide free training for advocates, AAA advisors, navigators, free care providers, brokers and HR specialists regarding benefits of VBID and other forms of payment reform | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 67 | Develop a video for payers and purchasers (including MaineCare) to use that explains how VBID plans work. | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 1 10/1/13-9/30/2014 Q4; Year 3 10/1/15-9/30/16 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 68 | Provide training for payers' staff members, MaineCare employees regarding characteristics and merits of VBID and other forms of payment reform | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 69 | Develop and make available a VBID implementation tool kit | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 2 10/1/14-9/30/15 Q1; Year 3 10/1/15-9/30/16 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 70 | Provide CME credits and curriculum around VBID for providers | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 1 10/1/13-9/30/2014 Q4; Year 2 10/1/14-9/30/15 Q2 to Year 3 10/1/15-9/30/16 Q4
Objective 6: Accountability Targets | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: Year 1 Target: Educate brokers, patient advocates, HR Specialists, union leaders on merits of VBID. Outreach to 200 people.; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Continue education and outreach efforts, reaching for all major payer organizations and MaineCare. Reach an additional 200 individuals.; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Continued outreach and education; reaching an additional 200 providers and individuals
Objective 6: Annual Cost (Aligns with annual budget total's submitted with contract) | [9 empty] | 102734 | 78125 | 78125 | 83125 | 94271 | 78125 | 83125 | 78125 | 94484 | 83125 | 78125 | 78125
Secondary Driver | Subcommittee |  |  | Key Objective | Associated DRR Section | ID# | Key Milestones | How is SIM enabling this objective/activity to occur? | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period 7/1/13-9/30/13; Year 1 10/1/13-9/30/2014 Q1: Year 1 10/1/13-9/30/2014; Year 2 10/1/14-9/30/15 Q1: Year 2 10/1/14-9/30/15; Year 3 10/1/15-9/30/16 Q1: Year 3 10/1/15-9/30/16 | Known Risks | Dependency and Link to ID#
| PR | DSR | DI | [5 empty] | 2013-10-01 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 |  |  | ID#
Data informed policy, practice and payment decisions/Aligned Payment Models/Multi-Stakeholder Coalition Building and Support |  | ü |  | Objective 7: Ensure effective management of SIM Payment Reform Subcommittee to promote sustainability of reform developed through SIM
[5 empty] | A, T | MHMC 71 | Identify and finalize Subcommittee membership | A. This objective/activity would not occur without SIM funding | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 72 | Convene Subcommittee | A. This objective/activity would not occur without SIM funding | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC 73 | Ensure participation and process according to established protocols | A. This objective/activity would not occur without SIM funding | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC74 | Develop a SIM communications Plan | bar: Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MHMC75 | Create and Maintain Listserv for general SIM correspondence | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC76 | Develop web portal for centralized communications ( Rackspace) | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 1 10/1/13-9/30/2014 Q2
[6 empty] | MHMC77 | Schedule/ host quarterly webinars | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC78 | Produce and disseminate monthly email update to list serve | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC79 | Develop and Disseminate Project Managers Report | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC80 | Develop and implement website enhancements | bar: Year 1 10/1/13-9/30/2014 Q1
[6 empty] | MHMC81 | Update and maintain SIM website | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 3 10/1/15-9/30/16 Q4
[6 empty] | MHMC82 | Develop/implement public information/relation strategy | bar: Year 1 10/1/13-9/30/2014 Q1; Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC83 | Create branding materials (slide decks, logos, descriptions) | bar: Year 1 10/1/13-9/30/2014 Q1 to Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC84 | Create SIM Overview flier | bar: Year 1 10/1/13-9/30/2014 Q1; Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC85 | Create and disseminate SIM Fact sheet specifically for the legislature | bar: Year 1 10/1/13-9/30/2014 Q1; Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC86 | Create and disseminate SIM Fact sheet specifically for employers | bar: Year 1 10/1/13-9/30/2014 Q1; Year 1 10/1/13-9/30/2014 Q3
[6 empty] | MHMC87 | Create and disseminate SIM Fact sheet specifically for consumers | bar: Year 1 10/1/13-9/30/2014 Q1; Year 1 10/1/13-9/30/2014 Q4
[6 empty] | MHMC88 | Create and disseminate SIM Fact sheet specifically for providers | bar: Year 1 10/1/13-9/30/2014 Q1; Year 1 10/1/13-9/30/2014 Q4
[6 empty] | MHMC89 | Craft and disseminate media pitches, focused on SIM data and results | bar: Year 1 10/1/13-9/30/2014 Q1; Year 1 10/1/13-9/30/2014 Q4 to Year 2 10/1/14-9/30/15 Q1; Year 2 10/1/14-9/30/15 Q3; Year 3 10/1/15-9/30/16 Q1; Year 3 10/1/15-9/30/16 Q3
Objective 7 Accountability Targets: | [8 empty] | Planning Period 7/1/13-9/30/13 2013-10-01: Planning Period Target: establish infrastructure, membership for Payment Reform Subcommittee; Year 1 10/1/13-9/30/2014 Q1: Go Live Target: identify membership for Payment Reform Subcommittee Year 1 Target: Provide support for Subcommittee in manner that supports active participation of membership; Year 2 10/1/14-9/30/15 Q1: Year 2 Targets: Provide support for Subcommittee in manner that supports active participation of membership; Year 3 10/1/15-9/30/16 Q1: Year 3 Targets: Provide support for Subcommittee in manner that supports active participation of membership
Objective 7: Annual Cost | [8 empty] | Year 1 10/1/13-9/30/2014 Q1: 4800; Year 2 10/1/14-9/30/15 Q1: 4800; Year 3 10/1/15-9/30/16 Q1: 4800
Commitments from HIN/MHMC during Plan Synchronization: • Insuring a synergistic and integrative approach to the work of PTE- BH and the HIN BH RFP Quality work. • Clearly outlining and communicating the process for a collaboration between HIN, health care provider(s) (Covered Entity(is)) and MHMC in integrating clinical and administrative claims data for a possible proof of concept.
Note on BC2: Chenard, Randal: Include dependencies on tasks inside AND outside your organization. Any dependencies should include Notes for greater explanation
Note on A3: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B3: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E3: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F3: If available
Note on G3: Numbering convention important to tie dependencies together in column X
Note on H3: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I3: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A32: Targets must be quantifiable. Examples: - # of providers reached - # of patients touched - # of reports developed - # of programs developed etc.
Note on A34: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B34: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E34: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F34: If available
Note on G34: Numbering convention important to tie dependencies together in column X
Note on H34: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I34: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A52: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B52: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E52: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F52: If available
Note on G52: Numbering convention important to tie dependencies together in column X
Note on H52: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I52: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A99: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B99: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E99: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F99: If available
Note on G99: Numbering convention important to tie dependencies together in column X
Note on H99: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I99: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A108: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B108: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E108: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F108: If available
Note on G108: Numbering convention important to tie dependencies together in column X
Note on H108: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I108: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on A117: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B117: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E117: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F117: If available
Note on G117: Numbering convention important to tie dependencies together in column X
Note on H117: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I117: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding
Note on I120: Ellen Schneiter:
Note on A129: Refer to Driver Diagrams. Could be aligned to multiple secondary drivers
Note on B129: PR: Payment Reform DSR: Delivery System Reform DI: Data Infrastructure
Note on E129: Objectives should represent the high level goals of each partner. These can be represented by activities as outlined in the driver diagrams, or represented on a different basis. Importance here is that all of the objectives together cover the totality of the work that will be executed with SIM funding
Note on F129: If available
Note on G129: Numbering convention important to tie dependencies together in column X
Note on H129: Milestones are the key activities that support the overall objective and include timeframes as to when those activities will occur
Note on I129: Potential input: -A. This objective/activity would not occur without SIM funding B. This objective/activity is significantly enhanced by SIM funding

## Denominator Footnotes
Number and Explain each denominator:
Organization | Objective | Number | Explanation
HIN | 1 | 1 | Currently there an average of 1,600 active provider organization users of the HIE portal, tracked by HIN. The goal is increase the number of active users per target numbers as the expansion of these services to care managers grows. It is not possible to know the number of clinical support staff (care managers in this case) that support the "Clinician providers" (MD/DO/APRN/PA), thus there is no denominator for this population, thus tracking HIE active use is the selected target.
HIN | 1 | 2 | Currently there is an average of 450 unique provider users of the HIE or notifications on a weekly basis, tracked by HIN. We aim to increase the number of unique provider users weekly, as a measure of success of implementing notifications with users.
HIN | 2 | 3 | In Maine there are approximately 65 independent Behavioral Health Organizations. By reaching 20 organizations we will be impacting approximately 30% of this provider community. Because the RFP awardees are not known until the RFP process is vetted, the applicants confirmed, and awardees announced, the number of unique provider organization users cannot be articulated at this time. Once the 20 organizations are identified, HIN could establish more specific targets related to these organizations. The target for objective 2 is to acheive the RFP annual milestones and distribute the incentives each year.
HIN | 4 | 4 | Make 230,000+ mainecare member population data available in HIN Dashboard: which includes geographic distribution, gender distribution, age distribution, chronic disease prevalence and distribution, utilization statistics, and prospective risk for use of the emergency department. MaineCare estimates as of 8.2013 that there are 280,988 MaineCare members, thus the target of 230,000 allows for a margin of error and considers that less than 100% of MaineCare members are participants in the HIE. It is not known what the exact % of MaineCare members that are participants in the HIE today.
HIN | 5 | 5 | The goal is to engage 5% of the PHR user's for the pilot site in the go-live period of the 12 month pilot by measuring that they have accessed their CCD via the "Blue Button" technology that links the PHR to the HIE patient record summary (CCD). Once the pilot site is selected we can determine what the total number of PHR users targeted.
MaineCare | 3 | 6 | Will be RFPd - contained as MaineCare as a placeholder for now
MaineCare | 4 | 7 | Will be RFPd - contained as MaineCare as a placeholder for now
Maine CDC |  | 8 | CHW Referrals: CHW Pilot sites will be located in different areas in Maine.The number of providers making referrals to the CHW program will likely vary with location type - more in urban and fewer in rural areas. This Pilot Project will explore different models of to determine what works best in the different location types.
Maine CDC |  | 9 | CHW clients: the projections are for number of clients carried at any point in time. We cannot accurately project the turnover rate in a CHW's caseload to identify an annual total of clients seen.
MHMC |  | 10 | Estimated providers: 450-500