Subcommittee: Evaluation

Date: February 25, 2015

Time: 3:00 to 5:00 pm

35 Anthony Avenue, Augusta, ME  04333

Co-Chairs: Amy Wagner (DHHS/OCQI); Kathy Woods (Lewin)

Core Member Attendance:  Angela Cole Westhoff (Maine Osteopathic Association), Poppy Arford (Consumer), Sadel Davis (UPC of ME), Peter Kraut (DHHS/MaineCare), Jim Leonard (DHHS/MaineCare), Lisa Letourneau (QC), Andrew MacLean (ME Medical Association), Katherine Pelletreau ( ME Assoc. of Health Plans), Kitty Purington (DHHS/MaineCare), Debra Wigand (Maine CDC), Jay Yoe (DHHS/OCQI), Andrew MacLean (Maine Medical Association), Peter Flotten (MeHMC), Shaun Alfreds (Health Infonet), Cindy Seekins (Parent of Consumer)

Interested Parties & Guests:  Beth Austin (Crescendo Consulting), Randy Chenard (ME SIM), David Hanig (Lewin), Jessica Newman (Lewin), Andy Paradis (Lewin), Jade Christie-Maples (Lewin), Scott Good (Crescendo Consulting), Brian Robertson (Market Decisions), Gi Kim (Lewin)

Unable to attend: Simonne Maline (Consumer), Sheryl Peavey (DHHS/Commissioner’s Office)

| Topics | Lead | Notes | Actions/Decisions |
| --- | --- | --- | --- |
| - Welcome & Introductions, Goals of meeting | Wagner | - Review and approve previous meeting minutes, as well as subcommittee charter. - Crescendo Consulting & Market Decisions will be conducting provider and consumer interviews (respectively) as part of the self-evaluation process - Meeting focus: Obtain Committee feedback regarding provider and stakeholder portions of the evaluation | N/A |
| - Review & Approve Dec. 10th and Feb. 11th Meeting Minutes | Wagner | - Minutes were circulated prior to the Feb. 25th meeting for review by subcommittee members. Minutes were approved unanimously without changes to draft. | - December 10, 2014 and February 11, 2015 Minutes approved. |
| - Review & Approve SIM Evaluation Subcommittee Charter | Woods | - Charter was circulated prior to the Feb. 25th meeting for review by members. - No comments or clarifications were suggested. - Charter was approved unanimously. | - Charter approved. |
| - Provider Interview Tool | Woods Hanig Crescendo | - Detailed review of the provider and key stakeholder tools, timeline, targeted cohorts, and communication plan was presented; - Interviews will be conducted by phone or in person, and will be designed to consider other surveys currently being conducted by different vendors across these provider groups. - Feedback from February 11th committee meeting has been incorporated into the latest iteration of the tools. Those changes: - Enhance clarity to provider portal related questions - Enhance questions related to support from partner organizations - Realign payment model questions to target practice managers and leads, as well as administrators, and to differentiate between commercial and MaineCare Models - Target outreach towards HH practice leads - Target questions related to CHW and NDPP for providers participating directly in these initiatives but not entire cohort. - February 25 meeting feedback: - Discussion of whether Accountable Communities should be included as part of the interview questions at this time, given their current state of implementation. - Questions regarding topics that require further clarity to ensure provider understanding and relevant feedback – e.g. “Are you using practice reports? Are you using the data regarding inpatient transfers? How much are you using? What’s valuable?” - Questions about Learning Collaboratives, should specify which collaborative is to be reviewed (HH or BHH), instead of Learning Collaboratives generally. - Key stakeholder interview & potential time constraints for participants- suggestion that 10 vs. 30 minutes may be more viable to engage this cohort in interview participation. - The timeline for provider and stakeholder interviews is projected to be: - Tool Finalization – Early March - Cohort Communications - Interviews begin within next 1-2 months | - Committee feedback will be incorporated into final iteration of provider interview tool (feedback due by 3/2); - Committee feedback will be incorporated into next iteration of key stakeholder interview tool (feedback due by 3/2); - DHHS to have further discussion regarding inclusion of Accountable Community related questions |
| - Consumer interview tool | Woods Hanig Market Decisions | - Detailed review of the consumer stakeholder tools timeline, and communication plan was presented; - Two tools are being developed by Market Decisions to target: - Stage A HH, Accountable Community, and Control Group consumers which will utilize the CAHPS survey with the Patient Centered Medical Home supplemental survey - Stage B BHH consumers which will utilize the 2013 MaineCare Adult/Youth & Family Survey - The tools will be supplemented by additional questions that focus on SIM research questions and hypotheses. - Market Decisions will use telephone outreach to conduct interviews with the aim of completing within approximately 15 minutes. - Selected questions will target a series of priority domains identified by the state: - Consumer engagement in treatment planning, decision-making - Communication effectiveness - Physical / Behavioral Health Integration - Care Coordination - Behavioral Health Recovery Goals & Community Supports - Discussion on the inclusion of Accountable Community or Health Home terms; group consensus to not include so that the interview focuses on the patient’s experience of care. - Behavioral Health tool- clarity suggested for definition of “service providers” per interview question; Market Decisions will incorporate into training for the staff who will implement these interviews. - Market Decisions will reinforce with consumers that multiple efforts are currently taking place in the state, but focus of questions vary, so their participation is encouraged. - Lewin will coordinate with other vendors currently implementing surveys in the state to avoid as much duplication as possible. | - Committee feedback will be incorporated into next iteration of consumer interview tool (feedback due by 3/5) |
| - Next Steps | Wagner | Members will provide additional feedback on provider and stakeholder tools with the following deadlines: - Provider and stakeholder tool feedback due Monday 3/2. - Consumer tool feedback due 3/5. The March 25th meeting agenda will include: - Evaluation Plan review, Risk management process, Update on provider & consumer interview process | - Meeting materials to be posted to ME SIM website at: http://maine.gov/dhhs/sim/committees/evaluation.shtml |

Next Meeting:  Wednesday, March 25, 2015

Conference Room A, 35 Anthony Avenue, Augusta, Maine     Please NOTE- this is a FRAGRANCE FREE building

| Workgroup Risks Tracking |  |  |  |  |
| --- | --- | --- | --- | --- |
| Date | Risk Definition | Mitigation Options | Pros/Cons | Assigned To |

| Dependencies Tracking |  |  |  |
| --- | --- | --- | --- |
| Payment Reform | Data Infrastructure | Delivery System Reform | Other |