## Sheet1
| Item # | Risk/Issue/Dependency Name | Impacted SIM Objectives (SST Obj #, eg.. MHMC #3, HIN #4, etc.) | IF…. | THEN… | Accountability Target Impacts (from SST) | Drivers Impacted | Item Owner (Project Manager Name) | Status (Open, In Progress, Resolved, Closed) | Creator (Originator) | Date Created and Date Closed | Updated by (name) | Date last updated | Weighted Priority (1= Low, 3= Med, 5 = High) | Probability 1-3 (1=Low, 2= Med 3=High) | Impact 1-3 (1=Low, 2= Med 3=High) | Priority Calc | Details | Plan to address (free form) | Associated Risks | Above (A) or Below (B) waterline for Risk Mitigation Planning | Risk Plan Complete
New Draft Version | 24 | Primary Care Payment reform | MHMC Obj 2- Stimulate Value Based Insurance Design. | If payment reform, including support from Medicare and commercial payers in addition to Medicaid fails to support enhanced primary care models (which includes the patient centered medical home, health homes and community care team) | Meaningful delivery system reform will be impeded and not be sustainable | MHMC Obj 2 | Dev New Payment Models and Dev New Workforce Models and Strengthen PC | Steering Committee | Open | Lisa Tuttle | 41695 | GAC | 42199 | 5 | 3 | 3 | 45 |  | Payment Reform SC will present findings and recommendations of Discern report to the DSR SC to solicit suggestions for a strategy to proceed to adopt Discern recommendations |  | A | No
Note on O2: Chenard, Randal: Weighted priority appropriately weights the risk based on the objectives that are potentially impacted by the risks. If higher priority objectives are impacted by the occurrence of the risk, then the risk would receive a higher Priority rating than if the risk may impact a less impactful objective. Refer to the Objective weight assignments for determination, which is located on the 'weighted objective' tab in the spreadsheet. For example, a risk that may impact, the blue button pilot (HIN objective 5), will not be weighted as heavily as a risk that may impact the MaineCare Accountable Community model development (MaineCare Objective #1)
Note on S2: Chenard, Randal: Free form, can capture additional descriptive info or any updates Chenard, Randal: