Draft workplan for Selection of Core Metrics for Maine SIM

|  |  |  |
| --- | --- | --- |
| Timeline | Core Activities | Activity Needed from ME SIM Team |
| Week of 11/11 | * Kick off meeting
 | * Identify key participants and their availability
* Participate in kickoff
 |
| Weeks 11/18 – 11/25 | * TA team to gather candidate metrics and map to ME DD based on criteria refined in kickoff, identify key gaps
* Develop agenda and hold second meeting to discuss draft mapping
 | * Assist TA team in identifying sources for candidate measures not included in ME’s OP
* Participate in second discussion to refine draft mapping of metrics to DD
 |
| Week of 12/2 | * TA team to provide revised mapping and write up of decisions points from second meeting back to Maine team
 | None |
| Week of 12/9 |  | * Circulate revised mapping of DD to core metrics to additional stakeholders for feedback
 |
| Week of 12/16 | * TA team to make additional revisions if needed based on feedback gathered in week 5
 | * Maine to vet final draft with steering committee
 |