## Sheet1
Timeline Tool to determine Dates for Withdrawal Agreements:
Important dates regarding timeline for Final vote on Withdrawal:
|  | Date of next Statewide General Election: | 2020-11-03 | (date for vote on withdrawal referendum)
|  | At least 10 days prior to general election: | 2020-10-24 | (deadline for municipality to hold public hearing on upcoming vote)
|  | At least 35 days prior to general election: | 2020-09-29 | (absolute deadline for written notice from DOE of date of vote - must have final (after public hearing) conditional approval on withdrawal agreement)
|  | At least 45 days prior to general election: | 2020-09-19 | (absolute deadline for written notice from DOE of date of vote - in order to be on the absentee ballot - per municipal law)
|  | Within 30 days after public hearing/at least two weeks prior to Deadline for Referendum Date by Commissioner: | 2020-09-05 | (Results of public hearing must be reported to Commissioner prior to final conditional approval or changes resulting from public hearing
|  | Date of initial public hearing for conditional agreement - latest date it can be held is 8/14/2020: | 2020-08-14 | (Initial public hearing to discuss merits of proposed withdrawal agreement)
|  | At least 10 days prior to public hearing: | 2020-08-04 | (RSU board must post a public notice in each municipality of the time and location of the public hearing)
|  | At least 20 days prior to public hearing: | 2020-07-25 | (DOE must notify municipality of conditional approval at least 20 days prior to public hearing date)
|  | Deadline for Submission of Signed Withdrawal Agreement to Commissioner: | 2020-06-30 | (This signficantly reduces the allowed time for review from 60 days to 30 days)
Note: only the dates highlighted in blue can be changed - other dates recalculate automatically based on those dates.