## Compiled_list
Bundle ID | Stream | Asset Name | MaineDOT Asset ID | MSHV | Town | Economic Disadvantage1 | Watershed | Latitude | Longitude | Existing Structure | Construction Year | DOT Condition | Fisheries | Habitat Type | Resource Agency Priority | Modeled BFW | 1.2 BFW | Proposed Structure | In MaineDOT Workplan | Notes | Location Link | Round Total Cost | Revised Bridge Cost | Scope | Likely Structure | Kickoff | PDR | PSE | ADV | Construction Begin | Construction Complete
Central Maine | Pattees Pond Outlet | Fish Bridge | 0509 | 16433 | Winslow | N | Kennebec River |  |  | culvert | 1921 | 4 | Herring | Migration | High | 33 | 39.6 |  | Y |  | https://mdotinetapps.state.me.us/map/?map=ezAzMjdCRjIxLTcwQzgtMTFFRC1BQjE4LUQwNjcyNkJBMUVDOH0= | 2500000 | 2500000 | Culvert Replacement | 58' NEXT Beam | 2019-05-02 | 2022-12-21 | 2023-10-11 | 2023-11-01 | 2024-03-07 | 2025-08-13
| Ben Brook 1 | John Erskine Bridge | 3639 | 3713 | Alna | N | Sheepscot River |  |  | culvert | 1938 | 5 | ATS | Mapped Upstream Spawning | High | 21.5 | 25.8 |  |  |  | https://mdotinetapps.state.me.us/map/?map=ezE2QzlGRERFLTcwQzgtMTFFRC1BNzU0LUQwNjcyNkJBMUVDOH0= | 1500000 | Pending | Culvert Replacement | Short Span Bridge | 2024-05-19 | 2025-05-05 | 2026-08-07 | 2026-08-28 | 2026-10-30 | 2027-11-01
| Ben Brook 2 | N/A | 0610 | 3747 | Alna | Alna | [17 empty] | Culvert Replacement
| Morton Brook (aka Nehumkeag Brook) | Nehumkeag Bridge | 5283 | 13169 | Pittston | N | Kennebec River |  |  | culvert | 1982 | 4 | Herring | Migration | High | 21.3 | 25.56 |  | Y |  | https://mdotinetapps.state.me.us/map/?map=ezI1ODlBMDYxLTcwQzgtMTFFRC05NTRCLUQwNjcyNkJBMUVDOH0= | 1500000 | 2200000 | Culvert Replacement | Short Span Bridge | 2022-05-19 | 2023-07-25 | 2024-09-04 | 2024-09-25 | 2024-11-27 | 2025-06-25
| Threemile Stream | N/A | N/A | 16194 | Vassalboro | [18 empty] | Culvert Replacement
| Castner Brook | N/A | N/A | 14145 | Damariscotta | [18 empty] | Culvert Replacement
| Chopps Creek | N/A | 5584 | 16139 | Woolwich | N | Kennebec River | 44.0032 | -69.8068 | culvert | 1956 | 6 | Smelt | Spawning | High | 14.8 | 17.76 |  |  |  | https://mdotinetapps.state.me.us/map/?map=ezM1MEU4RUIwLTcwQzgtMTFFRC05RDUyLUQwNjcyNkJBMUVDOH0= | 1500000 | 1500000 | Culvert Replacement | TBD | 2024-05-19 | 2025-05-05 | 2026-08-07 | 2026-08-28 | 2026-10-30 | 2027-11-01