## Downeast Bundle only
Bundle ID | Stream | Asset Name | MaineDOT Asset ID | MSHV | Town | Economic Disadvantage1 | Watershed | Latitude | Longitude | Existing Structure | Construction Year | DOT Condition | Fisheries | Habitat Type | Resource Agency Priority | Modeled BFW | 1.2 BFW | Proposed Structure | In MaineDOT Workplan | Notes | Location Link | Round Total Cost | Revised Bridge Cost | Scope | Likely Structure | Kickoff | PDR | PSE | Advertise | Construction Begin | Construction Complete
Downeast | Beaver Dam Stream | N/A | 2061 | 13302 | Wesley | N | Machias River |  |  | culvert | 1982 | 4 |  |  | High | 22 | 26.4 |  | Y | Actual BFW | https://mdotinetapps.state.me.us/map/?map=ezkxODk2NkNGLTcwQzYtMTFFRC05Qjk2LUQwNjcyNkJBMUVDOH0= | 2000000 | 3000000 | Bridge Culvert Replacement | Short Span Bridge | 2022-05-18 | 2023-05-23 | 2024-08-07 | 2024-08-28 | 2024-10-30 | 2025-12-24
| New Stream | N/A | 6289 | 50036 | Wesley | N | Machias River |  |  | culvert | 1997 | 4 |  |  | High | 16.5 | 19.8 |  | Y |  | https://mdotinetapps.state.me.us/map/?map=e0EzODk0MDMwLTcwQzYtMTFFRC04MjM3LUQwNjcyNkJBMUVDOH0= | 2000000 | 2000000 | Bridge Culvert Replacement | Box Culvert | 2023-05-18 | 2023-06-06 | 2024-08-21 | 2024-09-11 | 2024-11-13 | 2026-01-07
| Tributary to Denny's River | N/A | 943284 | None | Meddybemps | N | Denny's River | 45.038 | -67.356 | 54-inch culvert |  | Good |  |  | DMR | 8 | 9.6 |  |  |  | https://mdotinetapps.state.me.us/map/?map=e0I0QjkxRjVFLTcwQzYtMTFFRC04RDVELUQwNjcyNkJBMUVDOH0= | 1500000 |  | Large Culvert Replacement | Box Culvert | 2025-09-19 | 2026-05-05 | 2026-08-07 | 2027-08-28 | 2027-10-30 | 2028-11-01
| Joe Meadow Brook | N/A | 46436 | 50999 | Wesley | N | Machias River | 44.872 | -67.6164 | 48-inch culvert |  | Poor |  | Proximity |  | 12.6 | 15.12 |  |  |  | https://mdotinetapps.state.me.us/map/?map=e0MxMzZDMTIxLTcwQzYtMTFFRC1CNTIwLUQwNjcyNkJBMUVDOH0= | 1500000 |  | Large Culvert Replacement | Box Culvert | 2025-09-19 | 2026-05-05 | 2026-08-07 | 2027-08-28 | 2027-10-30 | 2028-11-01
| Unnamed Tributary to Pineo Brook | N/A | 925280 | 50496 | Wesley | N | Machias River | 44.8794 | -67.6211 | 36-inch culvert |  | Fair to Poor |  | Proximity |  | 8 | 9.6 |  |  |  | https://mdotinetapps.state.me.us/map/?map=e0MxMzZDMTIxLTcwQzYtMTFFRC1CNTIwLUQwNjcyNkJBMUVDOH0= | 1500000 |  | Large Culvert Replacement | Box Culvert | 2025-05-19 | 2026-05-05 | 2026-08-07 | 2027-08-28 | 2027-10-30 | 2028-11-01
| Whites Brook 1 | N/A | N/A | 1464 | Bucksport
| Whites Brook 2 | N/A | N/A | 1465 | Bucksport
| Honeymoon Stream 1 | N/A | 108598 | none | Day Block Twp | N | Machias River | 44.929 | -67.754 | 60-inch culvert |  | Good | ATS |  | DSF DMR | 7 | 12 |  |  |  | https://mdotinetapps.state.me.us/map/?map=e0RFODExMzcwLTcwQzYtMTFFRC05QjBGLUQwNjcyNkJBMUVDOH0= | 1500000 |  | Large Culvert Replacement | Box Culvert | 2025-05-19 | 2026-05-05 | 2026-08-07 | 2027-08-28 | 2027-10-30 | 2028-11-01
| Honeymoon Stream 2 | N/A | 108709 | 50814 | Day Block Twp | N | Machias River | 44.9238 | -67.7641 | 60-inch culvert |  | Good | ATS |  | DSF DMR | unk | 12 |  |  |  | https://mdotinetapps.state.me.us/map/?map=e0VCNUMxNzcwLTcwQzYtMTFFRC1BMTg2LUQwNjcyNkJBMUVDOH0= | 1500000 |  | Large Culvert Replacement | Box Culvert | 2025-05-19 | 2026-05-05 | 2026-08-07 | 2027-08-28 | 2027-10-30 | 2028-11-01