## Contact List
Contact List
Contact list 2026 |  | Contact number | Email
QA Engineer | Kevin Cummings | 592-0907 | Kevin.Cummings@maine.gov
Independent Assurance Manager | Tim Gouplille | 592 6417 | Tim.Goupille@maine.gov
Independent Assurance Bangor Central | Mark Austin | 446 4809 | Mark.A.Austin@maine.gov
Independent Assurance Bangor North | Ryan Vose | 215-9357 | Ryan.K.Vose@maine.gov
Independent Assurance South | Chris Lambert | 480-0027 | Christopher.Lambert@maine.gov
TIMs / MILEs | Bobby Dangeti | 885-7000 | Bobby.Dangeti@maine.gov
Pavement Quality Manager | Brian Luce | 446-0360 | Brian.Luce@maine.gov
Pavement Quality Engineer | Tim Kelley | 215-2043 | Timothy.A.Kelley@maine.gov
Assistant Asphalt Pavement Materials Engineer | William Kelly | 941 4538 | William.Kelly@maine.gov
Environmental Coordinators | Region 1 - Justin Sweitzer | 458-1651 | Justin.L.Sweitzer@maine.gov
| Region 2 - Hannah Johnson | 624-8200 | Hannah.Johnson@maine.gov
| Region 3 - Paulo Ribeiro | 562-4228 | Paulo.B.Ribeiro@maine.gov
| Region 4 - Samuel Butler | 816- 2405 | Samuel.Butler@maine.gov
| Region 5 - Cara Odonnell | 592-2463 | Cara.M.ODonnell@maine.gov
| Bridge, MM, and Statewide - Ryan Annis, Jamie Bray, Nick Koltai | (Ryan) 557-1058 (Jamie) 446-8724 (Nick) 557-3471 | Ryan.Annis@maine.gov Jamie.Bray@maine.gov Nicholas.Koltai@maine.gov
Environmental Hazardous Materials | Brad Tirone - Hazardous Materials | 592-2293 | Bradley.Tirone@maine.gov
Health and Safety Office | Eula DeRocle, Director, Health and Safety Program | 446-6527 | Eula.J.DeRocle@maine.gov
| Ferry & Traffic - Austin Chipman | 441-9315 | Austin.C.Chipman@maine.gov
| Region 1 - Tony Price |  | anthony.e.pricejr@maine.gov
| Region 2 - Nick St.Amand | 624 8200 | Nick.St.Amand@maine.gov
| Region 3 - Derrek Savage | 592-2216 | Derrek.W.Savage@maine.gov
| Region 4 - Deborah Sanborn | 213=3310 | Deborah.Sanborn@maine.gov
| Region 5 - James E Ball | 557-1236 | James.E.Ball@maine.gov
Title II ADA Coordinator | Theresa Savoy | 592-1562 | Theresa.Savoy@maine.gov
State Traffic Engineer | Steve Landry | 557-0347 | Stephen.Landry@maine.gov
Assistant State Traffic Engineer | Jeffery Pulver | 624 3305 | Jeffrey.Pulver@maine.gov
Work Zone Traffic Engineer | Curtis Thopmson | 592 4187 | Curtis.Thompson@maine.gov
Transportation Traffic System Manager | Brooke Glidden | 441-7541 | Brooke.Glidden@maine.gov
Traffic Engineering ( WIMs, Signals, lighting, electrician, dig safe, Etc.) | Alan Farrington | 441- 9081 | Alan.R.Farrington@maine.gov
| Brooke Glidden | 441 -7541 | Brooke.Glidden@maine.gov
Region Traffic Engineers | Region 1 - Randy Illian | 592-1848 | Randy.Illian@maine.gov
| Region 2 - Darryl Belz | 446 6849 | Darryl.Belz@maine.gov
| Region 3 - Tim Soucie | 441-5602 | Timothy.Soucie@maine.gov
| Region 4 - James Baines | 592-2243 | James.Baines@maine.gov
| Region 5 - Ray Demerchant | 592-6461 | Raymond.Demerchant@maine.gov
Fabrication Engineer | Jason Stetson | 215 8818 | Jason.B.Stetson@maine.gov
Assistant Fabrication Engineer | Taylor Clark, Paul Hamzvai, Sam Stillwell | Taylor 530-3632 Paul 436-2719 Sam 441-8639 | Taylor.Clark@maine.gov Paul.Hamzavi@maine.gov Sam.Stilwell@maine.gov
Coating Specialists | Jason Stetson & Taylor Clark, Bridge Program
Shop Drawing Submittals | Fabrication.MaineDOT@maine.gov |  | Fabrication.MaineDOT@maine.gov
Concrete Specialists | Taylor Clark, Bridge Program | 530-3632 | Taylor.Clark@maine.gov
Concrete Mix Design submittal / review | Concrete.MaineDOT@maine.gov |  | Concrete.MaineDOT@maine.gov
Bridge Geotechnical Engineer | Nathan Pukay, Bridge Program | 991-2854 | Nathan.P.Pukay@maine.gov
Civil Rights Office | Sherry Tompkins, Director | 624-3066 | Sherry.Tompkins@maine.gov
DBE, Title VI, Labor Compliance & OJT | Mary Bryant | 624-3056 | Mary.Bryant@maine.gov
OJT, Labor Compliance, Title VI & DBE | Jennifer Laliberte | 624-3036 | Jennifer.E.Laliberte@maine.gov
Documentation Manager / Sub Contracts / Close Out Documentation | Kevin Hanlon | 592-2139 | Kevin.W.Hanlon@maine.gov
Close Out Documentation | Brian Cooley | 592 2298 | Brian.Cooley@maine.gov
Close Out Documentation | Roxane Cleaves | 557-8920 | Roxane.Cleaves@maine.gov
Close Out Documentation & Sub Approvals | Tim Bishop | 624-3410 | Timothy.N.Bishop@maine.gov
Close Out Documentation/ Minimum Testing Requirements | Brian Burgess | 624-3472 | Brian.Burgess@maine.gov
Elations System Manager | William Turner | 624-3519 | William.Turner@maine.gov
Chief Surveyor | Guy Ladd | 624 3499 | Guy.Ladd@maine.gov
Construction Support Managers | Devin Anderson, Bridge Program | 446-0428 | Devin.Anderson@maine.gov
| Travis Hamel, Bridge Program | 215-7312 | Travis.W.Hamel@maine.gov
| Tom Stevens, Multimodal Program | 592 4508 | Thomas.Stevens@maine.gov
| Shawn Smith, Regional / Highway | 557-1663 | Shawn.Smith@maine.gov
NOTE:
The Resident is the conduit for all submittals from the Contractor.
The Resident shall notify the Contractor in writing, approving the plan after all reviewer's concerns
have been addressed in a revised final.

## Paving, Milling & Crack Seal
Paving, Milling & Crack Seal
Submittal Type | Review and Comment | Approval Authority
Quality Control Plan for Paving and Recycling, Boiler Plate | Asst Highway Program Manager, Pavement Quality Manager, Asphalt Pavement Engineer | Asst. Highway Program Manager
QA Engineer, Contrsuction Support Manager
Quality Control Plan for Paving and Recycling, Project Specific | Resident, Pavement Quality Manager, Asphalt Pavement Engineer, QA Engineer | Resident
Construction Support Manager
Special Provision 202 Removing Pavement Surface Quality Control Plan | Resident, Construction Support Manager, Pavement Quality Manager | Resident
Special Provision 424 Crack Seal Quality Control Plan | Resident, Construction Support Manager, Pavement Quality Manager | Resident

## Traffic Plans
TRAFFIC PLANS
Submittal Type | Review and Comment | Approval Authority
Traffic Control Plan | Resident, Safety Office Transportation System Manager, | Resident
Region Traffic Engineer, Construction Support Manager
Detour Plans | Resident, Safety Office Transportation System Manager, | Resident
Region Traffic Engineer, Construction Support Manager

## Fabrication
FABRICATION
Submittal Type | Revirew and Comment | Approval Authority
Standard Specification Section 202 | Resident, Sr. Design Project Manager, Design Engineer, Construction Support Manager | Resident
Removing Structures and Obstructions -
Bridge/Superstructure Demolition Plan as required on
Contract Plans
Standard Specification 501 | Resident, Geotechnical Engineer, Fabrication Engineer | Geotechnical Engineer
Foundation Piles - Quality Control Plan
Standard Specification 501 | Resident, Fabrication Engineer, Design Engineer | Fabrication Engineer, Geotechnical Engineer
Foundation Piles - Pile Splicer and Tip Product Data
Welder Certifications
Standard Specification Section 502 | Resident, Concrete Specialist, Construction Support Managers | Concrete Specialist
Structual Concrete - QC Plan for Concrete
Standard Specification Section 502 | Resident, Fabrication Engineer, Design Engineer | Resident
Structural Concrete- Precast Deck Panels - Deck and
Overhang Falsework - Design Comps & Working
Drawings, Bridge Drains, Shop Drawings, Fabrication
Notification
Standard Specification Section 502 | Resident, Design Engineer, Fabrication Engineer | Resident
Structural Concrete - Deck and Overhang Falsework
Design Comps & Working Drawings
Standard Specification Section 503 | Rsident, Design Engineer, Fabrication Engineer | Fabrication Engineer
Reinforcing Steel - Mechanical Couplers & Welding
of Reinforcing Steel
Standard Specification Section 504 | Resident, Design Engineer, Fabrication Engineer | Fabrication Engineer
Structural Steel - Shop Drawings, Fabrication Notification
Standard Specification Section 506 | Resident, Fabrication Engineer | Fabrication Engineer
Shop Applied Protective Coatings - QC Plan
Applicator Qualifications, Job Control Records
Special Provision Section 506 | Resident, Office of Safety and Compliance, Coatings Specialist, Environmental Coordinator | Resident, Coating Specialist
Field Applied Protective Coating - QC Plan
Job Control Records, Surface Preparation/Coating Plan
Containment Plan, Environmental Containment Plan
Standard Specification Section 507 | Resident, Design Engineer, Fabrication Engineer | Fabrication Engineer
Railings - Shop Drawings, Fabrication Notification
Standard Specification Section 509 | Resident, Design Engineer, Fabrication Engineer | Fabrication Engineer
Structural Plate Pipes, Pipe Arches, Arches and
Metal Box Culverts - Shop Drawings
Standard Specification Section 510 | Resident, Safety Office Transportation System Manager, Sr. Design Project Manager | Resident
Special Detours - Design Computations and Drawings | Region Traffic Engineer, Construction Support Manager
Standard Specification Section 511 | Resident, Design Engineer, Geotechnical Engineer, Construction Support Manager | Resident
Cofferdams - Working Drawings
Standard Specification Section 520 | Resident, Design Engineer, Fabrication Engineer, Construction Support Engineer | Fabrication Engineer
Expansion Devices - Shop Drawings, Fabrication
Notification
Standard Specification Section 521 | Resident, Design Engineer, Fabrication Engineer | Fabrication Engineer
Finger Expansion Devices - Shop Drawings
fabrication Notification
Standard Specification Section 522 | Resident, Design Engineer, Fabrication Engineer | Fabrication Engineer
Modular Expansion Devices - Shop Drawings
Fabrication Notification
Standard Specification Section 523 | Resident, Design Engineer, Fabrication Engineer | Fabrication Engineer
Bearings - Shop Drawings, Fabrication Notification
Standard Specification Section 524 | Resident, Contruction Support Manager, Design Engineer | Design Engineer
Temporary Structural Supports - Design Computations
and Working Drawings
Standard Specification Section 525 | Resident, Contruction Support Manager, Design Engineer | Resident
Granite Masonry - Setting Plan
Standard Specification Section 534 | Resident, Design Engineer, Fabrication Engineer, Construction Support Manager | Fabrication Engineer
Structural Precast Concrete - Shop Drawings,
Design Computations, Fabrication Notification
Standard Specification Section 535 | Resident, Design Engineer, Fabrication Engineer, Construction Support Manager | Fabrication Engineer
Precast, Prestressed Concrete Superstructure -
Shop Drawings, Fabrication Notification
Standard Specification Section 608 | Resident, Construction Support Manager, Concrete Specialist | Concrete Specialist
Sidewalks - Concrete Mix Design
Standard Specification Section 609 | Resident, Construction Support Manager, Concrete Specialist | Resident, Concrete Specialist
Curb - Shop Drawings, Fabrication Notification for
Precast Curb
Standard Specification Section 626 | Resident, Geotechnical Engineer, Design Engineer, Traffic Engineering, Fabrication Engineer | Resident
Foundations, Conduit and Junction Boxes for Highway | Concrete Specialist
Signing, Lighting and Signals (Precast/Cast-in-Place)
Shop Drawings, Design Computations, Fabrication
Notification, as applicable
Standard Specification Section 634 | Resident, Design Engineer, Traffic Engineering, Fabrication Engineer | Resident
Highway Lighting - Shop/Manufacturer Drawings
Design Computations, Fabrication Notification
Standard Specification Section 642 | Resident, Concrete Speicalist | Resident
Steps - Concrete Mix Design
Standard Specification Section 643 | Resident, Design Engineer, Traffic Engineering, Fabrication Engineer, Concrete Specialist | Resident
Traffic Signals - Shop Drawings, Design Computations
Fabrication Notification, Concrete Mix Design
Standard Specification Section 645 | Resident, Design Engineer, State Traffic Engineer, Fabrication Engineer, Concrete Specialist | Resident
Highway Signing - Shop Drawings, Design Computations
Fabrication Notification, Concrete Mix Design
Standard Specification Section 672 | Resident, Design Engineer, Geotechnical Engineer, Fabrication Engineer | Fabrication Engineer
Precast Concrete Block Gravity Wall - Shop Drawings
Design Computations, Fabrication Notification
Standard Specification Section 673 | Resident, Design Engineer, Geotechnical Engineer, Fabrication Engineer | Resident
Wet Cast Small Landscape Block Wall - Shop Drawings
Design Computations, Fabrication Notification
Standard Specification Section 674 | Resident, Design Engineer, Geotechnical Engineer, Fabrication Engineer | Fabrication Engineer, Geotechnical Engineer
Prefabricated Concrete Modular Gravity Wall -
Shop Drawings, Design Computations, Fabrication
Notification
Standard Specification Section 677 | Resident, Design Engineer, Geotechnical Engineer, Fabrication Engineer | Fabrication Engineer, Geotechnical Engineer
Mechanically Stabilized Earth Retaining Wall
Shop Drawings, Design Computations, Fabrication
Notification
Standard Specification Section 681 | Resident, Design Engineer, Geotechnical Engineer, Fabrication Engineer | Fabrication Engineer, Geotechnical Engineer
Precast Aggregate - Filled Concrete Block Gravity Wall
Shop Drawings, Design Computations, Fabrication
Notification
NOTE:
The Resident is the conduit for all submittals from the Contractor.
The Resident shall notify the Contractor in writing, approving the plan after all reviewer's concerns
have been addressed in a revised final.

## Other
OTHER
Submittal Type | Review and Comment | Approval Authority
Soil Erosion and Water Pollution Control | Resident, Environmental Coordinator, Sr. Design Project Manager, Construction Support Manager | Resident
Plan & Spill Prevention Plan
Blasting Plan | Resident, Geotechnical Engineer, Environmental Coordinator, Construction Support Manager | Resident
Health & Safety Plan | Office of Safety and Compliance, ENV, Construction Support Managers, Resident | Resident
Standard Specification Section 105 | Resident, Design Engineer, Sr. Design Project Manager, Construction Support, Chief Surveyor | Resident
General Scpoe of Work - Survey Work Plan
& Contractor 3D model