## Sheet1
MaineDOT 2024 Construction Advertisement Plan Last Revised: Jan 2, 2024
This is MaineDOT's bid advertisement plan for capital projects to be advertised during the calendar year.
In years in which major funding components of MaineDOT's capital program are being debated, partial plans or mid-year alterations may be required.
Such years could include odd numbered years during which state budgets and bonding levels are typically decided, and years in which federal transportation authorization bills are pending.
This Plan is to be distinguished from the Current Construction Advertisement Schedule, which is a separate dynamic document updated online each Monday.
The current schedule will reflect changes caused by such factors as cash flow, bid prices, local and public input, and design and permitting.
Work Type | Project ID | Planned Advertise Date | Project Title | Work Plan Description | Program Manager | Executive Comment | Estimate | Program Manager Phone
Bridge Construction | 021725.00 | 03/06/2024 | FREEPORT / YARMOUTH, ROUTE 1/COUSINS RIVER BRIDGE #2183 | Route 1/Cousins River Bridge (#2183) over Cousins River. Located on the Freeport-Yarmouth town line. | Wayne Frankhauser | - | $10,256,000 | 624-3490
Bridge Construction | 027098.00 | 04/15/2024 | LEVANT, LAKE BRIDGE (#3359) PERKINS BRIDGE #6133 | Lake Bridge (#3359) over Black Stream. Located 0.04 of a mile west of Pecal Lane. Perkins Bridge (#6133) over Black Stream. Located 0.10 of a mile west of Pecal Lane. | Wayne Frankhauser | - | $2,870,000 | 624-3490
Bridge Construction | 025631.08 | 07/03/2024 | PITTSFIELD, I95 SB/WEBB ROAD BRIDGE #1449 | I95 SB/Webb Road Bridge (#1449) over Webb Road. Located 1.11 miles south of Somerset Avenue. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $3,770,000 | 624-3490
Bridge Construction | 025631.06 | 07/03/2024 | PITTSFIELD, I95 SB/SOMERSET AVENUE BRIDGE #1447 | I95 SB/Somerset Avenue Bridge (#1447) over Somerset Avenue. Located 1.21 miles south of Route 152. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $4,370,000 | 624-3490
Bridge Construction | 025631.09 | 07/03/2024 | PITTSFIELD, I95 NB/WEBB ROAD BRIDGE #5984 | I95 NB/Webb Road Bridge (#5984) over Webb Road. Located 2.58 miles north of Snakeroot Road. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $3,770,000 | 624-3490
Bridge Construction | 025631.07 | 07/03/2024 | PITTSFIELD, I95 NB/SOMERSET AVENUE BRIDGE #5985 | I95 NB/Somerset Avenue Bridge (#5985) over Somerset Avenue. Located 1.11 miles north of Webb Road. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $4,370,000 | 624-3490
Bridge Construction | 025631.13 | 07/24/2024 | HAMPDEN, 202 NB/SOUADABSCOOK STREAM BRIDGE #6079 | 202 NB/Souadabscook Stream Bridge (#6079) over Souadabscook Stream. Located 0.33 of a mile north of Route 9. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $5,510,000 | 624-3490
Bridge Construction | 025631.12 | 07/24/2024 | HAMPDEN, 202 SB/SOUADABSCOOK STREAM BRIDGE #1524 | 202 SB/Souadabscook Stream Bridge (#1524) over Souadabscook Stream. Located 1.11 miles south of Somerset Avenue. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $5,510,000 | 624-3490
Bridge Construction | 025631.14 | 08/14/2024 | HOWLAND, ROUTE 155/I95 BRIDGE #6068 | Route 155/I95 Bridge (#6068) over Interstate 95. Located 0.26 of a mile east of Maxfield Road. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $5,660,000 | 624-3490
Bridge Construction | 025631.11 | 09/04/2024 | HAMPDEN, ROUTE 202 /MCRR BRIDGE #6080 | Route 202 /MCRR Bridge (#6080) over MCRR. Located 0.23 of a mile northeast of Carey Drive. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $4,505,000 | 624-3490
Bridge Construction | 025631.10 | 09/04/2024 | BANGOR, US 202/I-395 BRIDGE #6082 | US 202/I-395 Bridge (#6082) over Interstate 395. Located 0.18 of a mile north of Perry Road. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $7,675,000 | 624-3490
Bridge Construction | 027836.01 | 09/04/2024 | WINSLOW, FISH BRIDGE (#0509) | Fish Bridge (#0509) over Pattees Pond Outlet. Located 0.09 of a mile south of the Benton town line. FHWA Culvert Grant Recipient. | Wayne Frankhauser | - | $2,500,000 | 624-3490
Bridge Construction | 025095.01 | 10/09/2024 | CAMDEN BIKE/PED BRIDGE | Rawson Avenue Pedestrian Bridge over Megunticook River. Located 0.05 of a mile southwest of Washington Street. | Jeffrey Tweedie | - | $500,000 | 624-3420
Bridge Construction | 023515.00 | 10/16/2024 | MT. DESERT, BABSONS BRIDGE #5244 | Babsons Bridge (#5244) over Meadow Brook. Located 0.09 of a mile east of Route 102. | Wayne Frankhauser | - | $5,670,000 | 624-3490
Bridge Construction | 026095.00 | 10/23/2024 | BANGOR, KENDUSKEAG AVENUE/I-95 BRIDGE #5798 | Kenduskeag Avenue/I-95 Bridge (#5798) over Interstate 95. Located 0.19 of a mile north of Linden Street. | Wayne Frankhauser | - | $9,850,000 | 624-3490
Bridge Construction | 027176.00 | 10/23/2024 | BANGOR, INTERSTATE 95 BRIDGES #1427 AND 5800 | Interstate 95 Bridges (#1427, #5800) over Stillwater Avenue. Located 0.10 of a mile north of Interstate 95 southbound exit #186 on-ramp. | Wayne Frankhauser | - | $18,350,000 | 624-3490
Bridge Construction | 025299.00 | 10/30/2024 | ALBION, PUDDLE DOCK BRIDGE #3107 | Puddle Duck Bridge (#3107) over 15 Mile Stream. Located 0.11 of a mile north of Knights Road. | Wayne Frankhauser | - | $3,210,000 | 624-3490
Bridge Construction | 026168.00 | 11/20/2024 | WASHINGTON, FARRAR BRIDGE #3929 | Farrar Bridge (#3929) over Jackson Stream. Located 0.51 of a mile west of Vanner Road. | Wayne Frankhauser | - | $1,575,000 | 624-3490
Bridge Construction | 026238.00 | 11/25/2024 | BENEDICTA TWP, CASEY ROAD / I-95, #6165 | Casey Road/I-95 Bridge (#6165) over Interstate 95. Located 0.76 of a mile west of Aroostook Road. | Wayne Frankhauser | - | $6,515,000 | 624-3490
Bridge Construction | 026442.00 | 11/27/2024 | VASSALBORO, MEADOW BROOK BRIDGE #5856 | Meadow Brook Bridge (#5856) over Meadow Brook. Located 0.46 of a mile west of Bradley Lane. | Wayne Frankhauser | - | $1,700,000 | 624-3490
Bridge Construction | 022238.00 | 11/27/2024 | GORHAM, MITCHELL BRIDGE #0216 | Mitchell Bridge (#0216) over Nonesuch River. Located 0.04 of a mile northwest of the Scarborough town line. | Wayne Frankhauser | - | $1,510,000 | 624-3490
Bridge Construction | 023643.00 | 12/04/2024 | HOLLIS, SALMON FALLS BRIDGE #3708 | Salmon Falls Bridge (#3708) over Saco River. Located on the Hollis-Buxton town line. | Wayne Frankhauser | - | $8,700,000 | 624-3490
Bridge Construction | 025161.00 | 12/04/2024 | CUMBERLAND, TUTTLE ROAD / I295 BRIDGE #5801 | Tuttle Road / I-295 Bridge (#5801) over Interstate 295 and Route 1 and MCRR. Located 1.64 miles north of the Falmouth town line. | Wayne Frankhauser | - | $20,395,000 | 624-3490
Bridge Construction | 025453.00 | 12/04/2024 | FORT FAIRFIELD, PUDDLE DOCK BRIDGE #2691 | Puddle Dock Bridge (#2691) over Pattie Brook. Located 0.02 of a mile north of Dorsey Road. | Wayne Frankhauser | - | $4,100,000 | 624-3490
Bridge Construction | 025309.00 | 12/04/2024 | TURNER, TURNER CENTER BRIDGE #3886 | Turner Center Bridge (#3886) over the Nezinscot River. Located 0.07 of a mile west of Lower Street. | Wayne Frankhauser | - | $7,875,000 | 624-3490
Bridge Construction | 025449.00 | 12/04/2024 | NEWCASTLE, MEADOW BROOK BRIDGE #2535 | Meadow Brook Bridge (#2535) over Deer Meadow Brook. Located 4.09 miles west of Bunker Hill Road. | Wayne Frankhauser | - | $1,615,000 | 624-3490
Bridge Construction | 026192.00 | 12/11/2024 | NEW GLOUCESTER, ROYAL RIVER BRIDGE #2729 | Royal River Bridge (#2729) over Royal River. Located 0.04 of a mile south of the Auburn town line. | Wayne Frankhauser | - | $6,970,000 | 624-3490
Bridge Construction | 026574.00 | 12/11/2024 | BAR HARBOR, CROMWELL BROOK #3 BRIDGE #0452 | Cromwell Brook #3 Bridge (#0452) over Cromwell Brook. Located 0.03 of a mile north of White Spruce Road. | Wayne Frankhauser | - | $3,020,000 | 624-3490
Bridge Construction | 025991.00 | 12/11/2024 | OTISFIELD, COLLEGE SWAMP BR#3475 | College Swamp Bridge (#3475) over College Swamp. Located 0.415 of a mile north of Route 121. | Wayne Frankhauser | - | $1,500,000 | 624-3490
Bridge Construction | 026158.00 | 12/11/2024 | WHITEFIELD, JEWETT BRIDGE #5460 | Jewett Bridge (#5460) over Albee Stream. Located 0.24 of a mile west of Townhouse Road. | Wayne Frankhauser | - | $1,700,000 | 624-3490
Bridge Construction | 026226.00 | 12/11/2024 | KENNEBUNK, DAYS MILLS BRIDGE #2221 | Days Mill Bridge (#2221) over Kennebunk River. Located 0.02 of a mile north of Days Mills Road. | Wayne Frankhauser | - | $3,665,000 | 624-3490
Bridge Construction | 026105.00 | 12/18/2024 | CHARLOTTE, ROUND POND BRIDGE #3787 | Round Pond Bridge (#3787) over Round Pond Outlet. Located 1.10 miles northeast of Ayers Junction Road. | Wayne Frankhauser | - | $3,600,000 | 624-3490
Bridge Construction | 025105.00 | 12/18/2024 | WILTON, BRIDGES BRIDGE #2102 | Bridges Bridge (#2102) over Wilson Stream. Located 0.03 of a mile southeast of the Weld Road. | Wayne Frankhauser | - | $2,750,000 | 624-3490
Bridge Construction | 022382.00 | 12/18/2024 | YARMOUTH, ROUTE 1/ I-295 BRIDGE #5804 | Route 1/ I-295 Bridge (#5804) over Interstate 295. Located 0.04 of a mile north of Interstate 295 northbound Exit 15. | Wayne Frankhauser | - | $19,710,000 | 624-3490
Bridges Other | 022258.00 | 01/24/2024 | SOUTH PORTLAND, RAMP SP4 BRIDGE #1376 | Ramp SP4 Bridge (#1376) over northbound ramp of Interstate 295 to Route 1. Located off Exit 4 on Interstate 295 southbound. | Wayne Frankhauser | - | $6,750,000 | 624-3490
Bridges Other | 026884.00 | 02/28/2024 | VARIOUS I-295 BRIDGE JOINTS | Interstate 295 bridges. | Wayne Frankhauser | - | $1,980,000 | 624-3490
Bridges Other | 026462.00 | 03/06/2024 | YARMOUTH, INTERSTATE 295 BR# 1137 | I-295 NB/Cousins River Bridge (#1137) over Cousins River. Located on the Freeport-Yarmouth town line. | Wayne Frankhauser | - | $521,000 | 624-3490
Bridges Other | 027184.30 | 03/06/2024 | AUGUSTA, I-95 BOND BROOK BRIDGES #1466, #5787 | Interstate 95 Bridges (#1466, #5787). | Wayne Frankhauser | - | $875,000 | 624-3490
Bridges Other | 027778.00 | 03/20/2024 | PENOBSCOT NARROWS BRIDGE & OBSERVATORY - SAFETY FENCE PROJECT | Penobscot Narrows Bridge & Observatory (#6421) over the Penobscot River. Located on the Prospect-Verona town line. | Wayne Frankhauser | - | $1,200,000 | 624-3490
Bridges Other | 026904.00 | 03/20/2024 | PORTLAND, I295 SB / ST JOHNSTREET BRIDGE #6538 | I-295 SB/St John Street Bridge (#6538) over St. John Street. Located 0.25 of a mile east of Route 9. | Wayne Frankhauser | - | $450,000 | 624-3490
Bridges Other | 026906.00 | 03/20/2024 | HARPSWELL, EWING NARROWS BRIDGE #6217 | Ewing Narrows Bridge (#6217) over Ewing Narrows. Located 0.16 of a mile west of Salty Lane. | Wayne Frankhauser | - | $1,600,000 | 624-3490
Bridges Other | 023220.00 | 03/23/2024 | BENTON, I-95 SB/RIVER ROAD BRIDGE #1455 | I-95 SB/ River Road Bridge (#1455) over River Road. Located 0.53 of a mile east of the Fairfield town line. | Wayne Frankhauser | - | $350,000 | 624-3490
Bridges Other | 026438.00 | 03/27/2024 | NEW SHARON, FILLIBROWN BRIDGE #3842 | Fillibrown Bridge (#3842) over Fillibrown Brook. Located 0.42 of a mile southwest of Taylor Road. | Wayne Frankhauser | - | $200,000 | 624-3490
Bridges Other | 026436.00 | 03/27/2024 | CHAIN OF PONDS TWP., DEAD RIVER BRIDGE #3135 | Dead River Bridge (#3135) over North Branch Dead River. Located 0.02 of a mile north of Alder Stream Twp. town line. | Wayne Frankhauser | - | $200,000 | 624-3490
Bridges Other | 026077.00 | 03/27/2024 | REGION 5 BRIDGES | Interstate 95 Southbound and Northbound Region 5 Bridges. | Wayne Frankhauser | - | $1,650,000 | 624-3490
Bridges Other | 026472.00 | 03/27/2024 | YARMOUTH, COTTON MILL BRIDGE #3983 | Cotton Mill Bridge (#3983) over Royal River. Located 0.16 of a mile north of Main Street. | Wayne Frankhauser | - | $300,000 | 624-3490
Bridges Other | 026450.00 | 03/27/2024 | PORTLAND, ST. JOHN STREET BRIDGE #6297 | St. John Street Bridge (#6297) over St. John Street. Located 0.12 of a mile north of Park Avenue. | Wayne Frankhauser | - | $400,000 | 624-3490
Bridges Other | 026079.00 | 03/27/2024 | HOULTON, I95SB/MEDUXNEKEAG RIVER BRIDGE #6099 | I-95 SB / Meduxnekeag River Bridge (#6099) over Meduxnekeag River. Located 0.50 of a mile north of Foxcroft Road. | Wayne Frankhauser | - | $800,000 | 624-3490
Bridges Other | 026416.00 | 03/27/2024 | GILEAD, ANDROSCOGGIN RIVER BRIDGE #5084 | Androscoggin River Bridge (#5084) over the Androscoggin River. Located 0.32 of a mile north of Route 2. | Wayne Frankhauser | - | $1,000,000 | 624-3490
Bridges Other | 026414.00 | 03/27/2024 | BYRON, NEW COOS BRIDGE #5847 | New Coos Bridge (#5847) over the Swift River. Located 0.11 of a mile north of Byron Village Road. | Wayne Frankhauser | - | $300,000 | 624-3490
Bridges Other | 026178.00 | 03/27/2024 | FALMOUTH, I295 NB / PRESUMPSCOT RIVER BRIDGE #5828 | I-295 NB/Presumpscot River Bridge (#5828) over Presumpscot River. Located 0.98 of a mile north of Portland town line. | Wayne Frankhauser | - | $600,000 | 624-3490
Bridges Other | 023186.00 | 04/06/2024 | BENTON, INTERSTATE 95 NB/ RIVER ROAD BRIDGE #5993 | Interstate 95 NB/ River Road Bridge (#5993) over River Road. Located 0.75 of a mile east of Interstate 95 northbound Exit 133. | Wayne Frankhauser | - | $350,000 | 624-3490
Bridges Other | 027494.00 | 05/15/2024 | TOPSHAM, ROUTE 201/CATHANCE RIVER BRIDGE #6309 | Route 201/Cathance River Bridge (#6309) over Cathance River. Located 0.24 of a mile north of Meadow Road. | Wayne Frankhauser | - | $500,000 | 624-3490
Bridges Other | 026894.00 | 05/29/2024 | SACO-BIDDEFORD, NEW COUNTY ROAD BRIDGE #2603 | New County Road Bridge (#2603) over Saco River. Located on the Saco-Biddeford town line. | Wayne Frankhauser | - | $700,000 | 624-3490
Bridges Other | 027076.00 | 06/19/2024 | TAUNTON & RAYNHAM ACADEMY GRANT, WEST OUTLET BRIDGE #3113 | West Outlet Bridge (#3113) over the West Outlet Kennebec River. Located 0.20 of a mile south of the Transfer Station Road. | Wayne Frankhauser | - | $975,000 | 624-3490
Bridges Other | 027292.00 | 06/26/2024 | BATH, WINTER STREET BRIDGE #0998 | Winter Street Bridge (#0998) over SMO Railroad. Located 0.09 of a mile west of Willow Street. | Wayne Frankhauser | - | $100,000 | 624-3490
Bridges Other | 027074.00 | 06/26/2024 | BANGOR, BULLS EYE BRIDGE #3301 | Bulls Eye Bridge (#3301) over the Kenduskeag Stream. Located 0.15 of a mile northeast of Ohio Street. | Wayne Frankhauser | - | $1,300,000 | 624-3490
Bridges Other | 027492.00 | 06/26/2024 | BATH, OAK STREET BRIDGE #0997 | Oak Street Bridge (#0997) over M.D.O.T. Railroad. Located 0.04 of a mile east of Middle Street. | Wayne Frankhauser | - | $100,000 | 624-3490
Bridges Other | 027184.10 | 07/17/2024 | FAIRFIELD-BENTON, I-95 SB BRIDGES #1455, #1456, #5999 | Interstate 95 Bridges (#1455, #1456, #5999). | Wayne Frankhauser | - | $1,125,000 | 624-3490
Bridges Other | 027258.00 | 07/24/2024 | HARPSWELL, EWING NARROWS BRIDGE #6217 | Ewing Narrows Bridge (#6217) over Ewing Narrows. Located 0.16 of a mile west of Salty Lane. | Wayne Frankhauser | - | $1,400,000 | 624-3490
Bridges Other | 027260.00 | 07/24/2024 | WISCASSET,-WESTPORT ISLAND WESTPORT-WISCASSET BRIDGE# 3180 | Westport-Wiscasset Bridge (#3180) over Cowsweag Narrows. Located 0.10 of a mile west of Burnell Road. | Wayne Frankhauser | - | $1,600,000 | 624-3490
Bridges Other | 027082.00 | 08/28/2024 | WATERBORO-LIMERICK, LEDGEMERE STATION BRIDGE #1203 | Ledgemere Station Bridge (#1203) over Little Ossipee River. Located on the Waterboro-Limerick town line. | Wayne Frankhauser | - | $380,000 | 624-3490
Bridges Other | 026113.00 | 09/04/2024 | MADISON, BICENTENNIAL MEMORIAL BRIDGE #2491 | Bicentennial Memorial Bridge (#2491) over Kennebec River. Located on the Madison-Anson town line. | Wayne Frankhauser | - | $1,630,000 | 624-3490
Bridges Other | 027184.20 | 11/13/2024 | WATERVILLE, I-95 BRIDGES #1457, #1458, #1459, #5816, #5817 | Interstate 95 Bridges (#1457, #1458, #1459, #5816, #5817). | Wayne Frankhauser | - | $2,750,000 | 624-3490
Bridges Other | 025295.00 | 12/18/2024 | BELFAST, VETERANS MEMORIAL BRIDGE #5750 | Veterans Memorial Bridge (#5750) over the Passagassawaukeag River. Located 0.27 of a mile east of High Street. | Wayne Frankhauser | - | $250,000 | 624-3490
Highway Construction | 012800.30 | 01/24/2024 | I-295 EXIT 4 SOUTH BOUND ACCESS | New access on Interstate 295 at Exit 4. Project is a partnership with South Portland. | Brad Foley | - | $4,635,000 | 624-3480
Highway Construction | 024201.00 | 03/21/2024 | TURNER, ROUTE 4 | Located at the intersection of Route 4, Bear Pond Road, and Howe's Corner Road. | Brad Foley | - | $3,564,000 | 624-3480
Highway Construction | 022658.00 | 05/22/2024 | VAN BUREN, US ROUTE 1 | Beginning 0.18 of a mile north of Parent Road in Van Buren and extending north 1.91 miles. This Project is using Congressionally Directed Spending. | David Bernhardt | - | $6,095,000 | 624-3380
Highway Construction | 018283.00 | 07/17/2024 | CAMDEN-LINCOLNVILLE, ROUTE 1 | Beginning 0.55 of a mile north of Sagamore Farm Road and extending north 1.56 miles. This project is using Congressionally Directed Spending. | Brad Foley | - | $8,609,000 | 624-3480
Highway Construction | 020405.00 | 12/04/2024 | MILBRIDGE-CHERRYFIELD RTE 1 | Beginning 0.07 of a mile north of Spruce Street in Milbridge and extending north 4.81 miles. This Project is using Congressionally Directed Spending. | Brad Foley | - | $17,045,000 | 624-3480
Highway Light Capital Paving | 026792.00 | 02/21/2024 | HOULTON AREA LCP 2024 | Houlton Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026794.00 | 02/21/2024 | SHERMAN AREA LCP 2024 | Sherman Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026764.00 | 02/21/2024 | CUMBERLAND AREA LCP 2024 | Cumberland Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026766.00 | 02/21/2024 | PARSONSFIELD AREA LCP 2024 | Parsonsfield Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026768.00 | 02/21/2024 | SANFORD AREA LCP 2024 | Sanford Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026770.00 | 02/21/2024 | BRISTOL AREA LCP 2024 | Bristol Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026772.00 | 02/21/2024 | HALLOWELL AREA LCP 2024 | Hallowell Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026774.00 | 02/21/2024 | ISLESBORO AREA LCP 2024 | Islesboro Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026776.00 | 02/21/2024 | KNOX AREA LCP 2024 | Knox Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026778.00 | 02/21/2024 | ATHENS AREA LCP 2024 | Athens Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026784.00 | 02/21/2024 | HUDSON AREA LCP 2024 | Hudson Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026786.00 | 02/21/2024 | MACHIAS AREA LCP 2024 | Machias Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026788.00 | 02/21/2024 | PITTSFIELD AREA LCP 2024 | Pittsfield Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Light Capital Paving | 026790.00 | 02/21/2024 | CARIBOU AREA LCP 2024 | Caribou Area LCP 2024 | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 018995.57 | 01/24/2024 | 2024 SEALING-REGION 5 | Crack Seal. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027318.00 | 01/31/2024 | CARIBOU, ROUTE 164 | Beginning 0.17 of mile southwest of Meadowbrook Drive and extending east 2.70 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027320.00 | 01/31/2024 | PRESQUE ISLE, ROUTES 10,167, 1A | Beginning at Centerline Road and extending west 1.44 miles. Beginning at Route 1 and extending east 0.94 of a mile. Beginning at Route 161 and extending north 6.43 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026340.00 | 01/31/2024 | WEST GARDINER - TOPSHAM I-295 SOUTHBOUND | Beginning 1.19 miles north of the Gardiner town line and extending south 21.63 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026342.00 | 01/31/2024 | TOPSHAM - GARDINER I-295 NORTHBOUND | Beginning at the Brunswick town line and extending north 21.51 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 025483.00 | 02/07/2024 | BANGOR- BREWER, INTERSTATE 395 EASTBOUND | Beginning at Odlin Road and extending east 4.76 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 025481.00 | 02/07/2024 | BANGOR- BREWER, INTERSTATE 395 WESTBOUND | Beginning at Route 1A and extending west 4.93 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027730.00 | 02/14/2024 | CROSS LAKE TWP.-FORT KENT , ROUTE 161 | Beginning 0.57 of a mile west of the Sinclair Twp. town line and extending west 5.23 miles. Beginning 1.33 miles west of Martin Road and extending northwest 1.39 Miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027740.00 | 02/14/2024 | FRENCHVILLE, ROUTE 1 | Beginning 0.05 of a mile east of Paradis Avenue and extending west 1.38 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027734.00 | 02/14/2024 | GRAND ISLE-MADAWASKA, ROUTE 1 | Beginning 0.14 of a mile north of Corbin Road and extending northwest 8.16 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027736.00 | 02/14/2024 | CARIBOU-LIMESTONE, ROUTE 89 | Beginning 0.07 of a mile north of Route 1 and extending northeast 9.64 miles to Route 1A. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027738.00 | 02/14/2024 | FORT FAIRFIELD, ROUTE 1A | Beginning at Presque Isle Road and extending north 1.11 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027732.00 | 02/14/2024 | FRENCHVILLE, ROUTE 1 | Beginning 0.17 of a mile north of Route 162 and extending southwest 1.46 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027328.00 | 02/14/2024 | NEWPORT, ROUTE 2 | Beginning at Route 11 and extending southeast 1.07 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027324.00 | 02/14/2024 | DIXMONT-NEWBURGH, ROUTE 202 | Beginning at the Troy town line and extending east 10.75 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026266.00 | 02/14/2024 | WESTBROOK, ROUTE 25B | Beginning at Larrabee Road and extending west 0.56 of a mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027338.00 | 02/21/2024 | WATERVILLE AND GARDINER, WASHINGTON STREET/ROUTE 24 2024 LCPP | Washington Street: Beginning 0.07 of a mile south of Campus Road and extending south 1.54 miles to Route 11. Route 24: Beginning 0.16 of a mile north of Sherburne Avenue and extending north 1.02 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027334.00 | 02/21/2024 | JAY-FARMINGTON, ROUTE 133 2024 LCPP | Beginning 0.09 of a mile north of Osgood Road and extending north 9.51 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027330.00 | 02/21/2024 | FARMINGTON-WILTON, ROUTE 156 2024 LCPP | Beginning at Route 41 and extending southwest 0.48 of a mile, then beginning 0.08 of a mile east of Pope Road and extending east 8.12 miles to Route 2. Beginning at Coldwell Road and extending east 0.18 of a mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027322.00 | 02/21/2024 | BLUE HILL-ELLSWORTH, ROUTE 172 2024 LCPP | Beginning 0.07 of a mile south of Turkey Farm Road and extending north 11.31 miles to Route 3. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027352.00 | 02/21/2024 | FREEPORT-DURHAM, ROUTE 136 2024 LCPP | Beginning 0.02 of a mile north of Durham Road and extending north 12.06 miles to the Auburn town line. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027340.00 | 02/21/2024 | WALDOBORO-JEFFERSON, ROUTE 32-AUGUSTA ROAD 2024 LCPP | Beginning at Route 1 and extending north 14.21 miles. Beginning at Route 17 and extending south 0.09 of a mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026005.10 | 02/28/2024 | SOUTH PORTLAND, OCEAN STREET & OCEAN STREET SPUR | Beginning at Market Street and extending south 0.11 of a mile to Broadway (Route 77). Work includes 0.04 of a mile on Ocean Street spur. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027718.00 | 02/28/2024 | AUGUSTA, ROUTES 9/201 | Route 9: Beginning 0.05 of a mile north of Glenridge Drive and extending north 0.86 of a mile. Route 201: Beginning at Route 9 and extending north 1.05 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026488.00 | 02/28/2024 | ASHLAND-CASTLE HILL, ROUTE 163 | Beginning 0.18 of a mile west of T11 R4 WELS town line and extending east 3.18 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026432.00 | 02/28/2024 | FAIRFIELD, ROUTE 201 | Beginning 0.01 of a mile north of the Waterville town line and extending north 2.77 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026458.00 | 02/28/2024 | STATEWIDE, INTERSTATE CRACK SEALING | Interstate crack sealing. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026262.00 | 02/28/2024 | PORTLAND, STEVENS AVENUE | Beginning at Woodfords Street and extending north 0.36 of a mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026268.00 | 02/28/2024 | TOPSHAM, ROUTE 196 | Beginning at Smith Road and extending southeast 0.99 of a mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026280.00 | 02/28/2024 | SOUTH PORTLAND-PORTLAND, ROUTE 77 | Beginning at Cottage Road and extending west 1.52 miles and including, Casco Bay Bridge to York Street in Portland. Work includes Beach Street ramp to Casco Bay Bridge (#5900). | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026350.00 | 02/28/2024 | BREWER, STATE STREET | Beginning at Eastern Avenue and extending northwest 0.70 of a mile to the Penobscot Bridge. BACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027726.00 | 02/28/2024 | ORLAND-ELLSWORTH, ROUTE 1 | Beginning 0.12 of a mile south of Beechwood Lane and extending southeast 14.98 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026005.20 | 02/28/2024 | SOUTH PORTLAND, EVANS STREET | Beginning at Nutter Road and extending south 0.26 of a mile to Highland Avenue. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026352.00 | 02/28/2024 | BREWER, PARKWAY SOUTH | Beginning at Wilson Street and extending south 0.47 of a mile to the I-395 bridge joint. BACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026274.00 | 03/06/2024 | AUBURN, ROUTE 4 | Beginning at Turner Street and extending north 1.33 miles. Including both lanes of a divided highway for 0.23 of a mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026276.00 | 03/06/2024 | AUBURN, ROUTE 4 | Beginning at the Veterans Memorial Bridge and extending north 1.71 miles. Includes a portion of a south-bound lane. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 018995.37 | 03/06/2024 | 2024 SEALING-REGION 3 | Crack Seal. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026264.00 | 03/06/2024 | BUXTON-GORHAM, ROUTE 202 | Beginning 0.15 of a mile northwest of Pennell Road and extending northeast 4.17 miles. Beginning 0.04 of a mile southwest of Taren Street and extending northeast 0.36 of a mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027342.00 | 03/06/2024 | AUBURN, COURT STREET | Beginning at Union Street and extending southwest 1.82 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026005.60 | 03/06/2024 | SOUTH PORTLAND, RUNNING HILL ROAD | Beginning at Cummings Road and extending west 0.11 of a mile to the Scarborough town line. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026270.00 | 03/06/2024 | AUBURN, MINOT AVENUE, COURT STREET, ROUTE 11 | Begins 0.10 of a mile south of Albiston Way and extends north 0.82 of a mile. Begins at Minot Avenue and extends east 0.42 of a mile. Begins 0.02 of a mile south of High Street and extends south 0.37 of a mile. Includes 0.53 of a mile on Route 11. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026272.00 | 03/06/2024 | SOUTH PORTLAND, RUNNING HILL ROAD | Beginning at Maine Mall Road and extending west 0.83 of a mile to Cummings Road. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026630.16 | 03/06/2024 | CALAIS, ROUTE1 | Beginning 0.41 of a mile north of the Robbinston town line and extending northwest 7.67 miles. FHWA INFRA Grant recipient. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027716.00 | 03/13/2024 | SCARBOROUGH-GORHAM, ROUTE 22/114 | Route 22: Beginning 0.07 of a mile west of Dinsmore Lane and extending west 0.03 of a mile. Route 114: Beginning 0.14 of a mile north of Beech Ridge Road and extending northwest 1.70 miles. Including ramps. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 025117.00 | 03/13/2024 | STANDISH, ROUTE 25 | Beginning 0.12 of a mile west of Route 113 and extending west 1.86 miles. Continuing 0.09 of a mile west of Saco Road and extending west 1.00 mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026001.00 | 03/13/2024 | GARDINER-FARMINGDALE, ROUTE 201 | Beginning at the Gardiner-Interstate 295 southbound Route 201 Exit ramp and extending northeast 4.77 miles. Includes ramps. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026063.00 | 03/13/2024 | FARMINGDALE - HALLOWELL, ROUTE 201 | Beginning 0.04 of a mile south of 1st Street and extending north 1.07 miles. Project funding is contingent on Congressionally Directed Spending approval. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027714.00 | 03/13/2024 | WINDHAM-GRAY, ROUTE 115/202 | Route 115: Beginning 0.07 of a mile west of the Gray town line and extending east 0.08 of a mile. Route 202: Beginning 0.04 of a mile north of River Road and extending north 7.98 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027720.00 | 03/20/2024 | SOLON-BINGHAM, ROUTE 201 | Beginning 0.15 of a mile north of Lake Road and extending north 5.73 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026482.00 | 03/20/2024 | HAMPDEN, ROUTE 1A | Beginning at the Winterport town line and extending north 3.16 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026492.00 | 03/20/2024 | VAN BUREN, ROUTE 1 | Beginning 2.52 miles north of Old Mill Street and extending north 2.57 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026494.00 | 03/20/2024 | VAN BUREN, ROUTE 1 | Beginning at School Drive and extending north 1.76 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 018995.47 | 03/20/2024 | 2024 SEALING-REGION 4 | Crack Seal. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 018995.27 | 03/20/2024 | 2024 SEALING-REGION 2 | Crack Seal. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026101.00 | 03/20/2024 | HAMPDEN, ROUTE 1A | Beginning 0.05 of a mile northeast of Carriage Lane and extending northeast 1.77 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026103.00 | 03/20/2024 | BANGOR, WASHINGTON STREET | Beginning at the Washington Street Bridge and extending east 0.37 of a mile. Includes an additional 0.22 of a divided highway. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027326.00 | 03/27/2024 | BAR HARBOR-MOUNT DESERT, ROUTE 3 | Beginning at Cromwell Harbor Road and extending south 4.33 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027722.00 | 03/27/2024 | SULLIVAN, ROUTE 1 | Beginning 0.43 of a mile north of the Hancock town line and extending southeast 3.31 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026496.00 | 03/27/2024 | NORRIDGEWOCK- MADISON, ROUTE 201A | Beginning 0.09 of a mile north of Sophie May Lane and extending north 6.32 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 018995.17 | 03/27/2024 | 2024 SEALING-REGION 1 | Crack Seal. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026057.00 | 03/27/2024 | STOCKTON SPRINGS - PROSPECT, ROUTE 1A | Beginning at the Route 1-Route 1A interchange and extending north 5.95 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026059.00 | 03/27/2024 | WINTERPORT-HAMPDEN, ROUTE 1A | Beginning 0.01 of a mile south of Memorial Drive and extending north 3.75 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026061.00 | 03/27/2024 | WINTERPORT, ROUTE 1A | Beginning at Mountain View Drive and extending north 1.99 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026065.00 | 03/27/2024 | FORT FAIRFIELD, ROUTE 161 | Beginning at Route 1A and extending southeast 1.20 miles. Includes ramps to Route 1A. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026067.00 | 03/27/2024 | FORT FAIRFIELD, ROUTE 1A | Beginning 0.05 of a mile north of McShea Siding Road and extending northeast 1.04 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026069.00 | 03/27/2024 | ANSON, ROUTE 201A | Beginning at Main Street and extending north 4.67 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026430.00 | 03/27/2024 | FORT FAIRFIELD-CARIBOU, ROUTE 161 | Beginning at Route 1A and extending northwest 6.20 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027724.00 | 04/03/2024 | T26 ED BPP - CRAWFORD, ROUTE 9 | Beginning 0.38 of a mile north of the Wesley town line and extending north 6.76 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026005.40 | 04/03/2024 | PORTLAND, WASHINGTON AVENUE | Beginning at Lester Drive and extending north 0.16 of a mile. Beginning 0.01 of a mile north of Cypress Street and extending north 0.09 of a mile to Chapman Street. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026348.00 | 04/03/2024 | ORONO, ROUTE 2 | Beginning at the north intersection of Boulder Drive and extending north 0.76 of a mile to the Old Town town line. BACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026073.00 | 04/03/2024 | ELLSWORTH, ROUTE 3, ROUTE 1A | Route 3: Beginning at Route 1 (Main Street) and extending south 2.01 miles. Route 1A: Beginning 0.17 of a mile south of Forrest Avenue and extending south 0.20 of a mile. Continuing on Route 1A at Church Street and extending south 0.09 of a mile. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026005.50 | 04/03/2024 | PORTLAND, OCEAN AVENUE (ROUTE 9) | Beginning at Grafton Street and extending north 0.42 of a mile. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026071.00 | 04/03/2024 | FARMINGTON-KINGFIELD, ROUTE 27 | Beginning at Route 4 and extending northeast 19.30 miles. Project funding is contingent on Congressionally Directed Spending approval. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026630.01 | 04/03/2024 | PERRY-EAST MACHIAS, ROUTE 1 | Route 1: Beginning 1.93 miles north of Whiting town line and extending north 8.31, includes 8.73 additional miles along Route 1. Route 190: Beginning at Route 1 and extending south 2.53 miles. Including approaches. FHWA INFRA Grant recipient. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026626.30 | 04/03/2024 | WINTERVILLE PLT-EAGLE LAKE, ROUTE 11 | Beginning at Quimby Road and extending north 3.61 miles. This Project is using Congressionally Directed Spending. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026626.20 | 04/03/2024 | PORTAGE LAKE-T14 R6 WELS, ROUTE 11 | Beginning 0.12 of a mile south of T14 R6 WELS town line and extending north 4.40 miles. This Project is using Congressionally Directed Spending. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026005.30 | 04/03/2024 | PORTLAND, RIVERSIDE STREET | Beginning at Caddie Lane and extending north 0.75 of a mile to Washington Avenue. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 028492.00 | 04/17/2024 | PRESQUE ISLE, ROUTE 1 | Beginning 0.02 of a mile north of University Street and extending north 2.34 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027336.00 | 05/08/2024 | CANAAN, ROUTE 23 2024 LCPP | Beginning at the Clinton town line and extending north 3.96 miles. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 025749.00 | 05/22/2024 | BOOTHBAY HARBOR-EDGECOMB, ROUTE 27 | Beginning 0.05 of a mile south of Route 96 and extending north 1.09 miles. Beginning 0.64 of a mile north of the Boothbay Harbor town line and extending north 9.16 miles. This project is using Congressionally Directed Spending. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 026932.00 | 05/22/2024 | BANGOR, ROUTE 2 | Beginning at the Hermon town line and extending east 0.44 of a mile to Hammond Street Extension. BACTS Sponsored. | Jeffrey Tweedie | - |  | 624-3420
Highway Preservation Paving | 018803.00 | 06/26/2024 | VASSALBORO, ROUTE 32 | Beginning 1.14 miles north of Gray Road and extending north 0.73 of a mile. This project is using Congressionally Directed Spending. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 024999.00 | 11/20/2024 | YARMOUTH, ROUTE 88 | Beginning at Princes Point Road and extending north 0.79 of a mile to Falls Bridge over the Royal River. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027874.00 | 11/20/2024 | YARMOUTH, ROUTE 1 | Beginning at Portland Street and extending north 0.84 of a mile to Forest Falls Drive. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 027856.00 | 11/20/2024 | YARMOUTH, ROUTE 115 | Beginning at Main Street and extending southeast 0.15 of a mile to Route 88. PACTS Sponsored. | David Bernhardt | - |  | 624-3380
Highway Preservation Paving | 023669.00 | 12/04/2024 | LEWISTON, ROUTE 202 | Beginning 0.03 of a mile east of the Auburn town line and extending northeast 1.44 miles to Pettingill Street. ATRC Sponsored. | Jeffrey Tweedie | - |  | 624-3420
Highway Preservation Paving | 023669.10 | 12/04/2024 | LEWISTON, ROUTE 202 | Beginning at Pettingill Street and extending north 0.22 of a mile. | Jeffrey Tweedie | - |  | 624-3420
Highway Preservation Paving | 027728.00 | 12/04/2024 | MILBRIDGE, ROUTE 1 | Beginning 0.62 of a mile north of the Stueben town line and extending north 1.26 miles. | David Bernhardt | - |  | 624-3380
Highway Rehabilitation | 028518.00 | 02/21/2024 | MACHIAS-WESLEY, ROUTE 192 | Beginning at Route 1 and extending northwest 20.25 miles to the Airline Road. | David Bernhardt | - | $608,000 | 624-3380
Highway Rehabilitation | 027022.00 | 03/20/2024 | BRUNSWICK - FREEPORT I-295 | Southbound: Beginning at the Durham Road overpass and extending south 4.15 miles. Northbound: Beginning at the Exit 24 off-ramp and extending north 4.17 miles. | David Bernhardt | - | $10,550,000 | 624-3380
Highway Rehabilitation | 027480.00 | 03/27/2024 | ST. FRANCIS -ALLAGASH, ROUTE 161 | Beginning 0.83 of a mile west of Saint John Plt. town line and extending southwest 17.96 miles to the St John River Bridge. Includes bridges (#2014, #3909, #5658). | David Bernhardt | - | $20,000,000 | 624-3380
Highway Rehabilitation | 026065.10 | 03/27/2024 | FORT FAIRFIELD, ROUTE 161 | Beginning at the Canadian Border and extending west 1.33 miles. | David Bernhardt | - | $1,895,000 | 624-3380
Highway Rehabilitation | 027658.00 | 04/03/2024 | SABATTUS - PLEASANT HILL ROAD | Beginning 0.06 of a mile north of Route 9 and extending north 0.27 of a mile. | David Bernhardt | - | $500,000 | 624-3380
Highway Rehabilitation | 027656.00 | 04/03/2024 | FREEPORT - ROUTE 125 | Beginning at Route 136 and extending northeast 0.78 of a mile to 0.04 of a mile south of Baker Road. | David Bernhardt | - | $938,000 | 624-3380
Highway Rehabilitation | 026872.00 | 04/10/2024 | DEBLOIS-BEDDINGTON, ROUTE 193 | Beginning at Hatchery Road and extending north 9.07 miles. | David Bernhardt | - | $9,600,000 | 624-3380
Highway Rehabilitation | 026964.00 | 04/17/2024 | LANG- COPLIN, ROUTE 16 | Beginning 1.22 miles west of the Coplin Plt. town line and extending east 5.32 miles to the Nash Stream Bridge. | David Bernhardt | - | $7,630,000 | 624-3380
Highway Rehabilitation | 026966.00 | 04/24/2024 | WATERFORD-ALBANY TWP, ROUTE 35 | Beginning 0.08 of a mile north of Route 118 and extending north 0.96 of a mile. | David Bernhardt | - | $1,000,000 | 624-3380
Highway Rehabilitation | 026972.00 | 04/24/2024 | LOVELL ROUTE 5 | Beginning 0.38 of a mile north of Shave Hill Road and extending north 1.23 miles to Perkins Road. Beginning 0.08 of a mile north of Hatches Hill Road and extending north 0.90 of a mile. | David Bernhardt | - | $2,260,000 | 624-3380
Highway Rehabilitation | 026974.00 | 04/24/2024 | FRYEBURG, ROUTE 5 | Beginning 0.15 of a mile north of Melanie Lane and extending north 2.14 miles. | David Bernhardt | - | $2,140,000 | 624-3380
Highway Rehabilitation | 027662.00 | 05/08/2024 | CLINTON, ROUTE 23 | Beginning at Route 201 and extending northeast 3.16 miles to the Canaan town line. | David Bernhardt | - | $3,873,000 | 624-3380
Highway Rehabilitation | 027686.00 | 06/26/2024 | VASSALBORO, ROUTE 32 | Beginning 0.27 of a mile north of the Bog Road and extending north 2.09 miles. | David Bernhardt | - | $3,250,000 | 624-3380
Highway Rehabilitation | 020267.00 | 08/28/2024 | ACTON, ROUTE 109 | Beginning 0.60 of a mile south of Garvin Road and extending north 2.21 miles. Project funding is contingent on Congressionally Directed Spending approval. | Brad Foley | - | $9,220,000 | 624-3480
Highway Safety and Spot Improvements | 025999.00 | 01/10/2024 | ORONO, INTERSTATE 95 | Beginning 0.05 of a mile south of Interstate 95 Exit 193 northbound and extending north 0.60 of a mile. Continuing 0.08 of a mile north of Interstate 95 Exit 193 southbound and extending south 0.50 of a mile. | Jeffrey Tweedie | - | $1,305,000 | 624-3420
Highway Safety and Spot Improvements | 024363.00 | 01/24/2024 | SOUTH PORTLAND, I-295 EXIT 4 | Located at Interstate 295 Exit 4. | Brad Foley | - | $2,895,000 | 624-3480
Highway Safety and Spot Improvements | 025461.00 | 02/05/2024 | ELLSWORTH, ROUTE 1A/WINKUMPAUGH ROAD | Located at the intersection of Route 1A and Winkumpaugh Road. | Brad Foley | - | $791,000 | 624-3480
Highway Safety and Spot Improvements | 023803.00 | 02/07/2024 | WINSLOW, ROUTE 100A | Large culvert (#93710) located 0.55 of a mile south of Heywood Road. | David Bernhardt | - | $298,000 | 624-3380
Highway Safety and Spot Improvements | 026396.00 | 02/14/2024 | WARREN, ROUTE 90 (#46641) | Large culvert (#46641) located 1.19 miles north of Billings Road. | Brad Foley | - | $1,901,000 | 624-3480
Highway Safety and Spot Improvements | 023755.00 | 02/14/2024 | SMYRNA, ROUTE 2 (#47102) | Large culvert (#47102) located 0.39 of a mile southwest of Timoney Lake Road. | David Bernhardt | - | $850,000 | 624-3380
Highway Safety and Spot Improvements | 023697.00 | 02/14/2024 | OAKFIELD, RIDGE ROAD (#942363) | Cross culvert (#942363) located 0.20 of a mile east of Crandall Lane. | David Bernhardt | - | $820,000 | 624-3380
Highway Safety and Spot Improvements | 026244.00 | 02/28/2024 | PORTLAND-NORWAY, ROUTE 26 | Install backplates with yellow reflective strips and supplemental signal heads. | Jeffrey Tweedie | - | $217,000 | 624-3420
Highway Safety and Spot Improvements | 026242.00 | 02/28/2024 | PORTLAND-RAYMOND, ROUTE 302 | Install Backplates with Yellow Reflective Strips and Supplemental Signal Heads. | Jeffrey Tweedie | - | $570,000 | 624-3420
Highway Safety and Spot Improvements | 025475.00 | 03/06/2024 | GREENE, SAWYER ROAD (#47417) | Large culvert (#47417) located 0.26 of a mile west of Wilkins Road. | David Bernhardt | - | $640,000 | 624-3380
Highway Safety and Spot Improvements | 024287.00 | 03/06/2024 | GREENE, SAWYER ROAD | Large culvert (#779960) located 0.81 of a mile north of Barnard Cove Drive. | David Bernhardt | - | $575,000 | 624-3380
Highway Safety and Spot Improvements | 023263.00 | 04/03/2024 | COPLIN PLT, ROUTE 16 (#921882 AND #921883) | Cross culverts (#921882 and #921883) located 0.14 of a mile south of the Eustis town line. | David Bernhardt | - | $710,000 | 624-3380
Highway Safety and Spot Improvements | 026916.00 | 04/03/2024 | REGION 3 CABLE GUARDRAIL REPLACEMENT | Obsolete cable guardrail replacement. | David Bernhardt | - | $1,306,000 | 624-3380
Highway Safety and Spot Improvements | 027710.00 | 04/10/2024 | REGION 4 ADA RAMP IMPROVEMENTS - 2 | ADA improvements. | David Bernhardt | - | $215,000 | 624-3380
Highway Safety and Spot Improvements | 027708.00 | 04/10/2024 | REGION 4 ADA RAMP IMPROVEMENTS - 1 | ADA improvements. | David Bernhardt | - | $400,000 | 624-3380
Highway Safety and Spot Improvements | 026594.40 | 04/10/2024 | WATERVILLE-OAKLAND-FAIRFIELD ADA RAMP IMPROVEMENTS IN REGION 2-2023. | Waterville-Oakland-Fairfield ADA Ramp Improvements in Region 2-2023. | David Bernhardt | - | $1,155,000 | 624-3380
Highway Safety and Spot Improvements | 026594.30 | 04/10/2024 | BOOTHBAY HARBOR-ROCKPORT-CAMDEN ADA RAMP IMPROVEMENTS | Boothbay Harbor-Rockport-Camden ADA Ramp Improvements for LCP and CPR in Region 2-2023. | David Bernhardt | - | $750,000 | 624-3380
Highway Safety and Spot Improvements | 024353.00 | 04/17/2024 | SABATTUS, HIGH STREET & GREENE STREET | Beginning at Holden Lane and extending west 0.11 of a mile to Elm Street. Beginning at Hemlock Street and extending west 0.04 of a mile. | David Bernhardt | - | $567,000 | 624-3380
Highway Safety and Spot Improvements | 026286.00 | 04/17/2024 | TURNER, ROUTE 4 | Located at the intersection of Route 4 and Weston Road. | Brad Foley | - | $1,308,000 | 624-3480
Highway Safety and Spot Improvements | 026246.00 | 04/17/2024 | 2024 LARGE ANIMAL SIGNAGE | Install large animal high impact area signage on select corridors. | David Bernhardt | - | $94,000 | 624-3380
Highway Safety and Spot Improvements | 024199.00 | 04/17/2024 | TURNER, ROUTE 4 | Located at the intersection of Route 4 and Route 117. | Brad Foley | - | $997,000 | 624-3480
Highway Safety and Spot Improvements | 026630.14 | 04/24/2024 | MACHIAS-WHITING, ROUTE 1/ROUTE 190 | Various locations on Route 1 and Route 190 between Machias and Whiting. FHWA INFRA Grant recipient. | David Bernhardt | - | $654,000 | 624-3380
Highway Safety and Spot Improvements | 026134.00 | 04/24/2024 | BRUNSWICK, PLEASANT STREET, MAINE STREET | Traffic signal modifications on Maine Street and Pleasant Street. | Jeffrey Tweedie | - | $1,040,000 | 624-3420
Highway Safety and Spot Improvements | 026138.00 | 04/24/2024 | TOPSHAM, ROUTE 196, TOPSHAM FAIR MALL ROAD | Traffic Signal modifications on Route 196 and Topsham Fair Mall Road. | Jeffrey Tweedie | - | $1,353,000 | 624-3420
Highway Safety and Spot Improvements | 026968.00 | 04/24/2024 | ALBANY TWP, ROUTE 5 | Beginning at Stoneham town line and extending southeast 0.91 of a mile. | David Bernhardt | - | $910,000 | 624-3380
Highway Safety and Spot Improvements | 027712.00 | 04/24/2024 | REGION 5 ADA RAMP IMPROVEMENTS | ADA improvements. | David Bernhardt | - | $930,000 | 624-3380
Highway Safety and Spot Improvements | 026260.00 | 06/12/2024 | 2024 STATEWIDE RUMBLE STRIPS | Rumble Strips: New and replacement for recently paved roads. | David Bernhardt | - | $745,000 | 624-3380
Highway Safety and Spot Improvements | 024267.00 | 06/19/2024 | EAGLE LAKE, ROUTE 11 (#941218) | Large culvert (#941218) located 0.11 of a mile south of Makayla Drive. | David Bernhardt | - | $655,000 | 624-3380
Highway Safety and Spot Improvements | 026592.00 | 07/31/2024 | ADA IMPROVEMENTS FOR LCP AND CPR IN REGION 1 | ADA Improvements for LCP and CPR in Region 1. | David Bernhardt | - | $696,000 | 624-3380
Highway Safety and Spot Improvements | 026354.00 | 10/09/2024 | BANGOR, GRIFFIN ROAD AND KENDUSKEAG AVENUE SIGNAL | Located at the intersection of Kenduskeag Avenue and Griffin Road. BACTS Sponsored. | Jeffrey Tweedie | - | $373,000 | 624-3420
Highway Safety and Spot Improvements | 023531.00 | 11/27/2024 | BROOKLIN, ROUTE 175 | Large culvert (#46688) located 0.05 of a mile south of Flye Point Road. | David Bernhardt | - | $871,000 | 624-3380
Highway Safety and Spot Improvements | 026799.00 | 12/04/2024 | EDGECOMB, RIVER ROAD (#123913) | Large culvert (#123913) located 0.94 of a mile north of McKay Road. | David Bernhardt | - | $905,000 | 624-3380
Highway Safety and Spot Improvements | 024279.00 | 12/11/2024 | ETNA, ROUTE 2 | Large culvert (#47394) located 0.73 of a mile east of West Etna Road. | David Bernhardt | - | $670,000 | 624-3380
Highway Safety and Spot Improvements | 026284.00 | 12/13/2024 | CHELSEA, ROUTE 17 | Located at the intersection of Route 17 and Windsor Road. | Brad Foley | - | $945,000 | 624-3480
Highway Safety and Spot Improvements | 025329.00 | 12/18/2024 | DOVER FOXCROFT, ROUTE 15 | Located at the intersection of Route 7 and Route 15. | Brad Foley | - | $1,485,000 | 624-3480
Highway Safety and Spot Improvements | 025265.00 | 12/18/2024 | WINDHAM, ROUTE 302 | Located at the intersection of Route 302 and Albion Road. | Jeffrey Tweedie | - | $585,000 | 624-3420
Highway Safety and Spot Improvements | 023747.00 | 12/26/2024 | SANFORD, ROUTE 202 | Large culvert (#46484) located 0.19 of a mile northeast of Jellerson Road. | David Bernhardt | - | $1,501,000 | 624-3380
Maintenance | 026624.00 | 03/13/2024 | KITTERY I-95 NB VISITOR INFORMATION CENTER PARKING AREA AND ACCESS ROAD | Located at the Kittery Interstate 95 Northbound Visitor Information Center. | David Bernhardt | - | $1,250,000 | 624-3380
Maintenance | 025371.00 | 05/15/2024 | MADAWASKA, MILL STREET | Beginning 0.02 of a mile north of Route 1 and extending northeast 0.15 of a mile. | David Bernhardt | - | $265,000 | 624-3380
Maintenance | 024185.00 | 07/17/2024 | STATEWIDE, RWIS ITS | Dedicated Short-Range Communications (DSRC), Road Weather Information System (RWIS), On-Board Units (OBUs), Automatic Vehicle Location (AVL) and meteorological support for plow truck connections. | Jeffrey Tweedie | - | $1,490,000 | 624-3420
Maintenance | 026128.00 | 09/25/2024 | BANGOR, I-395 OHVDS ITS | Over Height Detection. | Jeffrey Tweedie | - | $400,000 | 624-3420
Maintenance | 026130.00 | 10/23/2024 | STATEWIDE, INTERSTATE TRAFFIC CAMERAS ITS | Streaming cameras. | Jeffrey Tweedie | - | $530,000 | 624-3420
Maintenance | 025971.00 | 12/04/2024 | PACTS RTMS, TCMS UPGRADE | Upgrade the server and PACTS Remote Traffic Microwave System (RTMS). | Jeffrey Tweedie | - | $245,000 | 624-3420
Multimodal | 026310.00 | 01/24/2024 | SANFORD HEADS UP - UPDATED PEDESTRIAN SIGNAGE | Purchase and installation of new and replacement regulatory and warning signage at various locations. | Jeffrey Tweedie | - | $75,000 | 624-3420
Multimodal | 026746.01 | 02/28/2024 | MAINE NORTHERN RAILWAY EARMARK | Upgrade the Presque Isle/Houlton/Fort Fairfield/Madawaska Lines and the mainline from Millinocket to Scopan Township. This project is using Congressionally Directed Spending. | Jeffrey Tweedie | - | $1,283,000 | 624-3420
Multimodal | 027762.00 | 04/17/2024 | BATH CHARTER BOAT PUBLIC DOCK SHIP | To construct a convenient, safe and accessible dock facility for the charter boats operating out of Bath and to allow easy public access to their business in a central location. | Jeffrey Tweedie | - | $218,000 | 624-3420
Multimodal | 019426.10 | 05/22/2024 | SCARBOROUGH, EASTERN TRAIL | Eastern Trail bicycle and pedestrian connection. Beginning at Nonesuch River and extending east 0.60 of a mile to Pleasant Hill Road. | Jeffrey Tweedie | - | $4,768,000 | 624-3420
Multimodal | 019426.00 | 05/22/2024 | S. PORTLAND-SCARBOROUGH, EASTERN TRAIL | Beginning at Wainwright Field in South Portland and extending south 0.80 of a mile to Pleasant Hill Road in Scarborough. | Jeffrey Tweedie | - | $1,858,000 | 624-3420
Multimodal | 025207.00 | 06/19/2024 | KENNEBUNKPORT, CAPE PORPOISE PHASE 2, SHIP | Wharf improvements located at the end of Pier Road. | Jeffrey Tweedie | - | $500,000 | 624-3420
Multimodal | 025205.00 | 06/19/2024 | KENNEBUNKPORT, CAPE PORPOISE PHASE 3, SHIP | Bait shed demolition and reconstruction located at the end of Pier Road. | Jeffrey Tweedie | - | $500,000 | 624-3420
Multimodal | 026232.00 | 06/19/2024 | BRUNSWICK, BOAT RAMP SHIP | Located 0.45 of a mile south of Pennell Way. | Jeffrey Tweedie | - | $350,000 | 624-3420
Multimodal | 026824.00 | 06/26/2024 | LUBEC, BREAKWATER | Creation of a new breakwater, boat launch, parking lot, and wharf located off of Route 189 (135 Main Street). MARAD BUILD Grant recipient. | Jeffrey Tweedie | - | $56,246,000 | 624-3420
Multimodal | 025277.00 | 08/05/2024 | SKOWHEGAN, SRTS SIDEWALKS | Beginning 0.38 of a mile northeast of Mary Street and extending northeast 0.29 of a mile on Norridgewock Avenue, and 0.09 of a mile on Pleasant Street and extending to Coburn Avenue. | Jeffrey Tweedie | - | $1,065,000 | 624-3420
Multimodal | 027610.00 | 09/25/2024 | VINALHAVEN, MAIN STREET, SHIP | Replacement of Boat Ramps in downtown Vinalhaven. | Jeffrey Tweedie | - | $504,000 | 624-3420
Multimodal | 024605.10 | 09/25/2024 | MCS FERRY REPLACEMENT - MSFS | New ferry that services the Maine State Ferry Service Project. Recipient of federal discretionary grant. | Jeffrey Tweedie | - | $38,000,000 | 624-3420
Multimodal | 024685.01 | 09/25/2024 | CHEBEAGUE/ GREAT DIAMOND/ CLIFF ISLAND/ PEAK'S | Improvements to state owned assets serving the ferry. | Jeffrey Tweedie | - | $4,450,000 | 624-3420
Multimodal | 024357.00 | 09/25/2024 | EASTPORT, HIGH ST. SIDEWALKS | Beginning at Battery Street and extending north 0.27 of a mile. | Jeffrey Tweedie | - | $600,000 | 624-3420
Multimodal | 027756.00 | 10/09/2024 | BAR HARBOR COMMERCIAL SKIFF FLOATS | The replacement of a float system that services commercial fishermen for the purposes of skiff and dinghy tie up. | Jeffrey Tweedie | - | $99,000 | 624-3420
Multimodal | 027758.00 | 10/16/2024 | SWAN'S ISLAND EMS RAMP / FLOAT | Installation of a gangway on the new float system. | Jeffrey Tweedie | - | $60,000 | 624-3420
Multimodal | 025621.00 | 11/27/2024 | LEWISTON, MAIN STREET, SABATTUS STREET, HEADS UP | Pedestrian safety improvements to three new priority crosswalk locations on Main and Sabattus Streets to include ADA accommodations, high visibility treatments, and rectangular rapid flashing beacons (RRFBs). | Jeffrey Tweedie | - | $810,000 | 624-3420
Multimodal | 026318.00 | 11/27/2024 | LEWISTON HEADS UP - NEW MAIN ST. PED CROSSING BETWEEN BEARCE AVE. AND MONTELLO ST. | Installation of a new high visibility pedestrian crossing. Beginning at Bearce Avenue and extending north 0.25 of a mile to Montello Street. | Jeffrey Tweedie | - | $225,000 | 624-3420
Multimodal | 026322.00 | 11/27/2024 | LEWISTON HEADS UP - "5 CORNERS" PED SAFETY CROSSING IMPROVEMENTS | Located at the intersection of Sabattus Street, Webster Street, Central Avenue, and Ash Street. | Jeffrey Tweedie | - | $355,000 | 624-3420
Multimodal | 023813.00 | 12/04/2024 | LIMESTONE, 1A; HIGH; HUGGARD | Beginning on Route 1A at School Avenue and extending west on FFA Avenue for 0.10 of a mile, then continuing on High Street for 0.43 of a mile to Route 89. Also includes Huggard Avenue from High St. 0.10 of a mile east, across Route 1A to Cyr Drive. | Jeffrey Tweedie | - | $1,136,000 | 624-3420