Community Risk Reduction Plan Development Guide and Schedule

GOAL: Develop and implement a full Community Risk Reduction Plan based on fire risk.

| Progression | Description | Date |
| --- | --- | --- |
| Step 1 | CRA Work Session with SFMO |  |
|  | SFMO Advisory Session (Phone call or TEAMS) | Day 7 |
| Step 2 | Submit Part A from your CRR Plan Worksheet | Day 10 |
| Step 2A | Address Part A Comments | Day 15 |
|  | SFMO Advisory Session | Day 20 |
| Step 3 | Submit Part B from your CRR Plan Worksheet | Day 25 |
| Step 3A | Address Part B Comments | Day 35 |
|  | SFMO Advisory Session | Day 37 |
| Step 4 | Submit Part C from your CRR Plan Worksheet | Day 40 |
| Step 4A | Address Part C Comments | Day 45 |
|  | SFMO Advisory Session | Day 50 |
| Step 5 | Submit Final Draft CRR Plan | Day 55 |
| Step 6 | Address Comments/ Submit Final CRR Plan | Day 60 |