## Compiled_list
Bundle ID | Stream | MSHV | MaineDOT Asset ID | Town | Economic Disadvantage1 | Watershed | Latitude | Longitude | Existing Structure | Construction Year | DOT Condition | Fisheries | Habitat Type | Resource Agency Priority | Modeled BFW | 1.2 BFW | Proposed Structure | In MaineDOT Workplan | Notes | Location Link | Round Total Cost | Revised Bridge Cost | Scope | Likely Structure (ft) | NEPA Complete | Kickoff | PDR | PSE | ADV | Construction Begin | Construction Complete
Mid-Coast | Little Medomak Brook | NA | 3930 | Washington | Alna | [17 empty] | Replacement | 21 | 2028-03-01 | 2026-11-19 | 2027-10-15 | 2028-09-01 | 2028-09-30 | 2028-10-30 | 2029-12-01
| Togus Stream | 15995 | 0493 | Randolph | N | Kennebec River |  |  | culvert | 1982 | 4 | Herring | Migration | High | 21.3 | 25.56 |  | Y |  | https://mdotinetapps.state.me.us/map/?map=ezI1ODlBMDYxLTcwQzgtMTFFRC05NTRCLUQwNjcyNkJBMUVDOH0= | 1500000 | 2200000 | Replacement | 45 | 2025-12-01 | 2025-07-01 | 2025-07-30 | 2026-05-01 | 2026-06-01 | 2026-06-30 | 2027-12-01
| Sevenmile Brook | 16241 | 0526 | Vassalboro | [18 empty] | Replacement | 53 | 2025-12-01 | 2025-07-01 | 2025-07-30 | 2026-05-01 | 2026-06-01 | 2026-06-30 | 2027-12-01
| Sheepscot River | 3831 | 2830 | Montville | [18 empty] | Replacement | 21 | 2028-03-01 | 2026-11-19 | 2027-10-15 | 2028-09-01 | 2028-09-30 | 2028-10-30 | 2029-12-01
| Unnamed Stream | 4514 | 46566 | Cushing | [18 empty] | Replacement | 18 | 2029-03-01 | 2027-11-19 | 2028-10-15 | 2029-09-01 | 2029-09-30 | 2029-10-30 | 1930-12-01