## Sheet1
MaineDOT 2025 Construction Advertisement Plan
Last Revised: January 2, 2025
This is MaineDOT's bid advertisement plan for capital projects to be advertised during the calendar year.
In years in which major funding components of MaineDOT's capital program are being debated, partial plans or mid-year alterations may be required.
Such years could include odd numbered years during which state budgets and bonding levels are typically decided, and years in which federal transportation authorization bills are pending.
This Plan is to be distinguished from the Current Construction Advertisement Schedule, which is a separate dynamic document updated online each Monday.
The current schedule will reflect changes caused by such factors as cash flow, bid prices, local and public input, and design and permitting.
WORK TYPE | PROJECT ID | PLANNED ADVERTISE DATE | PROJECT TITLE | WORK PLAN DESC | PRGRAM MANAGER | EXECUTIVE COMMENT | ESTIMATE | PHONE
Bridge Construction | 025453.00 | 01/29/2025 | FORT FAIRFIELD, PUDDLE DOCK BRIDGE #2691 | Puddle Dock Bridge (#2691) over Pattie Brook. Located 0.02 of a mile north of Dorsey Road. | Wayne Frankhauser | - | $4,100,000 | 624-3490
Bridge Construction | 026105.00 | 02/19/2025 | CHARLOTTE, ROUND POND BRIDGE #3787 | Round Pond Bridge (#3787) over Round Pond Outlet. Located 1.10 miles northeast of Ayers Junction Road. | Wayne Frankhauser | - | $3,600,000 | 624-3490
Bridge Construction | 026168.00 | 02/19/2025 | WASHINGTON, FARRAR BRIDGE #3929 | Farrar Bridge (#3929) over Jackson Stream. Located 0.51 of a mile west of Vanner Road. | Wayne Frankhauser | - | $1,565,000 | 624-3490
Bridge Construction | 028246.00 | 04/09/2025 | LITCHFIELD, MAXWELL BRIDGE #2524 | Maxwell Bridge (#2524) over Maxwell Brook. Located 0.42 of a mile west of Upper Pond Road. | Wayne Frankhauser | - | $2,000,000 | 624-3490
Bridge Construction | 025387.00 | 04/16/2025 | CODYVILLE TWP., LITTLE TOMAH BRIDGE #2472 | Little Tomah Bridge (#2472) over Little Tomah Stream. Located 1.80 miles southwest of Todd Farm Road. | Wayne Frankhauser | - | $4,310,000 | 624-3490
Bridge Construction | 025095.01 | 05/07/2025 | CAMDEN BIKE/PED BRIDGE | Rawson Avenue Pedestrian Bridge over Megunticook River. Located 0.05 of a mile southwest of Washington Street. | Jeffrey Tweedie | - | $500,000 | 624-3420
Bridge Construction | 025161.00 | 05/21/2025 | CUMBERLAND, TUTTLE ROAD / I295 BRIDGE #5801 | Tuttle Road / I-295 Bridge (#5801) over Interstate 295 and Route 1 and MCRR. Located 1.64 miles north of the Falmouth town line. | Wayne Frankhauser | - | $20,395,000 | 624-3490
Bridge Construction | 022382.00 | 05/28/2025 | YARMOUTH, ROUTE 1/ I-295 BRIDGE #5804 | Route 1/ I-295 Bridge (#5804) over Interstate 295. Located 0.04 of a mile north of Interstate 295 northbound Exit 15. | Wayne Frankhauser | - | $23,148,000 | 624-3490
Bridge Construction | 026226.00 | 06/18/2025 | KENNEBUNK, DAYS MILLS BRIDGE #2221 | Days Mill Bridge (#2221) over Kennebunk River. Located 0.02 of a mile north of Days Mills Road. | Wayne Frankhauser | - | $3,790,000 | 624-3490
Bridge Construction | 021686.10 | 07/09/2025 | CHARLOTTE, MOOSEHORN BRIDGE #3332 | Moosehorn Bridge (#3332) over Cranberry Creek. Located 0.17 of a mile west of Goodell Road. | Wayne Frankhauser | - | $2,175,000 | 624-3490
Bridge Construction | 025449.00 | 09/10/2025 | NEWCASTLE, MEADOW BROOK BRIDGE #2535 | Meadow Brook Bridge (#2535) over Deer Meadow Brook. Located 4.09 miles west of Bunker Hill Road. | Wayne Frankhauser | - | $1,495,000 | 624-3490
Bridge Construction | 023120.00 | 09/17/2025 | DOVER FOXCROFT, DOVER BRIDGE #5118 | Dover Bridge (#5118) over Piscataquis River. Located 0.04 of a mile east of River Street. This project is using Congressionally Directed Spending. | Wayne Frankhauser | - | $9,830,000 | 624-3490
Bridge Construction | 026630.07 | 09/24/2025 | PERRY, SMELT BROOK BRIDGE #2774 | Smelt Brook Bridge (#2774) over Smelt Brook. Located 0.10 of a mile west of Thompson Store Road. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $5,490,000 | 624-3490
Bridge Construction | 026630.06 | 09/24/2025 | ROBBINSTON, MILL COVE NEW BRIDGE #6205 | Mill Cove New Bridge (#6205) over Mill Cove. Located 0.08 of a mile north of Ridge Road. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $6,040,000 | 624-3490
Bridge Construction | 029486.00 | 09/30/2025 | SIDNEY - WATERVILLE, I-95 BRIDGES | Interstate 95 Bridges. Bridge Investment Program (BIP) Grant recipient. | Wayne Frankhauser | - | $87,074,000 | 624-3490
Bridge Construction | 023643.00 | 10/22/2025 | HOLLIS, SALMON FALLS BRIDGE #3708 | Salmon Falls Bridge (#3708) over Saco River. Located on the Hollis-Buxton town line. | Wayne Frankhauser | - | $8,865,000 | 624-3490
Bridge Construction | 026160.00 | 10/29/2025 | BOWDOIN, LEWIS BRIDGE #5396 | Lewis Bridge (#5396) over West Cathance Stream. Located 0.41 of a mile west of Deer Run Road. | Wayne Frankhauser | - | $1,745,000 | 624-3490
Bridge Construction | 026097.00 | 11/05/2025 | DIXMONT, CROCKER BROOK BRIDGE #5424 | Crocker Brook Bridge (#5424) over Crocker Brook. Located 0.40 of a mile east of Troy town line. | Wayne Frankhauser | - | $2,380,000 | 624-3490
Bridge Construction | 021687.00 | 11/05/2025 | ARGYLE TWP, HEMLOCK STREAM BRIDGE #3735 | Hemlock Stream Bridge (#3735) over Hemlock Stream. Located 2.22 miles north of Argyle Road. | Wayne Frankhauser | - | $3,854,000 | 624-3490
Bridge Construction | 026107.00 | 11/12/2025 | MARIAVILLE, TANNERY BRIDGE #3511 | Tannery Bridge (#3511) over Tannery Brook. Located 0.16 of a mile north of Olive Carr Road. | Wayne Frankhauser | - | $3,915,000 | 624-3490
Bridge Construction | 025309.00 | 11/12/2025 | TURNER, TURNER CENTER BRIDGE #3886 | Turner Center Bridge (#3886) over the Nezinscot River. Located 0.07 of a mile west of Lower Street. | Wayne Frankhauser | - | $7,630,000 | 624-3490
Bridge Construction | 026156.00 | 11/19/2025 | MONMOUTH, BAILEY FLAT BRIDGE #3671 | Bailey Flat Bridge (#3671) over Mud Mills Stream. Located 0.73 of a mile north of Gilman Road. | Wayne Frankhauser | - | $1,735,000 | 624-3490
Bridge Construction | 018595.11 | 11/19/2025 | BANGOR, EXIT 187 DDI HOGAN ROAD/ I-95 BRIDGE #5823 | Construction of diverging diamond interchange on Hogan Road/ Interstate 95 Exit 187 and Hogan Road/ I-95 Bridge (#5823) over Interstate 95. | Brad Foley | - | $60,000,000 | 624-3480
Located 0.26 of a mile north of Haskell Road. FHWA RAISE Grant recipient.
Bridge Construction | 026234.00 | 11/19/2025 | MONMOUTH, WAGGON BRIDGE #0487 | Waggon Bridge (#0487) over Wilson Stream. Located 0.13 of a mile south of Hansons Wood Road. | Wayne Frankhauser | - | $2,910,000 | 624-3490
Bridge Construction | 026180.00 | 11/26/2025 | CUMBERLAND, NOYES BRIDGE #5932 | Noyes Bridge (#5932) over Mill Brook. Located 0.18 of a mile north of Cross Road. | Wayne Frankhauser | - | $2,180,000 | 624-3490
Bridge Construction | 026236.00 | 11/26/2025 | BRIDGTON, CORNSHOP BRIDGE #0318 | Cornshop Bridge (#0318) over Stevens Brook. Located 0.20 of a mile west of Main Street. | Wayne Frankhauser | - | $3,130,000 | 624-3490
Bridge Construction | 027838.02 | 12/03/2025 | WESLEY, BIG NEW STREAM #6289 | Big New Stream (#6289) over East Branch New Stream. Located 0.10 of a mile west of New Stream Lane. FHWA Culvert Grant Recipient. | Wayne Frankhauser | - | $2,838,000 | 624-3490
Bridge Construction | 027838.01 | 12/03/2025 | WESLEY, BEAVER DAM BRIDGE #2061 | Beaver Dam Bridge (#2061) over Beaver Dam Brook. Located 0.30 of a mile south of T26 ED BPP. FHWA Culvert Grant Recipient. | Wayne Frankhauser | - | $3,700,000 | 624-3490
Bridge Construction | 027530.00 | 12/03/2025 | BROWNFIELD MERRILLS CORNER BRIDGE #0714 | Merrills Corner Bridge (#0714) over Shepards River. Located 0.07 of a mile south of Hampshire Road. | Wayne Frankhauser | - | $2,185,000 | 624-3490
Bridge Construction | 025541.00 | 12/10/2025 | PROSPECT, COLSON BRIDGE #2168 | Colson Bridge (#2168) over Colson Stream. Located 0.38 of a mile north of Hawes Bridge Road. | Wayne Frankhauser | - | $5,900,000 | 624-3490
Bridge Construction | 026083.00 | 12/10/2025 | VAN BUREN, ST. MARY'S BRIDGE #5309 | St. Mary's Bridge (#5309) over Violette Brook. Located 0.03 of a mile north of St. Mary's Brook Road. | Wayne Frankhauser | - | $3,310,000 | 624-3490
Bridge Construction | 027230.00 | 12/10/2025 | LEWISTON, HART'S RIVER ROAD BRIDGE #0093 | Hart's River Road Bridge (#0093) over Hart's Brook. Located 0.15 of a mile north of Interstate 95. | Wayne Frankhauser | - | $2,355,000 | 624-3490
Bridge Construction | 027232.00 | 12/17/2025 | LEWISTON, STETSON BROOK BRIDGE #0091 | Stetson Brook Bridge (#0091) over Stetson Brook. Located 0.20 of a mile north of Old Farm Road. | Wayne Frankhauser | - | $1,905,000 | 624-3490
Bridge Construction | 026434.00 | 12/17/2025 | PRESQUE ISLE, PHAIR CROSSING BRIDGE #3259 | Phair Crossing Bridge (#3259) over B&A Railroad. Located 0.68 of a mile east of Egypt Road. | Wayne Frankhauser | - | $6,470,000 | 624-3490
Bridge Construction | 025529.00 | 12/17/2025 | EAST MACHIAS, CHASE MILLS BRIDGE #5465 | Chase Mills Bridge (#5465) over Gardiner Lake Outlet. Located 0.03 of a mile north of Lakeside Road. | Wayne Frankhauser | - | $2,625,000 | 624-3490
Bridge Construction | 026184.00 | 12/17/2025 | SABATTUS, SABATTUS RIVER BRIDGE #5393 | Sabattus River Bridge (#5393) over Sabattus River. Located 0.14 of a mile northeast of Main Street. | Wayne Frankhauser | - | $3,840,000 | 624-3490
Bridge Construction | 026111.00 | 12/31/2025 | PITTSFIELD, OSBORNE BRIDGE #2634 | Osborne Bridge (#2634) over Farnham Brook. Located 0.18 of a mile north of Webb Road. | Wayne Frankhauser | - | $1,500,000 | 624-3490
Bridge Construction | 026109.00 | 12/31/2025 | PITTSFIELD, FARNHAM BRIDGE #2274 | Farnham Bridge (#2274) over Farnham Brook. Located 0.12 of a mile north of Webb Road. | Wayne Frankhauser | - | $1,500,000 | 624-3490
Bridges Other | 027778.00 | 02/19/2025 | PENOBSCOT NARROWS BRIDGE & OBSERVATORY - SAFETY FENCE PROJECT | Penobscot Narrows Bridge & Observatory (#6421) over the Penobscot River. Located on the Prospect-Verona town line. | Wayne Frankhauser | - | $1,815,000 | 624-3490
Bridges Other | 028408.00 | 03/19/2025 | GRAY, SWEETSER BRIDGE #5781 | Sweetser Bridge (#5781) over Royal River. Located 0.39 of a mile west of Town Farm Road. | Wayne Frankhauser | - | $300,000 | 624-3490
Bridges Other | 028400.00 | 03/19/2025 | WATERFORD, HORRS BRIDGE #5192 | Horrs Bridge (#5192) over Crooked River. Located 0.06 of a mile northwest of Route 118. | Wayne Frankhauser | - | $200,000 | 624-3490
Bridges Other | 028394.00 | 03/19/2025 | NEWBURGH, ROUTE 69/I95 BRIDGE #5967 | Route 69/I95 Bridge (#5967) over Interstate 95 southbound and northbound. Located 0.15 of a mile north of Murray Road. | Wayne Frankhauser | - | $1,300,000 | 624-3490
Bridges Other | 028390.00 | 03/19/2025 | ETNA, WEST ETNA ROAD/I95 BRIDGE #5961 | West Etna Road/I95 Bridge (#5961) over Interstate 95 southbound and northbound. Located 0.61 of a mile north of Route 69. | Wayne Frankhauser | - | $1,000,000 | 624-3490
Bridges Other | 026902.00 | 03/19/2025 | FALMOUTH, I295 SB / PRESUMPSCOT RIVER BRIDGE #1505 | I-295 SB/Presumpscot River Bridge (#1505) over Presumpscot River. Located 0.79 of a mile west of Lunt Road. | Wayne Frankhauser | - | $750,000 | 624-3490
Bridges Other | 027092.00 | 03/19/2025 | BELFAST, ROUTE US 1/ROUTE 3 BRIDGE #1378 | Route US 1/Route 3 Bridge (#1378) over Route 3. Located 0.39 of a mile north of Route 52. | Wayne Frankhauser | - | $400,000 | 624-3490
Bridges Other | 027090.00 | 03/19/2025 | WARREN, ST. GEORGE RIVER BRIDGE #5654 | St. George River Bridge (#5654) over Saint George River. Located 0.31 of a mile west of Route 131. | Wayne Frankhauser | - | $1,000,000 | 624-3490
Bridges Other | 027094.00 | 03/19/2025 | LEWISTON, INTERCHANGE/ROUTE 196 BRIDGE #0060 | Interchange/Route 196 Bridge (#0060) over Route 196. Located 0.15 of a mile south of Route 196. | Wayne Frankhauser | - | $500,000 | 624-3490
Bridges Other | 027268.00 | 03/19/2025 | LITCHFIELD, THOROUGHFARE BRIDGE #3925 | Thoroughfare Bridge (#3925) over Pleasant Road. Located on the Litchfield-Richmond town line. | Wayne Frankhauser | - | $200,000 | 624-3490
Bridges Other | 023192.10 | 03/19/2025 | FAIRFIELD, INTERSTATE 95/ M C RR BRIDGE #5999 | I-95/ MCRR Bridge (#5999) over Lower Kennebec River. Located 0.10 of a mile east of Interstate 95 northbound Exit 133. | Wayne Frankhauser | - | $475,000 | 624-3490
Bridges Other | 026228.00 | 03/26/2025 | CASCO ,ROUTE 302 / CROOKED RIVER #2200 | Route 302/Crooked River Bridge (#2200) over Crooked River. Located 0.16 of a mile northwest of Hillside Avenue. | Wayne Frankhauser | - | $1,010,000 | 624-3490
Bridges Other | 026898.00 | 03/26/2025 | REGION 2 AND 3 BRIDGES #3389, #3106, #1141, #6374, #1522, #1523, #2615, #3667 | Region 2 and Region 3 bridges (#3389, #3106, #1141, #6374, #1522, #1523, #2615, #3667). | Wayne Frankhauser | - | $1,800,000 | 624-3490
Bridges Other | 026081.00 | 03/27/2025 | ISLAND FALLS, I95SB/B&A RR AND PATTEN ROAD BRIDGE #6176 | I-95 SB/B&ARR and Patten Road Bridge (#6176) over Patten Road. Located 0.49 of a mile north of Crystal Road. | Wayne Frankhauser | - | $600,000 | 624-3490
Bridges Other | 027070.00 | 04/23/2025 | GORHAM - WINDHAM, GREAT FALLS #1 (LONG) BRIDGE #6210, WINDHAM GREAT FALLS #2 BRIDGE 1529 | Great Falls #1 (Long) Bridge (#6210) over the Presumpscot River. Located 0.04 of a mile east of the Gorham town line. Great Falls #2 Bridge (#1529) over the Presumpscot River. Located on the Gorham-Windham town line. | Wayne Frankhauser | - | $796,000 | 624-3490
Bridges Other | 026962.10 | 05/21/2025 | BASS HARBOR #6339 AND SWANS ISLAND #6349 | Upgrade Transfer bridges to Bass Harbor Bridge (#6339) and Swans Island Bridge (#6349). | Jeffrey Tweedie | - | $3,190,000 | 624-3420
Bridges Other | 028406.00 | 05/26/2025 | CAPE ELIZABETH, SPURWINK BRIDGE #2796 | Spurwink Bridge (#2796) over Spurwink River. Located 0.34 of a mile northwest of Spurwink Avenue. | Wayne Frankhauser | - | $470,000 | 624-3490
Bridges Other | 028530.00 | 05/28/2025 | STATEWIDE, INTERSTATE BRIDGE JOINTS PRESERVATION - PAVING SYNERGIES | Identification of bridge joint replacement needs. | Wayne Frankhauser | - | $10,000,000 | 624-3490
Bridges Other | 028410.00 | 06/11/2025 | MECHANIC FALLS-MINOT, POTTLE BRIDGE #2977 | Pottle Bridge (#2977) over Bog Brook. Located 0.18 of a mile north of Bucknam Road. | Wayne Frankhauser | - | $700,000 | 624-3490
Bridges Other | 027078.00 | 06/11/2025 | MECHANIC FALLS, MECHANIC FALLS BRIDGE #2540 | Mechanic Falls Bridge (#2540) over the Little Androscoggin River. Located 0.08 of a mile northwest of Elm Street. | Wayne Frankhauser | - | $1,055,000 | 624-3490
Bridges Other | 028012.00 | 06/25/2025 | FERRY SERVICE TRANSFER BRIDGES CAPITAL REHAB | Ferry Service Transfer Bridges - Apron hinge replacement bridges (#6349, #6339, #6343, #6342, #6344, #6351, #6341, #6473). | Jeffrey Tweedie | - | $700,000 | 624-3420
Bridges Other | 026186.00 | 06/25/2025 | SCARBOROUGH, PLEASANT AVENUE CROSSING BRIDGE #3911 | Pleasant Avenue Crossing Bridge (#3911) over B&M Railroad. Located 0.09 of a mile north of Rigby Road. | Wayne Frankhauser | - | $301,000 | 624-3490
Bridges Other | 026224.00 | 11/19/2025 | VANCEBORO, INTERNATIONAL BRIDGE #2401 | International Bridge (#2401) over Saint Croix River. Located 0.04 of a mile east of Water Street. | Wayne Frankhauser | - | $1,775,000 | 624-3490
Highway Construction | 025459.00 | 02/05/2025 | ALFRED, ROUTE 202 | Beginning 0.04 of a mile north of Mulberry Lane and extending north 0.25 of a mile. | Brad Foley | - | $2,390,000 | 624-3480
Highway Construction | 023689.00 | 02/05/2025 | NEWPORT, ROUTE 2 | Beginning 0.04 of a mile east of Lovely Drive and extending east 0.22 of a mile. This project is using Congressionally Directed Spending. | Brad Foley | - | $8,605,000 | 624-3480
Highway Construction | 025271.00 | 02/12/2025 | ELLSWORTH, ROUTE 1 | Located at the intersection of Route 1 and Route 172. | Brad Foley | - | $703,000 | 624-3480
Highway Construction | 026019.00 | 02/26/2025 | DAMARISCOTTA, ROUTE 1, BELVEDERE ROAD | Located at the intersection of Route 1 and Belvedere Road. | Brad Foley | - | $4,260,000 | 624-3480
Highway Construction | 026288.00 | 06/13/2025 | LEBANON, ROUTE 202 | Located at the intersection of Route 202, Center Street and Long Swamp Road. | Brad Foley | - | $2,590,000 | 624-3480
Highway Construction | 022643.00 | 09/10/2025 | LIVERMORE FALLS, ROUTE 17 | Beginning at the intersection of Route 133 and extending north 1.11 miles to Route 4. Includes 0.21 of a mile on Depot Street, Pleasant Street and Church Street, This project is using Congressionally Directed Spending. | Brad Foley | - | $16,911,000 | 624-3480
Highway Construction | 026282.00 | 09/19/2025 | LYMAN, ROUTE 111 | Located at the intersection of Route 111 and Day Road. | Brad Foley | - | $2,240,000 | 624-3480
Highway Construction | 025751.00 | 09/24/2025 | AUGUSTA, ROUTE 202, 201, 201S | Beginning at Route 105 and extending north 0.64 of a mile on Route 201. Beginning at Route 201 and extending east 0.08 of a mile on Route 202. Including exits on the rotary. This project is using Congressionally Directed Spending. | Brad Foley | - | $7,825,000 | 624-3480
Highway Construction | 006462.92 | 10/06/2025 | PRESQUE ISLE, SECTION I | Beginning at Route 1 and extending north 5.83 miles to the Conant Road. FHWA INFRA Grant recipient | Brad Foley | - | $84,224,000 | 624-3480
Highway Construction | 021651.00 | 11/19/2025 | YORK, ROUTE 1A. PHASE 1 | Beginning 0.04 of a mile south of Lindsay Road extending north 0.15 of a mile then northeast 0.17 of a mile on Long Sands Road. Also includes 0.29 of a mile of Route 1A from intersection to Moulton Lane; construction in WIN 21651.01. KACTS Sponsored. | Jeffrey Tweedie | - | $4,310,000 | 624-3420
Highway Construction | 025273.00 | 12/01/2025 | AUGUSTA, ROUTE 201 | Located at the intersection of Route 201 and Gage Street. | Brad Foley | - | $1,635,000 | 624-3480
Highway Light Capital Paving | 027806.00 | 02/19/2025 | RUMFORD AREA LCP 2025 | Rumford Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027814.00 | 02/19/2025 | LEVANT AREA LCP 2025 | Levant Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027816.00 | 02/19/2025 | ORLAND AREA LCP 2025 | Orland Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027818.00 | 02/19/2025 | CUTLER AREA LCP 2025 | Cutler Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027822.00 | 02/19/2025 | MADAWASKA AREA LCP 2025 | Madawaska Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028956.10 | 02/19/2025 | SEBAGO-NAPLES, ROUTE 107, 2025 LCP | Beginning 0.11 of a mile north of Convene Road and extending north 9.46 miles to Route 117. | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028958.10 | 02/19/2025 | SULLIVAN-FRANKLIN, ROUTE 200, 2025 LCP | Beginning at Route 1 and extending north 5.93 miles to Route 182. | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028960.10 | 02/19/2025 | SOLDIERTOWN TWP T2 R7 WELS-SHERMAN, ROUTE 11, 2025 LCP | Beginning at Grindstone Twp. town line and extending northeast 13.62 miles to Route 158. | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028962.10 | 02/19/2025 | DRESDEN-WOOLWICH, ROUTE 127, 2025 LCP | Beginning at Route 197 and extending south 12.49 miles. | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027808.00 | 02/19/2025 | PARIS AREA LCP 2025 | Paris Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027826.00 | 02/19/2025 | MEDWAY AREA LCP 2025 | Medway Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027812.00 | 02/19/2025 | SWAN’S ISLAND AREA LCP 2025 | Swan’s Island Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027804.00 | 02/19/2025 | SIDNEY AREA LCP 2025 | Sidney Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027802.00 | 02/19/2025 | DRESDEN AREA LCP 2025 | Dresden Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027800.00 | 02/19/2025 | ALBION AREA LCP 2025 | Albion Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027794.00 | 02/19/2025 | BUXTON AREA LCP 2025 | Buxton Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027792.00 | 02/19/2025 | BALDWIN AREA LCP 2025 | Baldwin Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027828.00 | 02/19/2025 | PRESQUE ISLE AREA LCP 2025 | Presque Isle Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028954.00 | 02/19/2025 | MADAWASKA-SAINT AGATHA, BEAULIEU ROAD, 2025 LCP | Beginning at Route 162 and extending northeast 12.25 miles to Route 1. | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028952.00 | 02/19/2025 | CORINNA-STETSON, ROUTE 222, 2025 LCP | Beginning at Route 11 and extending southeast 7.18 miles to Route 143. | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028950.00 | 02/19/2025 | ANDOVER-RUMFORD, ROUTE 120, 2025 LCP | Beginning at Route 5 and extending southeast 14.08 miles. | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 027798.00 | 02/19/2025 | WATERFORD AREA LCP 2025 | Waterford Area LCP 2025 | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028946.00 | 02/19/2025 | LEBANON-ACTON, DEPOT ROAD, MILTON MILLS ROAD, 2025 LCP | Beginning at Route 202 and extending northwest 8.07 miles. | Emory Lovely | - |  | 624-3380
Highway Light Capital Paving | 028948.00 | 02/19/2025 | WINTHROP-MONMOUTH, ROUTE 135, 2025 LCP | Beginning at Route 132 and extending northeast 9.65 miles to Route 202. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 018995.28 | 01/29/2025 | 2025 SEALING-REGION 2 | Crack Seal. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 018995.38 | 01/29/2025 | 2025 SEALING-REGION 3 | Crack Seal. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 018995.48 | 01/29/2025 | 2025 SEALING-REGION 4 | Crack Seal. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 018995.58 | 01/29/2025 | 2025 SEALING-REGION 5 | Crack Seal. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026005.30 | 01/29/2025 | PORTLAND, RIVERSIDE STREET | Beginning at Caddie Lane and extending north 0.75 of a mile to Washington Avenue. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026005.40 | 01/29/2025 | PORTLAND, WASHINGTON AVENUE | Beginning at Lester Drive and extending north 0.16 of a mile. Beginning 0.01 of a mile north of Cypress Street and extending north 0.09 of a mile to Chapman Street. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026005.50 | 01/29/2025 | PORTLAND, OCEAN AVENUE (ROUTE 9) | Beginning at Grafton Street and extending north 0.42 of a mile. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028194.00 | 01/29/2025 | NAPLES-POLAND, ROUTE 11 | Beginning at Route 302 and extending northeast 10.43 miles to 0.03 of a mile north of White Oak Hill Road. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027351.00 | 02/05/2025 | LEWISTON, PLEASANT STREET | Beginning at East Avenue and extending southeast 0.82 of a mile. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027344.00 | 02/05/2025 | LEWISTON, COLLEGE STREET | Beginning at Vale Street and extending south 0.32 of a mile to Sabattus Street. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028236.00 | 02/12/2025 | PRESQUE ISLE, ROUTE 227/227W/AIRPORT DRIVE/SKYWAY STREET/STATE ROAD | Airport Drive: Beginning at Skyway Street and extending south 1.00 mile to Central Drive. Skyway Street: Beginning at State Road and extending west 1.12 miles to Airport Drive. Includes 0.48 of a mile on Route 227/State Road and 0.07 on Route 227W. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027498.00 | 02/12/2025 | WATERVILLE-AUGUSTA, INTERSTATE 95 SOUTHBOUND | Beginning 0.08 of a mile west of the Benton town line and extending southwest 21.70 miles to the north abutment of the Civic Center Bridge overpass. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028864.00 | 02/12/2025 | UNION-JEFFERSON, ROUTE 17 | Beginning at the Washington town line and extending west 4.81 miles. Beginning at Shepard Hill Road and extending northwest 3.47 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028238.00 | 02/12/2025 | CARIBOU, ROUTE 161B/ROUTE 161BS | Route 161B: Beginning at Presque Isle Road and extending west 0.26 of a mile to Route 164. Beginning at Prospect Street and extending northwest 2.50 miles. Route 161BS: Beginning at Sweden Street and extending southeast 0.10 of a mile to Route 164. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027462.00 | 02/12/2025 | WINSLOW - WATERVILLE, ROUTE 137 | Beginning at Route 137B and extending west 2.32 miles. Beginning 0.03 of a mile north of Wyman Street and extending northwest 0.04 of a mile. Beginning at Route 104 and extending east 0.29 of a mile. Paving includes the Donald V. Carter Bridge. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028234.00 | 02/12/2025 | FORT FAIRFIELD, ROUTE 1A | Beginning 0.16 of a mile north of Upcountry Road and extending north 3.33 miles to Presque Isle Road. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028232.00 | 02/12/2025 | MARS HILL, ROUTE 1A | Beginning at Route 1 and extending north 2.80 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028218.00 | 02/19/2025 | MDI - SOUTHWEST HBR, ROUTE 102 2025 LCPP | Beginning at Pretty Marsh Road and extending south 4.57 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028216.00 | 02/19/2025 | LAGRANGE-HOWLAND, ROUTE 155 2025 LCPP | Beginning at Route 16 and extending northeast 12.37 miles to Route 2. Includes roundabout. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028196.00 | 02/19/2025 | SACO-LYMAN, ROUTE 5 2025 LCPP | Beginning 0.18 of a mile northwest of Interstate 95 and extending northwest 10.23 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028208.00 | 02/19/2025 | LEEDS, ROUTE 219 2025 LCPP | Beginning 0.01 of a mile east of Route 108 and extending east 1.88 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028202.00 | 02/19/2025 | RICHMOND, ROUTE 197 2025 LCPP | Beginning at Route 201 and extending east 1.50 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028200.00 | 02/19/2025 | BOWDOIN-RICHMOND. ROUTE 201 2025 LCPP | Beginning at the Topsham town line and extending north 8.43 miles to Route 197. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028214.00 | 02/19/2025 | PARIS-BUCKFIELD, ROUTE 117 2025 LCPP | Beginning at Route 119 and extending northeast 9.60 miles to Route 140. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028222.00 | 02/19/2025 | WEST PARIS - HARTFORD, ROUTE 219 2025 LCPP | Beginning at Bethel Road and extending northeast 13.44 miles to Bear Pond Road. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028228.00 | 02/19/2025 | WESTON-ORIENT, ROUTE 1 2025 LCPP | Beginning 0.35 of a mile north of Butterfield Landing Road and extending north 4.99 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028230.00 | 02/19/2025 | WINN-MATTAWAMKEAG, ROUTE 2 2025 LCPP | Beginning at the Lincoln town line and extending northeast 7.54 miles to the Medway Road. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028226.00 | 02/26/2025 | PARKMAN, ROUTE 150 | Beginning at the Cambridge town line and extending north 8.46 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027012.00 | 02/26/2025 | SACO, ROUTE 1/ROUTE 1S | Beginning 0.05 of a mile east of the Biddeford town line and extending east 0.44 of a mile. Beginning at Route 5 and extending west 0.05 of a mile to Route 112. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028204.00 | 02/26/2025 | UNITY, ROUTE 202 | Beginning 0.04 of a mile north of the Albion town line and extending north 5.81 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028876.00 | 02/26/2025 | WALLAGRASS, ROUTE 11 | Beginning 0.04 of a mile north of the Eagle Lake town line and extending north 3.12 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028878.00 | 02/26/2025 | LITTLETON-MONTICELLO, ROUTE 1 | Beginning 0.36 of a mile north of the Wiley Road and extending north 10.21 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027518.00 | 02/26/2025 | BELGRADE, ROUTE 27 | Beginning 0.14 of a mile south of Hazel Drive and extending north 7.18 miles. This Project is using Congressionally Directed Spending. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027514.00 | 02/26/2025 | ROME, ROUTE 27 | Beginning 0.09 of a mile south of Route 225 and extending north 2.52 miles to the New Sharon town line. This Project is using Congressionally Directed Spending. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027008.00 | 02/26/2025 | BIDDEFORD, ROUTE 111 | Beginning 0.01 of a mile west of Summit Street and extending west 0.67 of a mile. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028874.00 | 02/26/2025 | NEW SWEDEN-MADAWASKA LAKE TWP., ROUTE 161 | Beginning 0.07 of a mile south of the Station Road and extending north 9.43 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027010.00 | 02/26/2025 | BIDDEFORD-SACO, ROUTE 1 | Beginning at Dartmouth Street and extending north 1.40 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026626.40 | 02/26/2025 | T14 R6 WELS - WINTERVILLE, ROUTE 11 | Beginning 4.29 miles north of Portage Lake town line and extending north 6.81 miles to Quimby Road. This Project is using Congressionally Directed Spending. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026626.50 | 02/26/2025 | EAGLE LAKE-WALLAGRASS, ROUTE 11 | Beginning 0.37 of a mile north of Winterville Plt. town line and extending north 6.28 miles. This Project is using Congressionally Directed Spending. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026986.00 | 02/26/2025 | BELGRADE-ROME, ROUTE 27 | Beginning 0.26 of a mile north of Hulin Road and extending north 2.97 miles. This Project is using Congressionally Directed Spending. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028220.00 | 02/26/2025 | LINCOLN-CHESTER, ROUTE 116/ACCESS ROAD/ROUTE 2 | Route 116: Beginning at Route 2 and extending northwest 1.71 miles to Access Road. Access Road: Beginning at S. Chester Road and extending west 2.56 miles. Route 2: Beginning 0.03 of a mile south of River Road and extending north 0.95 of a mile. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028224.00 | 02/26/2025 | BANGOR-ORONO, ROUTE 2 | Beginning 0.02 of a mile northeast of Meadowbrook Road and extending northeast 4.14 miles to Kelley Road. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027504.00 | 03/05/2025 | AUGUSTA-WATERVILLE, INTERSTATE 95 | Beginning a the north abutment of the Civic Center Drive overpass and extending north 13.52 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026996.00 | 03/05/2025 | WALLAGRASS, ROUTE 11 | Beginning 0.44 of a mile north of Soldier Pond Road and extending north 2.37 miles to Sutton Siding Road. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027332.00 | 03/05/2025 | MADISON, ROUTE 148 | Beginning at Lakewood Drive and extending west 5.89 miles to Old Point Avenue. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028866.00 | 03/12/2025 | CHINA-LIBERTY, ROUTE 3 | Beginning 0.50 of a mile east of Alder Park Road and extending east 11.87 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028868.00 | 03/12/2025 | AUGUSTA, MOUNT VERNON AVENUE | Beginning 0.02 of a mile south of Boothby Street and extending north 1.54 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028210.00 | 03/19/2025 | WINTHROP, MAIN STREET | Beginning 0.01 of a mile west of Green Street and extending east 0.63 of a mile. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028862.00 | 03/19/2025 | LEWISTON-WINTHROP, ROUTE 202 | Beginning 0.05 of a mile north of Northwood Road and extending north 16.94 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028860.00 | 03/19/2025 | WINTHROP-WAYNE, ROUTE 133 | Beginning 0.09 of a mile northwest of Route 41 and extending northwest 4.71 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 025707.00 | 03/19/2025 | ABBOT TO GREENVILLE, ROUTE 6 | Beginning at Lily Bay Road and extending south 21.45 miles, then beginning 0.98 of a mile south of Gales Road and extending south 0.56 of a mile. This Project is using Congressionally Directed Spending. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028856.00 | 03/26/2025 | BRIDGTON, ROUTE 302 | Beginning at Gage Street and extending northwest 5.31 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028206.00 | 03/26/2025 | BELFAST, ROUTE 141 | Beginning at Route 1 and extending north 2.25 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027846.00 | 03/26/2025 | SCARBOROUGH, SACO STREET | Beginning at Gorham Road and extending north 0.67 of a mile to the Gorham town line. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027016.00 | 03/26/2025 | BRIDGTON, ROUTE 302, ROUTE117 | Beginning 0.04 of a mile north of Sandy Creek Road and extending north 1.51 miles. Beginning at Route 302 and extending north 0.03 of a mile. Includes 0.03 of a mile on Route 117S. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027854.00 | 03/26/2025 | WESTBROOK, SACO STREET | Beginning at the Scarborough town line and extending north 0.52 of a mile to Spiller Drive. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027852.00 | 03/26/2025 | WESTBROOK, STROUDWATER ST. | Beginning at Main Street and extending south 0.04 of a mile to William B Clarke Drive. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027844.00 | 03/26/2025 | SCARBOROUGH, SPRING STREET | Beginning 0.17 of a mile north of Mussey Road and extending north 0.27 of a mile. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 018995.18 | 03/26/2025 | 2025 SEALING-REGION 1 | Crack Seal. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028212.00 | 03/26/2025 | BELFAST, ROUTE 52/ROUTE 7/VINE STREET/LINCOLNVILLE AVENUE | Route 52: Beginning 0.25 of a mile northeast of Boynton Drive and extending northeast 0.20 of a mile. Route 7: Beginning at Route 3 and extending northwest 0.96 of a mile. Includes 0.19 of a mile on Vine Street and 0.55 of a mile on Lincolnville Avenue. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028858.00 | 04/02/2025 | NEW GLOUCESTER, ROUTE 202 | Beginning at the Gray town line and extending north 6.42 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028872.00 | 04/02/2025 | CANAAN, ROUTE 2 | Beginning at the Skowhegan town line and extending east 1.73 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028346.00 | 04/02/2025 | ROCKLAND - ROCKPORT, ROUTE 1 | Beginning at Route 17 and extending north 0.93 of a mile. Beginning at Old County Road and extending north 1.51 miles to Sea Light Lane. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027516.00 | 04/02/2025 | SKOWHEGAN, ROUTE 2 | Beginning at Route 150 and extending east 6.98 miles to the Canaan town line. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028870.00 | 04/02/2025 | FARMINGTON-PHILLIPS, ROUTE 4 | Beginning 0.20 of a mile west of the Strong town line and extending northwest 10.53 miles. Beginning 0.16 of a mile south of Route 27 and extending northwest 7.78 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027850.00 | 04/02/2025 | GORHAM, ROUTE 114 | Beginning 0.04 of a mile north of Maine Street and extending north 1.60 miles. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027702.00 | 04/02/2025 | SKOWHEGAN-MADISON ROUTE 201 | Beginning at Commercial Street and extending north 1.84 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026630.02 | 04/02/2025 | CALAIS, ROUTE 1/ROUTE 9 | Beginning 0.19 of a mile north of Riverview Lane and extending northerly 4.42 miles. Includes three segments off Route 1. FHWA INFRA Grant recipient. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027522.00 | 04/09/2025 | WELLS-KENNEBUNK, ROUTE 1 | Beginning 0.16 of a mile north of Bypass Road and extending north 2.17 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027512.00 | 04/09/2025 | CHARLESTON - DOVER-FOXCROFT, ROUTE 15 | Beginning 0.05 of a mile north of the Corinth town line and extending north 9.59 miles. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027520.00 | 04/09/2025 | WELLS, ROUTE 1 | Beginning 0.03 of a mile north of Harbor Road and extending north 0.37 of a mile. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028898.00 | 04/09/2025 | WOOLWICH, ROUTE 1 | Beginning 0.02 of a mile south of Route 127 and extending north 0.63 of a mile. Beginning 0.12 of a mile northeast of George Wright Road and extending northeast0.78 of a mile. Beginning 0.09 of a mile northeast of Nequasset Road and extending 3.19 miles | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027018.00 | 04/23/2025 | AUBURN, ROUTE 4,4S,136S,136 | Beginning at Academy Street and extending south 0.18 of a mile. Beginning at High Street and extending east 0.12 of a mile. Beginning 0.05 of a mile north of Mill Street and extending north 0.30 of a mile. Including 1.94 miles on Route 4 and Route 4S. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027876.00 | 04/23/2025 | FREEPORT, ROUTE 125 | Beginning at Main Street and extending northwest 0.30 of a mile. PACTS Sponsored. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027002.00 | 05/07/2025 | PORTLAND - FORE RIVER PKWY | Beginning 0.51 of a mile south of I-295 and extending south 0.82 of a mile. Beginning 0.07 of a mile north of I-295 and extending north 0.03 of a mile. Beginning 0.03 of a mile south of Valley Street and extending north 0.69 of a mile. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 027000.00 | 05/07/2025 | PORTLAND - W COMMERCIAL STREET | Beginning 0.04 of a mile east of Valley Street and extending east 0.63 of a mile. Includes 0.21 of a mile of divided highway. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026278.00 | 05/07/2025 | PORTLAND, CONGRESS STREET & FORE RIVER PARKWAY | Beginning at Interstate 295 Exit 5B southbound off-ramp and extending west 0.51 of a mile on Route 22. Beginning at Route 22 and extending south 0.21 of a mile on Fore River Parkway. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026930.00 | 05/14/2025 | BANGOR, ROUTE 222 | Beginning at Davis Road and extending east 1.50 miles to Griffin Road. BACTS Sponsored. | Jeffrey Tweedie | - |  | 624-3420
Highway Preservation Paving | 028198.00 | 05/28/2025 | PORTLAND, DEERING AVENUE/ROUTE 25/ROUTE 9/WOODFORD STREET | Deering Avenue: Beginning at Route 9 and extends south 0.72 of a mile. Route 25: Beginning at Route 22 and extends north 0.48 of a mile. Route 9: Beginning at Stevens Ave. and extends east 0.55 of a mile. Woodford Street: Includes 0.38 of a mile. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 026630.03 | 06/18/2025 | WHITING-ROBBINSTON, ROUTE 1 | Beginning 0.76 miles northeast of Dodge Road and extending northeast 5.16 miles. Beginning 1.59 miles north of Route 86 and extending north 7.71 miles. Beginning 0.53 mile north of Route 190 and extending north 8.26 miles. FHWA INFRA Grant recipient. | Emory Lovely | - |  | 624-3380
Highway Preservation Paving | 028734.00 | 09/10/2025 | LIVERMORE FALLS, CHURCH/PLEASANT STREETS | Beginning 0.07 of a mile north of Union Street and extending north 0.08 of a mile to Route 133. Beginning 0.02 of a mile north of Depot Street and extending north 0.36 of a mile to Searles Street. | Emory Lovely | - |  | 624-3380
Highway Rehabilitation | 027214.00 | 02/26/2025 | EAGLE LAKE, SLY BROOK ROAD REHAB | Beginning 1.06 miles south of the Wallagrass town line and extending north 0.18 of a mile. | Emory Lovely | - | $430,000 | 624-3380
Highway Rehabilitation | 026584.00 | 02/26/2025 | BASE REPAIR ON SLY BROOK ROAD IN EAGLE LAKE | Beginning 1.82 miles south of the Wallagrass town line and extending north 0.07 of a mile. | Emory Lovely | - | $303,000 | 624-3380
Highway Rehabilitation | 027526.00 | 03/05/2025 | NEW SHARON, ROUTE 27 | Beginning at the Rome town line and extending north 4.43 miles to the Mercer Road. This Project is using Congressionally Directed Spending. | Emory Lovely | - | $8,350,000 | 624-3380
Highway Rehabilitation | 027502.00 | 03/12/2025 | BRUNSWICK, ROUTE 1 SB | Beginning 0.70 of a mile west of Old Bath Road and extending west 2.72 miles. Including all approaches and ramps. | Emory Lovely | - | $8,035,000 | 624-3380
Highway Rehabilitation | 027500.00 | 03/12/2025 | BRUNSWICK, ROUTE 1 NB | Beginning 0.17 of a mile east of Cushing Street and extending east 2.81 miles. Including all approaches and ramps. | Emory Lovely | - | $8,035,000 | 624-3380
Highway Rehabilitation | 027670.00 | 03/12/2025 | CRYSTAL, ROUTE 159 | Beginning 0.54 of a mile east of Old Pattern Road and extending west 1.16 miles. | Emory Lovely | - | $1,573,000 | 624-3380
Highway Rehabilitation | 028900.00 | 03/19/2025 | FARMINGTON, TOWN FARM ROAD | Beginning 0.14 of a mile northwest of Marvel Street and extending northwest 2.86 miles to Route 4. | Emory Lovely | - | $3,855,000 | 624-3380
Highway Rehabilitation | 027668.50 | 03/26/2025 | BOWDOIN, ROUTE 125 | Beginning 0.03 of a mile east of the Lisbon town line and extending east 4.18 miles to Route 201. | Emory Lovely | - | $3,130,000 | 624-3380
Highway Rehabilitation | 027668.00 | 03/26/2025 | BOWDOIN, ROUTE 125 | Beginning 0.03 of a mile east of the Lisbon town line and extending east 4.18 miles to Route 201. | Emory Lovely | - | $6,458,000 | 624-3380
Highway Rehabilitation | 027668.40 | 03/26/2025 | BOWDOIN, ROUTE 125 | Beginning 0.03 of a mile east of the Lisbon town line and extending east 4.18 miles to Route 201. | Emory Lovely | - | $260,000 | 624-3380
Highway Rehabilitation | 027688.00 | 04/02/2025 | COPLIN PLT.-EUSTIS, ROUTE 16 | Beginning at the Nash Stream Bridge and extending east 2.31 miles to Route 27. | Emory Lovely | - | $3,569,000 | 624-3380
Highway Rehabilitation | 027676.00 | 04/02/2025 | ELLSWORTH/HANCOCK , MAIN ST/WASHINGTON JCT ROAD | Beginning 0.02 of a mile northeast of McKenzie Avenue and extending northeast 3.75 miles. | Emory Lovely | - | $5,250,000 | 624-3380
Highway Rehabilitation | 026970.00 | 06/04/2025 | LOVELL - STONEHAM ROUTE 5 | Beginning at West Stoneham Road and extending north 4.41 miles to the Albany Twp. town line. | Emory Lovely | - | $6,174,000 | 624-3380
Highway Rehabilitation | 018777.00 | 08/13/2025 | BLUE HILL, ROUTE 15 | Beginning at the Sedgwick town line and extending north 2.09 miles. | Emory Lovely | - | $9,560,000 | 624-3380
Highway Rehabilitation | 021812.00 | 09/24/2025 | PITTSFIELD, ROUTE 11/100 | Beginning 0.02 of a mile south of Nichols Street and extending north 1.85 miles. This project is using Congressionally Directed Spending. | Emory Lovely | - | $5,973,000 | 624-3380
Highway Rehabilitation | 026958.00 | 11/12/2025 | CHINA-VASSALBORO, ROUTE 32 | Beginning 0.90 of a mile north of Memory Lane and extending north 2.85 miles. | Emory Lovely | - | $4,403,000 | 624-3380
Highway Safety and Spot Improvements | 026382.00 | 01/08/2025 | BUXTON, ROUTE 22 | Large culvert (#1063141) located 0.01 of a mile southeast of Rankin Road. | Emory Lovely | - | $665,000 | 624-3380
Highway Safety and Spot Improvements | 026380.00 | 01/08/2025 | BUXTON, ROUTE 22 | Large culvert (#1063182) located 0.38 of a mile northwest of Dunnell Road. | Emory Lovely | - | $319,000 | 624-3380
Highway Safety and Spot Improvements | 025513.00 | 01/08/2025 | WHITEFIELD, ROUTE 194 | Large culvert (#894509) located 0.38 of a mile northwest of Radden Lane. | Emory Lovely | - | $675,000 | 624-3380
Highway Safety and Spot Improvements | 023531.00 | 01/08/2025 | BROOKLIN, ROUTE 175 | Large culvert (#46688) located 0.05 of a mile south of Flye Point Road. | Emory Lovely | - | $1,240,000 | 624-3380
Highway Safety and Spot Improvements | 025425.00 | 01/22/2025 | MATTAWAMKEAG, ROUTE 2 (#184299) | Cross culvert (#184299) located 0.38 of a mile northeast of the Winn town line. | Emory Lovely | - | $837,000 | 624-3380
Highway Safety and Spot Improvements | 025471.00 | 01/29/2025 | WARREN, MAIN STREET | Beginning 0.09 of a mile east of Western Road and extending east 0.25 of a mile. | Emory Lovely | - | $1,000,000 | 624-3380
Highway Safety and Spot Improvements | 026924.00 | 02/05/2025 | PITTSFIELD, ROUTE 2 WEIGH STATIONS | Located 0.81 of a mile northeast of Powers Road. | Brad Foley | - | $150,000 | 624-3480
Highway Safety and Spot Improvements | 026926.00 | 02/26/2025 | STATEWIDE WEIGH STATIONS | Truck Weight Areas. | Emory Lovely | - | $150,000 | 624-3380
Highway Safety and Spot Improvements | 024269.00 | 02/26/2025 | EAGLE LAKE, SLY BROOK ROAD XC-180935 | Large culvert (#180935) located 5.07 miles north of the Strip Road. | Emory Lovely | - | $565,000 | 624-3380
Highway Safety and Spot Improvements | 024247.00 | 03/26/2025 | T6R8, GRAND LAKE ROAD | Large culvert (#46554) located 0.43 of a mile east of T5 R8 WELS town line. | Emory Lovely | - | $670,000 | 624-3380
Highway Safety and Spot Improvements | 027706.00 | 03/26/2025 | REGION 3 ADA RAMP IMPROVEMENTS | ADA improvements. | Emory Lovely | - | $1,265,000 | 624-3380
Highway Safety and Spot Improvements | 024263.00 | 03/26/2025 | T6 R8 WELS, GRAND LAKE ROAD | Large culvert (#995797) located 0.70 of a mile east of the T5 R8 WELS town line. | Emory Lovely | - | $680,000 | 624-3380
Highway Safety and Spot Improvements | 024243.00 | 04/02/2025 | WALDOBORO, ROUTE 220 | Large culvert (#124776) located 0.51 of a mile northwest of Mayo Road. | Emory Lovely | - | $710,000 | 624-3380
Highway Safety and Spot Improvements | 024251.00 | 04/02/2025 | WALDOBORO-FRIENDSHIP, FINNTOWN ROAD | Large culvert (#46646) located on the Waldoboro-Friendship town line. | Emory Lovely | - | $1,093,000 | 624-3380
Highway Safety and Spot Improvements | 029536.00 | 04/02/2025 | STATEWIDE, CLOSED DRAINAGE INSPECTION/CLEANING | Closed drainage cleaning, inspecting, collecting and managing. | Emory Lovely | - | $500,000 | 624-3380
Highway Safety and Spot Improvements | 028848.00 | 04/09/2025 | REGION 5, SOUTHERN AROOSTOOK AREA, ADA RAMP IMPROVEMENTS | ADA improvements. | Emory Lovely | - | $116,000 | 624-3380
Highway Safety and Spot Improvements | 028882.00 | 04/09/2025 | REGION 5, NORTHERN AROOSTOOK AREA, ADA RAMP IMPROVEMENTS | ADA improvements. | Emory Lovely | - | $500,000 | 624-3380
Highway Safety and Spot Improvements | 028842.00 | 04/16/2025 | REGION 3 STRONG AREA, ADA RAMP IMPROVEMENTS | ADA improvements. | Emory Lovely | - | $1,140,000 | 624-3380
Highway Safety and Spot Improvements | 028968.00 | 04/16/2025 | SEARSPORT, SEARS ISLAND ROAD | Beginning 0.84 of a mile south of Route 1 and extending south 0.40 of a mile. | Emory Lovely | - | $1,700,000 | 624-3380
Highway Safety and Spot Improvements | 028838.00 | 04/16/2025 | REGION 2 CENTRAL AREA, ADA RAMP IMPROVEMENTS | ADA improvements. | Emory Lovely | - | $290,000 | 624-3380
Highway Safety and Spot Improvements | 028840.00 | 04/16/2025 | REGION 2 MIDCOAST AREA, ADA RAMP IMPROVEMENTS | ADA improvements. | Emory Lovely | - | $300,000 | 624-3380
Highway Safety and Spot Improvements | 028844.00 | 04/23/2025 | REGION 4 DOWNEAST AREA, ADA RAMP IMPROVEMENTS | ADA improvements. | Emory Lovely | - | $517,000 | 624-3380
Highway Safety and Spot Improvements | 028846.00 | 04/23/2025 | REGION 4, NEWPORT AREA, ADA RAMP IMPROVEMENTS | Americans with Disabilities Act (ADA) improvements. | Emory Lovely | - | $1,494,000 | 624-3380
Highway Safety and Spot Improvements | 024281.00 | 04/30/2025 | WATERBORO, ROUTE 202, LC#46515 | Large culvert (#46515) located 0.17 of a mile west of Old Alfred Road. | Emory Lovely | - | $980,000 | 624-3380
Highway Safety and Spot Improvements | 022841.00 | 05/07/2025 | CARIBOU, GRIMES ROAD | Beginning 1.50 miles northwest of the Murphy Road and extending north 0.16 of a mile. | Emory Lovely | - | $1,270,000 | 624-3380
Highway Safety and Spot Improvements | 025389.00 | 05/14/2025 | LISBON, ROUTE 196 | Beginning at Bowdoin Street and extending west 0.27 of a mile to Route 9. | Emory Lovely | - | $1,190,000 | 624-3380
Highway Safety and Spot Improvements | 027136.00 | 05/20/2025 | GARDINER, ROUTE 24, (#269786) | Large culvert (#269786) located 0.12 of a mile southwest of Costello Road. | Brad Foley | - | $1,045,000 | 624-3480
Highway Safety and Spot Improvements | 026422.00 | 05/28/2025 | ALLAGASH, ROUTE 161 (#179682) | Cross culvert (#179682) located 1.07 miles east of Carney Road. | Emory Lovely | - | $775,000 | 624-3380
Highway Safety and Spot Improvements | 026630.15 | 06/04/2025 | WHITING-EDMUNDS TWP., ROUTE 1 | Various locations on Route 1 between Whiting and Edmunds Twp. town line. FHWA INFRA Grant recipient. | Emory Lovely | - | $324,000 | 624-3380
Highway Safety and Spot Improvements | 027786.00 | 06/11/2025 | EDGECOMB, ROUTE 1/CROSS ROAD | Located at the intersection of Route 1, Cochran Road and Cross Road. | Jeffrey Tweedie | - | $725,000 | 624-3420
Highway Safety and Spot Improvements | 027054.00 | 06/11/2025 | STATEWIDE, RUMBLE STRIPS | Rumble Strips: New and replacement for recently paved roads. | Emory Lovely | - | $745,000 | 624-3380
Highway Safety and Spot Improvements | 026372.00 | 06/20/2025 | DIXFIELD, ROUTE 142 (#47306) | Large culvert (#47306) located 0.06 of a mile north of Holt Hill Road. | Brad Foley | - | $520,000 | 624-3480
Highway Safety and Spot Improvements | 021782.00 | 08/27/2025 | EDDINGTON, ROUTE 46 | Large culvert (#46776) located 0.22 of a mile north of Hatcase Pond Road. | Emory Lovely | - | $910,000 | 624-3380
Highway Safety and Spot Improvements | 027704.00 | 08/27/2025 | REGION 1 ADA RAMP IMPROVEMENTS | ADA improvements. | Emory Lovely | - | $1,040,000 | 624-3380
Highway Safety and Spot Improvements | 026630.09 | 09/24/2025 | PEMBROKE, LARGE CULVERT (#47373) | Large culvert (#47373) located 0.06 of mile south of Ayers Junction Road. FHWA INFRA Grant recipient. | Emory Lovely | - | $918,000 | 624-3380
Highway Safety and Spot Improvements | 026630.12 | 09/24/2025 | PERRY, CROSS CULVERT (#88085) | Cross culvert (#88085) located 0.12 of a mile west of Cannon Hill Road. FHWA INFRA Grant recipient. | Emory Lovely | - | $918,000 | 624-3380
Highway Safety and Spot Improvements | 026630.11 | 09/24/2025 | PERRY, CROSS CULVERT (#88081) | Cross culvert (#88081) located 0.21 of a mile east of Burby Road. FHWA INFRA Grant recipient. | Emory Lovely | - | $918,000 | 624-3380
Highway Safety and Spot Improvements | 026630.10 | 09/24/2025 | ROBBINSTON, LARGE CULVERT (#47367) | Large culvert (#47367) located 0.15 of a mile north of Granite Cliff Lane. FHWA INFRA Grant recipient. | Emory Lovely | - | $1,620,000 | 624-3380
Highway Safety and Spot Improvements | 026630.08 | 09/24/2025 | DENNYSVILLE, ROUTE 1 (#47382) | Large culvert (#47382) located 0.27 of a mile north of Shipyard Road. FHWA INFRA Grant recipient. | Wayne Frankhauser | - | $4,820,000 | 624-3490
Highway Safety and Spot Improvements | 024277.00 | 10/08/2025 | BAILEYVILLE, ROUTE 9 LC# 46925 | Large culvert (#46925) located 0.39 of a mile west of Route 1. | Emory Lovely | - | $1,014,000 | 624-3380
Highway Safety and Spot Improvements | 026398.00 | 11/19/2025 | BROOKS, ROUTE 7 | Cross culvert (#51171) located 1.09 miles north of Morgan Pitch Road. | Emory Lovely | - | $1,005,000 | 624-3380
Highway Safety and Spot Improvements | 025433.00 | 11/19/2025 | KITTERY, ROUTE 1 BYPASS-GORGES ROAD | Located at the Intersection of Route 1 Bypass and Gorges Road. | Jeffrey Tweedie | - | $408,000 | 624-3420
Highway Safety and Spot Improvements | 025435.00 | 11/19/2025 | KITTERY, ROUTE 1 | Located at the intersections of Routes 1 and 101 and Route 1 and Haley Drive, as well as the entrances to the Kittery Outlet Centers both north and south of Dexter Lane. | Jeffrey Tweedie | - | $1,620,000 | 624-3420
Highway Safety and Spot Improvements | 024339.00 | 12/17/2025 | SKOWHEGAN, ROUTE 2W | Located at the intersection of Madison Avenue and Commercial Street. | Jeffrey Tweedie | - | $902,000 | 624-3420
Maintenance | 026630.13 | 06/11/2025 | MACHIAS-CALAIS, ROUTE 1/ROUTE9/ROUTE 190 | Route 1: Beginning at the Whitneyville town line and extending north 63.17 miles. Route 190: Beginning at Route 1 and extending southeast 6.50 miles. FHWA INFRA Grant recipient. | Emory Lovely | - | $135,000 | 624-3380
Maintenance | 026140.00 | 07/16/2025 | STATEWIDE, RWIS ITS | Road Weather Information System (RWIS). | Jeffrey Tweedie | - | $2,140,000 | 624-3420
Maintenance | 027112.00 | 07/16/2025 | STATEWIDE, RWIS ITS | Install Road Weather Information systems (RWIS) at Statewide locations. | Jeffrey Tweedie | - | $975,000 | 624-3420
Maintenance | 028704.00 | 10/08/2025 | SOUTHWEST HARBOR, ROUTE 102A | Beginning 0.01 of a mile south of Seascape Lane and extending south 0.50 of a mile. | Emory Lovely | - | $1,125,000 | 624-3380
Maintenance | 024187.00 | 11/19/2025 | STATEWIDE, I-295 FIBER PROJECT ITS | Intelligent Transportation System (ITS) fiber/cameras/queue detection. | Jeffrey Tweedie | - | $2,624,000 | 624-3420
Multimodal | 023921.01 | 02/05/2025 | BRUNSWICK INTERMODAL CENTER - PHASE II | Beginning at Union Street and extending west 0.13 of a mile. | Jeffrey Tweedie | - | $665,000 | 624-3420
Multimodal | 019426.10 | 03/26/2025 | SCARBOROUGH, EASTERN TRAIL | Eastern Trail bicycle and pedestrian connection. Beginning at Nonesuch River and extending east 0.72 of a mile to Pleasant Hill Road. | Jeffrey Tweedie | - | $5,107,000 | 624-3420
Multimodal | 019426.00 | 03/26/2025 | S. PORTLAND-SCARBOROUGH, EASTERN TRAIL | Beginning at Pleasant Hill Road and extending north 0.83 of a mile to Gary L. Maietta Way. | Jeffrey Tweedie | - | $1,867,000 | 624-3420
Multimodal | 024357.00 | 03/26/2025 | EASTPORT, HIGH ST. SIDEWALKS | Beginning at Battery Street and extending north 0.27 of a mile. | Jeffrey Tweedie | - | $600,000 | 624-3420
Multimodal | 029516.00 | 04/23/2025 | STOCKTON SPRINGS, SHIP | Dock replacement off Dock Road. | Jeffrey Tweedie | - | $80,000 | 624-3420
Multimodal | 028474.00 | 06/11/2025 | BANGOR, 14TH STREET | Beginning at Ohio Street and extending northeast 0.37 of a mile to Valley Avenue. | Jeffrey Tweedie | - | $470,000 | 624-3420
Multimodal | 024769.00 | 06/25/2025 | AUGUSTA HIGH-VISIBILITY CROSSWALKS | High-Visibility Pedestrian Crossing Demonstration project. Located at multiple locations that will include innovative treatment such as Rectangular Rapid Flashing Beacons (RRFBs), dynamic pedestrian signage, thermoplastic crossings, and in-road lighting. | Jeffrey Tweedie | - | $300,000 | 624-3420
Multimodal | 026232.00 | 08/13/2025 | BRUNSWICK, BOAT RAMP SHIP | Located 0.45 of a mile south of Pennell Way. | Jeffrey Tweedie | - | $350,000 | 624-3420
Multimodal | 018469.00 | 08/13/2025 | PORTLAND - UNION BRANCH TRAIL | Multiuse trail along the abandoned Union Branch railway extending from Park Avenue to Forest Avenue. | Jeffrey Tweedie | - | $3,096,000 | 624-3420
Multimodal | 022216.00 | 08/27/2025 | HOULTON, SIDEWALKS | Sidewalks on Market Square, Water Street, Broadway, and Main Street for 0.53 of a mile. | Jeffrey Tweedie | - | $1,615,000 | 624-3420
Multimodal | 027754.00 | 10/08/2025 | EASTERN TRAIL, NORTH BERWICK-WELLS-KENNEBUNK | Connect gaps along the Boston & Maine Railroad. 2023 RAISE Grant recipient. | Jeffrey Tweedie | - | $5,510,000 | 624-3420
Multimodal | 027752.00 | 10/15/2025 | LINCOLNVILLE AND ISLESBORO FERRY TERMINALS FACILITY IMPROVEMENTS | Ferry terminal upgrades at the Lincolnville and Islesboro Ferry Terminals. Rural Ferry Grant recipient. | Jeffrey Tweedie | - | $31,255,000 | 624-3420
Multimodal | 027610.00 | 10/22/2025 | VINALHAVEN, MAIN STREET, SHIP | Replacement of Boat Ramps in downtown Vinalhaven. | Jeffrey Tweedie | - | $504,000 | 624-3420
Multimodal | 027536.00 | 11/12/2025 | SCENIC BYWAYS - RANGELEY LAKES RECREATIONAL FACILITIES | Develop two facilities for interpretive signage, parking, and connectivity to outdoor recreational facilities. Scenic Byways Grant Recipient. | Jeffrey Tweedie | - | $654,000 | 624-3420
Multimodal | 019397.01 | 11/13/2025 | BOOTHBAY/BOOTHBAY HBR SIDEWALK-PHASE 2 | Beginning 0.08 of a mile south of Hackmatack Road and extending north 0.63 of a mile to the traffic circle, then continuing north 0.14 of a mile on Back River Road. | Jeffrey Tweedie | - | $1,100,000 | 624-3420
Multimodal | 026960.00 | 12/03/2025 | VINALHAVEN, PARKING LOT/SIDEWALK RECONSTRUCTION | Located at the Vinalhaven Ferry Terminal. | Jeffrey Tweedie | - | $1,800,000 | 624-3420